## Feuil1
Monitoring Issue/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Railway Facilities | Grant of the Railway Concession (article 12.1.1 c of the Convention) | Not specified | The State |  |  | The Ministry in charge transport, the Ministry in charge of finances and the Ministry of economy and planification | Pending | Railway Agreement | Railway Agreement | Railway Concession | The Railway Project Company will not be entitled to carry out Railway Operations and the start the construction of the Railway
| Prepare or approve a Waste Management Procedures (article 29.4(a) of the Convention) | Prior to Commencement of work on Project Area (article 29.4(a) of the Convention) | Railway Project Company/Cam Iron |  |  |  | Pending | The Convention, Good International Industry Practice, Legislation (article 29.4 of the Convention) |  | waste management plan | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
| Complete Railway Commissioning (article 12.1.1 (i) and (j) of the Convention) | Within 6 years following the Date of Entry into Force, which shall occur at the latest 18 months of the Signature Date (article 3.6 (a)) of the Convention) | Railway Project Company/Cam Iron /the State |  |  | The Ministry in charge of transport | Pending |  | Railway Agreement | Finding of Compliance | A penalty for Delay Breacn Event of 70 000$ US per day of the delay if the delay Railway Commissioning result in a delay in the Project Commissioning Article 50.3 (a)(i) of the Convention
Note on A6: Road Map of the Mbalam Mining Convention Railway Facilities mean the Mainline Railway, the Initial Spur Lines (which is the standard gauge heavy haul railway, located within the Railway Area, in the case of the territory of Cameroon connecting the junction of the Mainline Railway to the Mine Loading Area or the junction of the Mainline Railway to the Congo Border Terminal) and, and eventually as the case may be any Additional Spur Lines. As per article 1 of the Convention defining Project Commissioning, the Contruction Phase with respect to the Railway Facilities begins from the Date of Entry into Force until Project Commissioning. The Railway Project Company is the entity in charge of the construction, procurement and exploitation of the Railway Facilities, this in accordance with: 1) the Railway Specifications detailed in the Railway Agreement which will describe the technical requirements of the Railway Faciliities based on the Railway Master Plan provided to the Railway Project Company by the State; 2) the Railway Concession granted to the Railway Project Company, by the appropriate authority, the terms of which are equally set out in the Railway Agreement. It should be noted that the signing of the Railway Agreement Constitute a condition precedent to the Entry into Foce of the Convention (Cf condition precedents to fulfilled on or before May 29, 2014). To this end, pursuant to the setting up of the Railway Project Company and the signing of the Railway Agreement, the contruction phase compliance with respect to Railway Facilities will consist in: - Obtaining the Railway Concession; - Requesting and obtaining the railway project lease; - Carrying out the design and construction of the Railway Facilities; - And proceeding with the Commissioning
Note on B6: Road Map of the Mbalam Mining Convention Railway Concession is defined under article 1 of the Convention as a concession granted by the appropriate authority and the terms of which are set out in the Railway Agreement. The beginning of the construction of the Railway Facilities is subject to the Railway Project Company being granted the right to carry out Railway Operations, which include the design, construction, operation and maintenance of Railway Facilities. Pursuant to article 12.1.1(c) of the Convention, the Railway Project Company shall only have the right to carry out Railway Operations from the later of the date when: - the Railway Project Company becomes Party to the Convention by delivering to the State the Accession Notice in accordance with article 6.4 of the Convention. The deliverance of such executed Accession Notice is a Condition Precedent to the entry into force of the Convention and should therefore occur before the Date of Entry into Force (that is to say during the pre-contractual phase as defined in this Roadmap); - the Railway Concession is granted to the Railway Project Company.
Note on C6: Road Map of the Mbalam Mining Convention : The Convention does not specify the deadline for the grant of the Railway Concession by the State. The grant of the Railway Concession is not included within the Conditions Precedents to be satisfied for the purpose of the entry into force of the Convention. However, article 20.3 of the Convention states that "the State shall grant, to each of the Railway Project Company and the Mineral Terminal Project Company, Project Leases over the areas identified in the Railway Concession and the Mineral Terminal Concession as being needed to construct and operate the Railway and the Mineral Terminal...". It results from this article that the area over which the Project Lease for the construction of Railway Facilities shall be granted is defined by the Railway Concession. As per article 4.1(z)(ix)of the Convention, the grant of the Project Lease is a Condition Precedent to the entry into force of the Convention and shall therefore occur before the commencement of the Construction Phase, which means that the Railway Concession should also be granted before the beginning of the Construction Phase, as it contains the definition of the area covered by the Project Lease. We specify however that the said area shall also be provided by the Railway Agreement to be executed as a condition precedent to the entry into force of the Convention, which means that even if the Railway Concession is not granted before the Date of the Entry into Force of the Convention, the Project Lease can however still be granted before the Date of Entry into Force and the beginning of the Construction Phase.
Note on G6: Road Map of the Mbalam Mining Convention Concession contracts relating to railway transportation are actually signed by, i) the Ministry in charge of transport, ii) the Ministry in charge of finances, iii) the Ministry in charge of Economy and Planification.
Note on I6: Ernst & Young: According to article 1 of the Convention defining Railway Concession, the terms of such Railway Concession are set out in the Railway Agreement. The Railway Concession shall there be drafted on the basis of the Railway Concession.
Note on B7: Road Map of the Mbalam Mining Convention : In accordance with article 29.1(a) of the Convention, prior to commencing work on the Railway Area, the Railway Project Company shall prepare a waste management procedure and comply to it while performing the work. Where the work performed by a Contractor or Subcontractor, the waste management procedure is prepared by the said Contractor or Subcontractor and submitted to the Railway Project Company for approval.
Note on B8: Road Map of the Mbalam Mining Convention : Railway Commissioning includes the commissioning of the Mainline Railway and the Initial Spur Line by the Railway Project Company. We would like to draw your attention to the fact that Railway Facilities may include one or more Additional Spur Line but the commissioning of such Additional Spur is not included within Railway Commissioning and is not required to occur within the deadline provided by the Convention for Project Commissioning.
Note on C8: Road Map of the Mbalam Mining Convention : The deadline for the Railway Commissioning is not provided by the Convention but stipulates that the Project Commissioning shall within 6 years following the Date of Entry into Force or such later date as otherwise agreed. Which means that Mine Comissioning shall occur before or on the date of the Project Commissioning. Please note that as per article 12.1.1 (j) of the Convention, the issuance by the State to the Railway Project Company of a Finding of Compliance will constitute the Railway Commissioning. In this respect the afore-mentioned article provides that the State may raise reservations that the Railway has not been constructed in accordance with the Railway Specifications. In that case, such reservations must be resolve prior to the Railway Commissioning. The Railway Project will have a period of 180 days to do the works such as to allow the removal of such reservation. An additional delay of 90 days can be added to the 180 days to the extent that the Railway Project Company is diligently working to remove such reservations and can demontrates in good faith that the reservations cannot be resolved within the 180 days.
Note on D8: Road Map of the Mbalam Mining Convention Pursuant to article 12.1.1 (j) of the Convention, issuance by the State to the Railway Project Company will constitute the Railway Commissioning. The State shall therefore be regarded as one of the Parties accountable for compliance.
Note on G8: Ernst & Young: The Convention does not specify which authority is, within the State, in charge of delivering to the Railway Project Company, the Finding of Compliance constituting the Railway Commissioning. It results from the defnition of the "Finding of Compliance" that it shall be delivered according both to the Specifications applicable for the construction of the Railway and to the Legislation. We assume that the Ministry of transport will be in charge of providing to the Railway Project Company, Railway Specifications on the basis of which the Railway shall be constructed, as the said Railway Specifications should be based on the National Railway Plan of the State, drafted by the Ministry of Transport. We therefore consider that the Ministry of transport is the authority within the State which may have the best competences to deliver the Finding of Compliance with respect to Railway Compliance.