## Feuil1
Conditions Precedents to be satisfied | Required actions or operation | Date for compliance (time frame, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance (State) | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Delivery of an updated Feasibility Study including the Project Economic Model (articles 4.1 and 4.3. (a) (ii)) | Update the actual Feasibility Study | May 29, 2013 | Cam Iron | Bruno | 2012-04-20 |  | Completed | The first Feasibility Study presented to the Government of Cameroon on April 15, 2011 / Independant reserve statement on the changes in construction and operating cost and on the Production Profile / Updated Project Economic Model |  | Updated Feasibility Study including an update of the Project Economic Model and, if necessary, of the Environmental Impact Study; Aknowlegment receipt from the General Secretary of the Prime Minister and from the Ministry of Industry, Mines and Technological Development, of the notification of satisfaction of the Condition Precedent | The State shall have no obligation to present the Enabling Law to the Parliament if this condition is not satisfied at the date for compliance
| File the updated Feasibility Study with the Ministry of Mines (section 47 of the Mining Code) |  |  | Herve | 2012-01-05 |  | Completed
| Notification of such update to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention. |  |  | Bruno | 2012-05-29 |  | Pending |  |  |  | The Convention may be terminated and any right arising from the Convention may be revoked
Note on A4: Road Map of the Mbalam Mining Convention - Conditions Precedent : Conditions Precedent are the ones contained in article 4.1. of the Convention. The Parties’s rights and obligations under the Convention shall only become effective subject to the prior satisfaction of the said conditions. In other words consequence, the entry into force of the Convention is subject to the prior satisfaction of these conditions. We would like to draw your attention to the fact that pursuant to article 3.5 of the Convention, the following documents were suppose to be delivered at the Signature Date: - A letter agreement from Sundance to the State, which provides notably for a guaranty by Sundance of the obligations of Cam Iron under the Convention prior to the Date of the Entry into Force and an agreement to pay or cause to be paid to the State any breakup fee required to be paid in accordance with article 4.6 or the Bonus Payment payable pursuant to article 36.5; - The certificate of appropriate public officiels required under article 3.5 (b).
Note on B4: Road Map of the Mbalam Mining Convention - Conditions Precedent: Required actions or operations are the ones to be carried out in order to reach to the expected result, that is to say for the satisfaction of the condition precedent.
Note on D4: Road Map of the Mbalam Mining Convention - Conditions Precedent: Party means either the State or CamIron or any other Project Company (the Mine Project Company, the Railway Project Company or the Mineral Terminal Project Company), depending on the case. This results from article 1 of the Convention according to which "Parties means all of the parties to this Convention, and, as applicable, to any Project Agreement, and Party means any one of them", it being specified that all the Project Companies are required to become a Party to this Convention (see the table on point 2.2.3 of this Convention concerning the "Conditions Precedents to be satisfied on or before 29 May 2014". With respect to Cam Iron, please note that: - pursuant to article 3.5 of the Convention, a letter agreement from Sundance in favour of the State providing, among other things, for a guarantee by Sundance of the obligations of Cam Iron under the Convention prior to the Date of Entry into Force (with the commitment to pay to the Sate a break-up fee in certain circumstances, was supposed to be delivered on the Signature Date. This means that in fact, Sundance has committed itself to guaranty the performance by Cam Iron of its obligation under the Convention until the Date of Entry into Force. As a consequence, it must be kept in mind that any reference to Cam Iron as a Party to the Convention shall also involve Sundance in this Roadmap, at least until the Date of the Entry into Force; - according to article 3.4 of the Convention, Cam Iron expressly consent to be jointly and severally liable to the State for all the obligations undertaken by the Mine Project Company, the Railway Project Company and the Mineral Terminal Project Company under the Convention and the various Project Agreements. Thus, it shall be kept in mind that where a Project Company is presented as being the "Party accountable for compliance", Cam Iron remain concerned and specific actions necessary for compliance may be taken by Cam Iron as set forth in the column relating to the individual responsible for action in this Roadmap.
Note on E4: Road Map of the Mbalam Mining Convention - Conditions Precedent: This refers to the specific individual responsible for compliance within the Sundance group when Cam Iron or any other Project Company is the Party accountable for compliance.
Note on F4: Road Map of the Mbalam Mining Convention - Conditions Precedent: This is the specific deadline assigned to the person in charge of action within Cam Iron or Sundance.
Note on G4: Road Map of the Mbalam Mining Convention - Conditions Precedent: This is the authority in charge of compliance where the State is the Party accountable for compliance.
Note on H4: Road Map of the Mbalam Mining Convention - Conditions Precedent: We would like to draw your attention to the fact that as per article 4.5(c) of the Convention, "each Party shall notify the other Party in writting of the occurrence of any event likely to prevent the Conditions Precedent from being satisfied before, or no later than, on the CP Long Stop Date, as soon as the Party became aware of the relevant event". Thus, if any of the actions necessary for the satisfaction of the Condition Precedent which the subject of this table is prevented for any reason, Cam Iron should, without delay, bring this situation to the attention of the State.
Note on K4: Road Map of the Mbalam Mining Convention - Conditions Precedent : The output shall alway include a notification, in French and English with acknowledment of receipt when delivered in Cameroon, of any satisfaction of the Conditions Precedent as and when they occur (article 4.5. of the Convention). Pursuant to article 64 of the Convention, such notifications shall be made to: - the General Secretary Office of the Prime Minister; - and the Ministry of Industry, Mines and Technological Development. Copy of the written notice (notification) shall be sent to the State Project Comimittee and to Patton Boggs LLP.
Note on A6: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Feasibility Sudy contemplated in article 4.1 of the Convention is the Project definitive feasibility which was submitted to the State on 15 April 2011 in accordance with section 46 of the Mining Code. This Feasibility Study is different from the "Beneficiation Feasibility Study" which shall be submitted to the State within 24 months from the Date of the First Commercial Shipping, if a "Positive Beneficiation Determination" has not occured (see our map relating to "Beneficiation Facility" under Construction Phase (Construction Phase Monitoring Item). In fact, the Feasibility Study is related to the exploitation of the DSO and the Beneficiation Feasibility Study is related to exploitation of the iron ore subject to beneficiation.
Note on B6: Rod Map of the Mbalam Mining Convention - Conditions Precedent: Pursuant to article 4.1 (a) of the Convention, the update of the Feasibility Study shall include and merely focus on the followings: i) Details of the costs for the construction of the foundations required for a dual track and any dalays and direct costs such construction would cause to the construction of the Mainline Railway. These information should be presented distinctively, (a) for the first 250 km of the Railway from Lolabe and (b) for the entire Railway; ii) The impact on the construction time frame for building the Mainline Railway (from our understanding, this means that the updated Feasibility Study shall include an update of the time frame for the construction of the Mainline Railway; iii)The update to the independent reserve statement including changes in construction and operating cost, the production profile and the Project Economic Model; iv) A description of the key components of and assumptions associated with reaching the Design Capacity (defined under article 1 of the Convention as meaning 100 000 000 tonnes of iron ore in a Calendar Year - these one hundred million tonnes consisting in 35 000 tonnes plus 65 000 000 wet tonnes - based on the assumption to be detailed in the Railway Agreement) and an annual capacity of 200 000 000 wet tonnes. The information required on point i) hereabove concerning the costs of the foundation of the dual track are of a great importance to the Government. In fact, pursuant to article 11.3 of the Convention, following receipt of the updated Feasibility Study, the Government may, in its sole discretion, elect by the Date of Entry into Force to fund these costs. Please note that the update of the Feasibility Study may also entail an update of the Environmental Impact Study that was submitted to the State along with the filing of the Feasibility Study on April 15, 2011.
Note on I6: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Updated Project Economic Model will take into account the new economic details provided in the Updated Feasibility Study.
Note on B8: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Convention does not require for the approval of the updated Feasibility Study by the Ministry of Mines. The Mining Legislation provides for the examination of the application for the Exploitation Permit, including the feasibility study submitted in this respect, by the services in charge of mines, within a delay that is not the same in the Mining Code (60 days) and in the Minng Code Implementing Decree (90 days). However, the Mining Legislation is silent regarding any changes made to the elements, such as the feasibility study, constituting the application file for the mining permit. In any case, the analysis of the Convention shows that the Parties did not intend to give to the Government the right to challenge the findings of the updated Feasibility Study (as a confirmation of this, the prior approval of the updated Feasibility Study is not provided as a Condition Precedent in the Convention and is not even required by it).
Note on B9: Road Map of the Mbalam Mining Convention - Conditions Precedent: Pursuant to article 4.5 (a) of the Convention, "each Party shall justify to the other Party any satisfaction of the Conditions Precedent as when they occur". According to article 64 of the Convention, the notification should be made by delivering to the State a notice wrtitten both in French and in English at the adressees provided in article 64 of the Convention: - The General Secratary Office of the Prime Minister; - The Ministry of Industry, Mines and Technological Development. Copy of all notifications to the State should be adressed to the State Project Committee. To recall, the State Project Committee is the committee that shall be established by the State in order to coordinate with Cam Iron and the Project Companies with respect to the performance of the State's responsabilities under the Project Agreements, as set forth in article 47 of the Mining Convention. The difficulty here concerning notifications to the State Project Committee of the satisfaction ot the Condition Precedent regarding the update of the Feasibilty Study is that the deadline provided for in the Convention for the establishment of this committee is after the Date of Entry into Force, that is well after the fulfillment of the condition. The Government is not required to set up the State Project Committee before the Date of Entry into Force. We recommend, however, to urge to Government for the establishment of this commitee as soon as possible given the major role it has to play in facilitating the Project. Please note also note that the firm Patton Boggs LLP (see it adress for notices in article 64 of the Convention) must receive a copy of all notices sent to the Government of Cameroon in connection with the Convention.
Note on L9: Road Map of the Mbalam Mining Convention - Conditions Precedent (article 4. 3 (b) and (c): In the event that such Condition Precedent is not satisfied or waived on the compliance date, the Parties shall meet to decide within 90 days as from the date for compliance, either to waive in writing the non satisfied condition, or to postpone the date for compliance. Failure to reach an agreement with respect to the Conditions Precedent will lead to the cancellation of the Convention.