## Feuil1
Conditions Precedents to be satisfied | Required actions or operation | Date for compliance (time frame, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance (State) | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Delivery of an updated Feasibility Study including the Project Economic Model (articles 4.1 and 4.3. (a) (ii)) | Update the actual Feasibility Study | 2013-03-12 | Cam Iron | Bruno | January 20, 2013 |  | Completed | The first Feasibility Study presented to the Government of Cameroon on April 15, 2011 / Independant reserve statement on the changes in construction and operating cost and on the Production Profile / Updated Project Economic Model |  | Updated Feasibility Study including an update of the Project Economic Model and, if necessary, of the Environmental Impact Study; Aknowlegment receipt from the General Secretary of the Prime Minister and from the Ministry of Industry, Mines and Technological Development, of the notification of satisfaction of the Condition Precedent | The State shall have no obligation to present the Enabling Law to the Parliament if this condition is not satisfied at the date for compliance
| File the updated Feasibility Study with the Ministry of Mines (section 47 of the Mining Code) |  |  | Herve | February 15, 2013 |  | Completed
| Notification of such update to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention. |  |  | Bruno | March 12, 2013 |  | Pending
Delivery of a commitment letter for the Debt required by the Project (article 4.1. (b)) | Negotiate and sign a commitment letter with the Lenders or the Lender if there only one. | August 29, 2013 | Cam Iron | Emmanuel | June 25, 2013 |  | Pending
| Deliver the commitment letter to the State and, specifically, to the General Secretary of the Prime Minister, with a copy to the Ministry of Industry, Mines and Technological Development, to Patton Boggs and to the State Project Committee when the said Committee will be established |  | Cam Iron |  | August 29, 2013 |  | Pending
Note on A6: Patient: Delivery of an updated Feasibility Study including the Project Economic Model (articles 4.1 and 4.3. (a) (ii))