## Feuil1
Conditions Precedent to be satisfied | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge | Due Date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Contribuate in the Management and funding of the direct environmental and social impact by tthe creation creation of Fund Commitee | Contribuate in the Management and funding of the direct environmental and social impact by tthe creation creation of Fund Commitee | During the Project | Project Compagnies / State |  | Cam Iron undertakes to make a cash contribution of twenty million (20,000,000) US Dollars per year for five (5) years commencing on the Date of Entry into Force to finance the South and East Regions Plan | Ministry of Finance : Ministry of Forets |  |  |  |  | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
The Project Companies shall also contribute or shall cause Marketing Company to contribute to the Special Development Fund | The Project Companies shall also contribute or shall cause Marketing Company to contribute to the Special Development Fund | During the Project | Project Compagnies / State |  | The Project Companies shall also contribute or shall cause Marketing Company to contribute to the Special Development Fund (which in addition to other uses may be used for university and technical educational purposes) an amount equal to 0.75% of the gross sales price of Mbalam Ore sold (whether it is sold as part of Blended Ore or otherwise). | Ministry of Finance : Ministry of Forets
Note on F6: Road Map of the Convention - Exploitation Phase Community: The State hereby agrees to hereinafter organize the Special Development Fund. With respect to the long term funding of the development of the area impacted by the Project, the State intends to allocate thirty percent (30%) of its portion of the base charge tariff paid by Expansion Capacity users and 30% of the lease payments it receives in connection with the Mineral Terminal Site and Railway Site to fund the Special Development Fund.