## Feuil1
Monitoring Items / Categories | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Global Monitoring | Provison of a report containing details on all works undertaken in connection with the Exploitation Permit | March 31 2015 and thereafter March 31 of each year. | Mine Project Company |  | 31 March every year from 2015 |  | Not yet done | Provison of a report containing details on all works undertaken in connection with the Exploitation Permit, in particular the details relating to the production of all Products, the development works, exploration works and other useful information in terms of the geology and mining resources in the Exploitation Area |  | Compliance with the provison of the Mining Legislation | Fine of from 5 000 000 XAF - 25 000 000 XAF as per Section 108 of the Mining Code
| Provision of specific information requested from mining companies listed on the Australian Securities Exchange in respectof the reporting of resource and reserves | March 31 2015 and thereafter March 31 of each year. |  |  | 31 March every year from 2015 |  |  | Provision of specific information requested from mining companies listed on the Australian Securities Exchange in respectof the reporting of resource and reserves
| Provision of statistical report for each permit and autorisation comprising: - the number of mining permit or authorization; the date of establishment of the renewal, an analytical summary of the progress report of the works carried out during the previous year,executive geological and mining report illustrated by an appropriate plan; the number of staff working Days; the weight, nature and content of obtained market minerals, the weight, nature and content of various consignments of exported minerals indicating the places and dates of dispatch and delivery; report of stocks of raw products and market products as at December 31; the list of accidents which have led to more than 4 Days of industrial disability and; the volume, in case of the geothermal deposit, spa or thermo-mineral waters as concerns the statistics required. | Prior to March 31 2015 and thereafter March 31 of each year. |  |  | Prior to March 31 2015 and thereafter March 31 of each year. |  |  | Provision of statistical report for each permit and authorisation comprising: - the number of mining permit or authorization; the date of establishment of the renewal, an analytical summary of the progress report of the works carried out during the previous year,executive geological and mining report illustrated by an appropriate plan; the number of staff working Days; the weight, nature and content of obtained market minerals, the weight, nature and content of various consignments of exported minerals indicating the places and dates of dispatch and delivery; report of stocks of raw products and market products as at December 31; the list of accidents which have led to more than 4 Days of industrial disability and; the volume, in case of the geothermal deposit, spa or thermo-mineral waters as concerns the statistics required.
| Provision of the status of the implementation of the Environmental and Social Assessment and Management Plan | Within the time set forth in the legislation | Project Company |  | Within the time set forth in the legislation |  |  | Provision of the status of the implementation of the Environmental and Social Assessment and Management Plan
| Provision of the audited financial statements of each respective Project Company prepared by the Independent Accountant | Within the time set forth in the legislation | [5 empty] | Provision of the audited financial statements of each respective Project Company prepared by the Independent Accountant
| Provision of a reasonably satisfactory report to the Minister with respect to mineral reserves and resources compliant with JORC, NI-43-101, SAMREC or mutually agreable standards | Within the time set forth in the legislation | [5 empty] | Provision of a reasonably satisfactory report to the Minister with respect to mineral reserves and resources compliant with JORC, NI-43-101, SAMREC or mutually agreable standards
| Provison of the obligations of the other Project Companies in terms of preparation and submission of reports to the State as specified in each Specific Agreement and include, notably, the provision of the audited financial statements within the time limits set frth in the Legislation | Within the time set forth in the legislation | [5 empty] | Provison of the obligations of the other Project Companies in terms of preparation and submission of reports to the State as specified in each Specific Agreement and include, notably, the provision of the audited financial statements within the time limits set frth in the Legislation
Note on C10: Enga Kameni: The exact date for the fulfilment of this condition is not clear. Neither the mining code nor its decree of application specifically mentions the time with which the Environmental and Social Assessment and Management Plan must be implemented. It is recommended that this plan be dran and implemented as soon as the commencement of the project
Note on F10: Enga Kameni: The exact date for the fulfilment of this condition is not clear. Neither the mining code nor its decree of application specifically mentions the time with which the Environmental and Social Assessment and Management Plan must be implemented. It is recommended that this plan be dran and implemented as soon as the commencement of the project