## Feuil1
Land compliances | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Expropriation Issues (article 28 of the Convention) | Carry all expropriation for delineating any Project Area for Mining Operations in compliance with the provisions of the Mining Code | During Exploitation Phase | Mine Project Company / State |  |  | Ministry of Domanial Affairs |  | Mining Code |  | Start the Mining Operations on expropriated lands | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
| Carry all expropriation for delineating any Project Area for Railway Operations and Mineral Terminal Operations, in compliance with the provisions of the Mining Code |  | Railway Company / Mineral Terminal Company / State |  |  | Ministry of Domanial Affairs
Publication of lands subject to expropriation | Lands concerned by the expropriation measures and by the indemnities paid to Third Parties shall be published in the Official Gazette | By the Time an agreement is met on the list of lands to be subject to expropriation | State |  |  | General Secretariat of the Prime Minister |  | List of Lands subject to expropriation |  | Publication of all lands subject to expropriation in the Official Gazette | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Obtain/ Execute the Project Leases in order to allow the Project Companies or their Contractors and Subcontractors to: 1-Temporarily use and occupy any portion of land located either outside the Exploitation Area, the Railway Area or the Mineral Terminal Area, for the purposes of the Project including for the procuring of building materials or within the Exploitation Area, the Railway Area or the Mineral Terminal Area ahead of the grant of a Project Lease for the purposes of the Project including for the procuring of building materials. 2- Determine more precisely the rights and obligations of the Project Company in the conduct of the Project Operations it is entitled to carry out | Request the Lease to the State or to its competent decentralized organ or to the competent company authorized to grant State concessions | During Exploitation Phase | Cam Iron/ Project Companies / Contractors and Subcontractors |  |  | State decentralized organ or competent company authorized to grant State concessions |  |  |  | Execute the Project Leases | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Obtain the granting from the State of the Project Leases
Temporary Use and Occupation of sites for construction camps for the purposes of the Project | Request to the State temporary rights for the use or occupation of sites for construction camps for the purposes of the Project | During Exploitation Phase | Cam Iron / Project Companies / Contractors and Subcontractors / State |  |  | State decentralized organ or competent company authorized to grant State concessions |  |  |  | Obtanin rights for temporary use and occupation of lands for the purpose of the Project | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Benefit of the right to access and use the lands contemplated by the Project Leases and the Specific Agreements under the conditions determined by the said documents. | Benefit of the right to access and use the lands contemplated by the Project Leases and the Specific Agreements under the conditions determined by the said documents. | During Exploitation Phase | Cam Iron / Project Companies | [7 empty] | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
State Covenants | Ensure that the State various ministries do not create or authorize material conflicting land use with respect to the land on which the Project Operations are being undertaken or conservation operations which are being undertaken by Cam Iron or a Project Company to offset the impact of Project Operations. | During Exploitation Phase | State |  |  | Ministtry of Mines / Ministry of Domanial Affairs |  |  |  | Respect all Covenants | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Enforces any provisions of any concession, licence agreement, right or title that it has granted or entered into with a Third Party where the failure to do so is allowing that Third Party to cause or create a materially adverse land use with respect to the Project Operations
Does not grant to a Third Party any rights to the land described in the Mineral Terminal Agreement as being set aside for expansion of the Mineral Terminal to achieve the Design Capacity
Does not permit any ministry to utilise any of the land described in the Mineral Terminal Agreement so set aside without having sought the confirmation from the Mineral Terminal Project Company that it no longer has any potential need for that land for the purpose of creating Expansion Capacity
Cam Iron/ Project Companies obligations: Prohibition on the right to sublease, assign or pledge. The Project Companies shall not have the right: | (a) to sublease all or part of the Project Areas | During Exploitation Phase | Cam Iron / Project Companies / Contractors and Subcontractors |  |  |  |  | Project Leases | Project Leases | Respect the obligations with respect to the use of Lands under Project Leases | Respect the obligations with respect to the use of Lands under Project Leases
(b) to assign all or part of their rights in the Project Areas
(c) to mortgage, secure, pledge, assign by way of security, or grant any other security interest over all or part of any Project Area
Emergency access to land outside the Project Area | In case of emergency, take any reasonable step or measure in order to prevent any imminent hazard or emergency situation of which it will be advised in the areas immediately adjacent to the Project Areas after having informed competent authorities. | Whenever occurs a case of emergency | Cam Iron/ Project Companies / Contractors and Subcontractors
Note on C6: Road Map of the Mbalam Mining Convention - Land Issues : Pursuant to the provisions of article 3.6 (a), (a), Cam Iron undertakes that the Project Commissioning occur within six (6) years following the Date of Entry into Force or such later date as otherwise agreed. Whereas the definition given by the Convention on the Construction Phase refers to "the period commencing on the Date of Entry into Force until Project Commissioning". Thus, as Project Commissionning has to occur six years following the Date of Entry into Force and the Construction refers to the phase commencing on the Date of Entry into Force till Project Commissioning, we can assume that the Construction Phase consist on the 6 years period following the Date of Entry into Force.
Note on D6: Road Map of the Mbalam Mining Convention - Land Issues : The Mine Project Company shall be liable to pay all indemnities due to Third Parties as a result of: - Expropriations for the delineating any Project Aarea for Mining Operations; - Any disturbance of peaceful possession, by a Third Party, of the land they occupy or the activities they conduct therein as a result of: - the grant to such Project Company of rights to occupy this Project Area; or - the conduct of activities in the same area. - Any loss or damage caused to a Third Party or their assets by a such Project Company, its Contractors or Subcontractors, including their employees. Indemnities provided here above shall include the costs, indemnities and, more generally, all charges resulting from the application of measures aimed at releasing, and granting a right of enjoyment in, the taxable land are borne by the Mine Project Company. The Mine Project Company shall fulfil its payment obligation within thirty (30) Days following receipt of said terms and conditions for payment, expressly provided that the rights to occupy and enjoy any land granted to the Mine Project Company is conditional upon the prior payment, by the Mine Project Company. The Mine Project Company shall be liable for the payment of all fees, duties and charges incurred by any Governmental Entity in connection with the implementation and conduct of any expropriation procedure carried out.
Note on A9: Road Map of the Mbalam Convention - Land Issues : It is specified that the Project Leases shall not grant to their beneficiary any mining rights, rights in the subsoil or rights in the mining substances and other natural resources contained in the soil and/or the subsoil of the State (article 20.1)
Note on B9: Road Map of the Mbalam Mining Convention - Land Issues: Any Project Lease Request or proposed Additional Specific Agreement to the State shall be made either: - In the context of an Additional Facility Request; or - As a separate requirement, indicating the purpose of the Project Lease Request or the Additional Specific Agreement and indicate a detailed study specifying: - the situation, area, and layout of the lands for which the Project Lease or the Additional Specific Agreement is requested; and - the extent to which such request cannot be satisfied within the Exploitation Area, the Railway Area or the Mineral Terminal Area as they exist at the date of the Project Lease Request. Any Project Lease Request or proposed Additional Specific Agreement and any related rental fee, if applicable, shall be appraised and negotiated by mutual agreement between the Parties in compliance with the timetable determined by the party making the request or the proposal and the State according to the purpose of the request.
Note on B10: Road Map of the Mbalam Mining Convention - Land Issues: The State shall grant, to each of the Railway Project Company and the Mineral Terminal Project Company, Project Leases over the areas identified in the Railway Concession and Mineral Terminal Concession as being needed to construct and operate the Railway and the Mineral Terminal and these Project Leases shall: - Be for the term of the Railway Concession and the Mineral Terminal Concession; and - Be on terms usually associated with project leases in the territory of the State; and - Attract a rental of the greater of (i) a total of five hundred and ten million (510,000,000) CFA Franc or (ii) three (3) CFA Franc per square metre for the area comprising the Mineral Terminal Area, Railway Area and area of the Project Road Adjacent to the Railway (if not duplicative and continuing after the applicable portions of such road are dedicated to public use) per annum, paid half yearly in advance.
Note on B11: Road Map of the Mbalam Mining Convention - Land Issues : The State shall employ reasonable efforts (obligation de moyens), consistent with applicable standards, to promptly grant to the party the temporary use and occupancy rights requested, provided that the application is in accordance with the terms thereof and of the Legislation, and does not otherwise adversely impact on the rights of Third Parties or the Reserved Rights of the State. The party requesting such temporary rights shall indemnify the State and the other Project Companies against any damage or liability resulting therefrom. Any such request shall take into account existing use and condition (from an environmental, geological and social standpoint) of the land and take all reasonable measures to avoid or mitigate any negative effects thereon
Note on A12: Road Map of the Mbalam Mining Convention - Land Issues: However, the State or any Third Party appointed to represent the State may access these lands at any time subject to a prior notification to the relevant Project Company and shall comply with the applicable provisions of the Legislation and the caution and security rules in force on the site, of which it shall be advised by such Project Company.
Note on B12: Road Map of the Mbalam Mining Convention - Land Issues: However, the State or any Third Party appointed to represent the State may access these lands at any time subject to a prior notification to the relevant Project Company and shall comply with the applicable provisions of the Legislation and the caution and security rules in force on the site, of which it shall be advised by such Project Company.
Note on A13: Road Map of the Mbalam Mining Convention - Land Issues : Any violation of the State Covenant may be deemed a Compensation Event giving rise to Convention Compensation. The Project Companies shall give the State prompt notice of any event or circumstances known to them which has or could be reasonably be expected to result in conflicting land use or other violation of the State’s covenants so that the State may attempt to mitigate the impact, and the Project Companies shall cooperate with the State and use their reasonable efforts to mitigate any such impact.