## Feuil1
Required action or operation (what need to be done) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party action accountable for compliance | Person in charge | Due date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Carry out Mining Operations specified in the Exploitation Pemit (article 8) | Carry out Mining Operations specified in the Exploitation Pemit (article 8) |  | Mine Project Company |  |  |  | Pending | Exploitation Permit / Project Agreements / Mining Code |  |  | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Carry out Mining Operations not specified in the Exploitation Permit | Carry out Mining Operations not specified in the Exploitation Permit |  | Mine Project Company |  |  |  | Pending | Exploitation Permit / Project Agreements / Mining Code |  |  | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Comply with respective obligations to cooperate to ensure Mine Commissioning (article 9) | Comply with respective obligations to cooperate to ensure Mine Commissioning (article 9) |  | Mine Project Company / Cam Iron / State |  |  | Ministry of Mines | Pending | Convention / Mine Agreement |  |  | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Ensure ramping up of production of Product and that the Minimum Annual Ore Production will be reached in the third (3rd) full Calendar Year post Project Commissioning. | Ensure ramping up of production of Product and that the Minimum Annual Ore Production will be reached in the third (3rd) full Calendar Year post Project Commissioning. | During a period of three (3) Calendar Years from the Date of Project Commissioning | Cam Iron |  |  |  | Pending |  |  | Ensure ramping up of the production of Product and reach the Minimum Annual Ore Production in a period of (3) years after Project Commissioning. | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Maintain the Minimum Annual Ore Production measured on a rolling average over a thirty-six (36) month period as adjusted on a pro rata basis for periods in which no High Grade Ore is being mined from Exploitation Area or the area covered by the Nabeba Permit | Maintain the Minimum Annual Ore Production measured on a rolling average over a thirty-six (36) month period as adjusted on a pro rata basis for periods in which no High Grade Ore is being mined from Exploitation Area or the area covered by the Nabeba Permit | During any period in which High Grade Ore from the Exploitation Area is being mined | Mine Project Company |  |  |  | Pending |  |  | Maintain the Minimum Annual Ore Production during a 36 months period | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Carry out the Mining Operations diligently and in compliance with the Operating Standards, the Legislation, and, to the extent applicable, any specific standard contained in the applicable Project Agreements. | Carry out the Mining Operations diligently and in compliance with the Operating Standards, the Legislation, and, to the extent applicable, any specific standard contained in the applicable Project Agreements. | During Mining Operations | Mine Project Company |  |  |  | Pending | Project Agreements |  |  | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Submit to the State the production program of Mbalam Ore and the corresponding budget set for the following Calendar Year, which shall notably demonstrate Cam Iron’s ability to maintain the Minimum Annual Ore Production (article 9.3) | Submit to the State the production program of Mbalam Ore and the corresponding budget set for the following Calendar Year, which shall notably demonstrate Cam Iron’s ability to maintain the Minimum Annual Ore Production (article 9.3) | 30th September of each calendar year following Project Commissionning | Mine Project Company |  |  |  | Pending |  |  | Submission each year to the State of the production program of Mbalam Ore and the corresponding budget | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Keep an up-to-date inventory of its Assets at its expense (article 9.4) | Keep an up-to-date inventory of its Assets at its expense (article 9.4) | Each year | Mine Project Company |  |  |  | Pending |  |  |  | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Prohibition without State's prior consent to (i) transfer, with or without consideration, all or part of the Assets of the Mine Project Company and to (ii) create a security right or grant any other right whatsoever over said Assets. | Prohibition without State's prior consent to (i) transfer, with or without consideration, all or part of the Assets of the Mine Project Company and to (ii) create a security right or grant any other right whatsoever over said Assets. |  | Mine Project Company |  |  |  | Pending |  |  |  | Termination of the right granted to the Project Company /Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Note on A6: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: Before carrying Mining Operations, the Mine Project Company shall have firstly obtained from Cam Iron the transfer of the Exploitation Permit and of the Exploitation Lease.The grant of the Exploitation Lease to the Mine Project Company shall be for an initial term of twenty-five (25) years as from the Date of Entry into Force with an option to extend automatically on the extension of the Exploitation Permit subject to applicable conditions and requirements. The initial transfer of the Exploitation Permit from Cam Iron to the Mine Project Company shall be exempt from any Tax including any Bonus Payment. (Details of such transfer are contained in the Mining Facilities of the Construction Phase) The Exploitation Lease will therefore grant, according to its terms, the Mine Project Company the right to access and to occupy, on an exclusive and temporary basis, subject to the Reserved Rights of the State, the land located within the Exploitation Area to carry out the Mining Operations therein.
Note on B6: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: Before carrying Mining Operations, the Mine Project Company shall have firstly obtained from Cam Iron the transfer of the Exploitation Permit and of the Exploitation Lease.The grant of the Exploitation Lease to the Mine Project Company shall be for an initial term of twenty-five (25) years as from the Date of Entry into Force with an option to extend automatically on the extension of the Exploitation Permit subject to applicable conditions and requirements. The initial transfer of the Exploitation Permit from Cam Iron to the Mine Project Company shall be exempt from any Tax including any Bonus Payment. (Details of such transfer are contained in the Mining Facilities of the Construction Phase) The Exploitation Lease will therefore grant, according to its terms, the Mine Project Company the right to access and to occupy, on an exclusive and temporary basis, subject to the Reserved Rights of the State, the land located within the Exploitation Area to carry out the Mining Operations therein.
Note on A7: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: This refers to the situation where the Mine Project Company discovers a reasonably material amount of mineral substances other than iron ore within the framework of Mining Operations . In that case, the Mine Project Company and Cam Iron undertake to promptly notify this discovery to the Minister in accordance with the provisions of the Mining Legislation. If the Mine Project Company indicates its intention to exploit such other mineral substance within the Exploitation Area, this exploitation shall require the application and approval of a new mining title as well as the conclusion of a new mining convention, in accordance with the provisions of the Mining Code. The Mine Project Company shall have (2) years following the notification to the State of a discovery of another mineral substance within the Exploitation Area to request for a formal exploitation permit or start all negotiations with the State in other to exploit such discoveries, failing which the State shall have all rights to grant the exploitation permit of such discoveries to one or more Third Parties. However, the grant of the exploitation permit to any Third Party shall not materially interfere with the performance of Project Operations. Nonetheless, it is expressly agreed that the exploration and exploitation of any natural resources, including any mineral substances (including iron ore), outside the Exploitation Area, would fall outside the scope of this Convention.
Note on B7: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: This refers to the situation where the Mine Project Company discovers a reasonably material amount of mineral substances other than iron ore within the framework of Mining Operations . In that case, the Mine Project Company and Cam Iron undertake to promptly notify this discovery to the Minister in accordance with the provisions of the Mining Legislation. If the Mine Project Company indicates its intention to exploit such other mineral substance within the Exploitation Area, this exploitation shall require the application and approval of a new mining title as well as the conclusion of a new mining convention, in accordance with the provisions of the Mining Code. The Mine Project Company shall have (2) years following the notification to the State of a discovery of another mineral substance within the Exploitation Area to request for a formal exploitation permit or start all negotiations with the State in other to exploit such discoveries, failing which the State shall have all rights to grant the exploitation permit of such discoveries to one or more Third Parties. However, the grant of the exploitation permit to any Third Party shall not materially interfere with the performance of Project Operations. Nonetheless, it is expressly agreed that the exploration and exploitation of any natural resources, including any mineral substances (including iron ore), outside the Exploitation Area, would fall outside the scope of this Convention.
Note on A8: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations : Pursuant to the provisions of the Convention, Mine Commissionning shall mean the wet commissionning of Mining Facilities, associated with the Mining Operations, not including the Beneficiation Operations.
Note on B8: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations : Pursuant to the provisions of the Convention, Mine Commissionning shall mean the wet commissionning of Mining Facilities, associated with the Mining Operations, not including the Beneficiation Operations.
Note on A9: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: It being understood that the Minimu Annual Ore means the mining and selling of a minimum of twelve (12) million Tonnes of High Grade Ore from the Exploitation Area in any Calendar Year, commencing in the Calendar Year post Project Commissionning.
Note on B9: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: It being understood that the Minimu Annual Ore means the mining and selling of a minimum of twelve (12) million Tonnes of High Grade Ore from the Exploitation Area in any Calendar Year, commencing in the Calendar Year post Project Commissionning.
Note on C10: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations : It being understood that the High Grade Ore means iron ore with an iron content greater than 50% Fe, with limitations on AI203, SiO2 and Phosphorous which render the product suitable for direct shipping ore (DSO).
Note on A11: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations : For the Mine Project Company, carrying out Mining Operations in complying with all relevant Legislation shall consist of: - Following Good International Industry Practices in order to effectively manage the mineral resource; - Ensuring that all materials, supplies, facilities and equipment that the Mine Project Company or its Contractors and Subcontractors use within the framework of the Mining Operations are compliant with the Operating Standards, and remain in a good state of use; - Using the resources available in the Exploitation Area such as water, sand, gravel and wood, in the most rational manner possible, for the exclusive purposes of the Mining Operations; - Placing the scrap and waste in recipients built for that purpose, and dispose of such scrap and waste in accordance with the Operating Standards and Legislation; - Taking all usual measures taken in accordance with Good International Industry Practice in order to avoid damages to areas outside Mining Operations and prevent emissions in excess of approved levels and, in each case, mitigate any damages and emissions through customary means, including payment of damages; - Supervising in a competent manner and continuously develop the employees of the Mine Project Company during Mining Operations. To this end, the Mine Project Company shall develop training programmes to ensure the employees are skilled to perform the task they are employed for; - Ensure that its Contractors and Subcontractors comply, in their respective fields: (i) with the standards and practices required by the Project Agreements, including Good International Industry Practice; (ii) with the Legislation; (iii) with the Environmental and Social Assessment and Management Plan; and (iv) with the applicable Project Companies’ quality, safety and health policies; and (h) pay all Taxes, duties, fees and other miscellaneous payments provided for under this Convention and the Legislation.
Note on B11: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations : For the Mine Project Company, carrying out Mining Operations in complying with all relevant Legislation shall consist of: - Following Good International Industry Practices in order to effectively manage the mineral resource; - Ensuring that all materials, supplies, facilities and equipment that the Mine Project Company or its Contractors and Subcontractors use within the framework of the Mining Operations are compliant with the Operating Standards, and remain in a good state of use; - Using the resources available in the Exploitation Area such as water, sand, gravel and wood, in the most rational manner possible, for the exclusive purposes of the Mining Operations; - Placing the scrap and waste in recipients built for that purpose, and dispose of such scrap and waste in accordance with the Operating Standards and Legislation; - Taking all usual measures taken in accordance with Good International Industry Practice in order to avoid damages to areas outside Mining Operations and prevent emissions in excess of approved levels and, in each case, mitigate any damages and emissions through customary means, including payment of damages; - Supervising in a competent manner and continuously develop the employees of the Mine Project Company during Mining Operations. To this end, the Mine Project Company shall develop training programmes to ensure the employees are skilled to perform the task they are employed for; - Ensure that its Contractors and Subcontractors comply, in their respective fields: (i) with the standards and practices required by the Project Agreements, including Good International Industry Practice; (ii) with the Legislation; (iii) with the Environmental and Social Assessment and Management Plan; and (iv) with the applicable Project Companies’ quality, safety and health policies; and (h) pay all Taxes, duties, fees and other miscellaneous payments provided for under this Convention and the Legislation.
Note on C12: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations : It being understood that Project Commissionning may occur: - at the date Mine Commissionning occurs; - at the date Railway Commissioning occurs; - at the date Mineral Terminal Commissioning occurs.
Note on A14: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: However, with respect to transfer of Assets, except for the purposes of financing (but not refinancing in a manner that grants a security interest in the Assets of the Project Companies within the last five (5) years of the Mineral Terminal Agreement and Railway Agreement) the Project and in favour of the Lenders of such financing. Nonetheless, the State must not unreasonably withhold its consent to any transfer of Assets, where the transferee agrees to be bound by the obligations to the State under this Convention with respect to the Assets of the Mine Project Company.
Note on B14: Road Map of the Mbalam Mining Convention - Exploitation Phase Mining Operations: However, with respect to transfer of Assets, except for the purposes of financing (but not refinancing in a manner that grants a security interest in the Assets of the Project Companies within the last five (5) years of the Mineral Terminal Agreement and Railway Agreement) the Project and in favour of the Lenders of such financing. Nonetheless, the State must not unreasonably withhold its consent to any transfer of Assets, where the transferee agrees to be bound by the obligations to the State under this Convention with respect to the Assets of the Mine Project Company.