## Feuil1
Obligations relating to personnel | Required actions or operation | Date for compliance (time frame, deadline) | Party action accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Individual/authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Conclude the Collective Bargaining Agreement |  | 6 years from the Date of Entry into Force | Cam Iron/ Labor Ministry / Social Security Organization / Ministry of Employment |  |  | Labour Ministry / Trade Unions / Cam Iron |  |  |  | Collective Bargaining Agreement
Apply the Collective Bargaining Agreement | Project Companies and their affiliate incorporated as cameroonian compagnies shall apply the Convention Barngaining Agrement to their Cameroonian employees (article 32.1) | 6 years from the Date of Entry into Force | Project Companies and their affiliates incorporated as cameroonian companies
| Project Companies' Affiliates operating in Cameroon, Contractors and Subcontractors incorporated as foreign companies shall have the choice to enter into and apply the Collective Bargaining Agreement to their employees specifically used to carry out services in connection with the Project. |  | Project Companies' Affiliates operating in Cameroon, Contractors and Subcontractors incorporated as foreign companies
| Cameroonian employees of the Project Companies' foreign Affiliates, Contractors and Subcontractors incorporated as foreign companies shall be granted employment terms and conditions not less favorable than those provided for in the Collective Bargaining Agreement. |  | Project Companies' Affiliates operating in Cameroon, Contractors and Subcontractors incorporated as foreign companies
Priority to be given to Cameroonian nationals |  | 6 years from the Date of Entry into Force | Project Companies, Affiliates, Contractors and Subcontractors whether or not incorporated as Cameroonian entities
Apply the provisions on working time and annual leaves as set forth in Article 32.8 for Cameroonian employees and for employees whose work contract is subject to Legislation
Do not subject to Legislation work contracts of foreign employees working on Rosters during the Construction Phase
Apply the general employment provisions set forth in Article 32.10
Apply the HSECS (Health, Safety, Environment, Community and Security) provisions set forth in Article 32.11
Apply the process for Immigration Documents for Foreign Personnel provided in Article 32.12 | [7 empty] | Single Entry Application procedure to be set up by the State / The Protocol drafted by the Labour Committee outlining the procedure that must be followed for any and all Application as well as expected deadlines for the issuance of Immigration Documents
Apply the provisions on professional training and transfer of know-how (Article 32.5) |  |  | Main Contractors and Subcontractors
Timely provide the Labor Committee: | With details on the workforce (number, level of qualification, etc.) that shall be needed to carry out all the major construction and operation-related works of the Project. | 6 years from the Date of Entry into Force | Project Companies
With an annual report outlining the detail of the number of domestic and foreign employees who have worked on the Project for the past year and anticipated number thereof for the coming year, together with details on the training programs that were and shall be implemented (article 32.7)
Provide a budget and deliver or require the Main Contractors and/or Main Subcontractors to deliver professional ongoing training programs on (i) health, safety and risk management and (ii) trades required for the Exploitation Phase of the Project, with a view to maximizing the Cameroonization of the workforce and more generally to providing development and careers opportunities for their Cameroonian workforce. |  | 6 years from the Date of Entry into Force | Project Companies
State and Cam Iron personnel may take part in meetings of the Expansion Committee (article 18.22) |  | 6 years from the Date of Entry into Force | State and Cam Iron
State and Cam Iron personnel may take part in meetings of the Joint Committee (article 30.5.2.c) |  |  | State and Cam Iron
Implement an accident prevention scheme and emergency plans to be implemented in case of loss or threatened loss that poses a risk to personnel or to the safety of persons.(article 29.3) |  |  | Project Companies / Contractors / Subcontractors | [6 empty] | The Accident and Prevention Scheme / Emergency Plans
Guarantee optimum conditions for health and safety of personnel (Article 29.3) |  |  | Project Companies / Contractors / Subcontractors |  |  |  |  | Appropriate and detailed procedures
Informing the Personnel and conduct awareness campaigns on safety, health and diseases (article 29.3) |  |  | Project Companies / Contractors / Subcontractors
Note on K4: Road Map of the Mbalam Mining Convention - Conditions Precedent : The General Output includes a notification, in French and English with acknowledment of receipt when delivered in Cameroon, of any satisfaction of the Conditions Precedent as and when they occur (article 4.5. of the Convention). Such notifications shall be made to Mr NGO'O Cyrus cordinator of the Technical secretariat of the MINIMIDT in compliance with the provisions of aticle 63 of the Convention.
Note on A6: Road Map of the Mbalam Mining Convention - Personnel Obligations: The Collective Bargaining Agreement means the agreement dated the Signature Date entered into between Cam Iron on the one hand and the trade unions designated therein, on the other hand, (the Ministry of Labor and Social Security and the Ministry of Employment and Professional Training having also executed such agreement) with a view to determining the terms and conditions of recruitment, dismissal, organization of the working conditions, remuneration, professional training, health and safety of the personnel hired for the purposes of the Project, and all the obligations of which shall be restated separately by each Project Company in the Specific Agreement to which it is a party. Such Agreement was concluded on November 29, 2012.
Note on B7: Road Map of the Mbalam Mining Convention - Personnel Obligations: Application of the Collective Bargaining Agreement shall be optional for non Cameroonian employees who are specifically used to carry out services in connection with the Project. Such option is also awarde to Project Companies Contractors and Subcontractors. (article 32.1.b)
Note on C7: Road Map of the Mbalam Mining Convention - Personnel Obligations : Pursuant to the provisions of article 3.6 (a), (a), Cam Iron undertakes that the Project Commissioning occur within six (6) years following the Date of Entry into Force or such later date as otherwise agreed. Whereas the definition given by the Convention on the Construction Phase refers to "the period commencing on the Date of Entry into Force until Project Commissioning". Thus, as Project Commissionning has to occur six years following the Date of Entry into Force and the Construction refers to the phase commencing on the Date of Entry into Force till Project Commissioning, we can assume that the Construction Phase consist on the 6 years period following the Date of Entry into Force.
Note on A11: Road Map of the Mbalam Mining Convention - Personnel Obligations: Article 32.3. provides that the Project Companies, the Contractors and Subcontractors undertake to give priority to the employment of Cameroonian nationals, subject to their availability at the time of recruitment and required level of qualification and professional experience. Project Companies shall not discriminate against Cameroonian nationals based on the work conditions applicable to them. The recruitment process shall be the following: - From the local Cameroonian nationals residing in the region of the Exploitation Area, Mineral Terminal Area and Railway Area throughout the duration of the Project; - From the ranks of the construction contractor's Cameroon national construction workforce; - Throughout Cameroon and from the international Cameroon diaspora. Where Cameroonian nationals with the required level of qualification and professional experience cannot be identified or are not available, foreign nationals may be recruited.
Note on A12: Road Map of the Mbalam Mining Convention - Personnel Obligations: Project Companies, Contractors and Subcontractors, shall be authorized to implement Shifts and Rosters under the following conditions: - Their respective employees shall not work Shifts extending beyond twelve (12) hours a Day; - Their respective employees shall not work in excess of sixty (60) hours a week on average over a full Roster period and that every fourteenth (14th) Day during such rotation period is a Business Day; - Any work period within a Roster does not exceed eight (8) weeks during the Exploitation Phase. Should the Project Companies, the Contractors or the Subcontractors, require Shifts and Rosters to be implemented in excess of those terms and conditions, the State shall consider how such flexibility could be implemented and shall facilitate such flexibility, in particular as regards the work inspector authorizations for overtime and, subject to the interest of the Cameroonian workforce. During the Construction Phase, annual leaves for employees under a Roster may be considered taken during weeks off and details thereof shall be set forth in their respective employment contracts.
Note on A14: Road Map of the Mbalam Mining Convention - Personnel Obligations: Pursuant to the provisions of article 23.10, General Employment Provisions cover discrimination of any nature whatsoever, with regard to race, sex, religion or nationality and the prohibition to use child labor or forced, including bonded or prison labor for the Project.
Note on A15: Road Map of the Mbalam Mining Convention - Personnel Obligations: Fulfilling all HSECS obligations entail, as per the provisions of article 32.11 of the Convention: - Developping and implementing (x) a detailed Health and Safety Management Plan and (y) a detailed environmental and social management plan that shall both be approved by the State and shall ensure compliance with internationally recognized standards such as ISO 9001:2008 (Quality management system requirements), ISO 31000:2009 (Risk management - Principles and guidelines), ISO/IEC 31010:2009 (Risk management - Risk assessment techniques), ISO/IEC 17021:2011 (Conformity assessment); - Providing a safe work place with safety systems in compliance with OHSAS 18001; - Being responsible for the safety of all staff and visitors to the site on which the relevant Project Companies (Contractors and Subcontractors) operate, which shall include the supply and timely replacement of all personal protective equipment for all such staff and visitors; - Providing trained medical staff (including doctors and nurses) as well as safety equipment (including ambulances), medicines and dressings for injuries that may occur; and - Providing first response medical facilities equipped to stabilize any serious casualties arising from work related accidents or health issues and maintain adequate medical evacuation plans and facilities to transfer casualties to an appropriate treatment center.
Note on A16: Road Map of the Mbalam Mining Convention - Personnel Obligations : As part of the process for Immigration Documents for foreign Personnel, Project Companies, Affiliates, Contractors and Subcontractors shall file applications for working permits and visas - as well as any other authorization or document that may be required for Foreign Personnel to lawfully enter and work in Cameroon for the sole purpose of carrying out their work activities in connection with the Project for any and all non-Cameroonian nationals who are hired for the purpose of carrying out services in connection with the Project in Cameroon, whether as employees, consultants or otherwise. However, In order to streamline the Applications and help speed up the issuances of Immigration Documents, the State shall set up a single entry application procedure for the review, processing of Applications and issuances of Immigration Documents. The Labor Committee shall prepare, in consultation with each relevant administration in charge of the review, processing and/or issuance of such Immigration Documents, a comprehensive document outlining the procedure that must be followed for any and all Application as well as expected deadlines for the issuance of Immigration Documents, such deadlines being set forth as an objective in view of Project operational requirements. The Project Companies, the Contractors and Subcontractors shall lodge the Applications in accordance with applicable Legislation and with the Procedure laid down by the Labour Committee (called the Protocol).
Note on A17: Road Map of the Mbalam Mining Convention - Personnel Obligations: Professional training programs shall concern health, safety and risk management, with a view to maximizing the Cameroonization of the workforce and more generally to providing development and careers opportunities for the Cameroonian workforce. The training budget shall be divided equally between internal fifty percent (50%) and relevant external fifty percent (50%) training. Internal training shall include: professional training centers within the Project Companies, scholarships for staff or prospective staff with potential to undertake specific undergraduate and post-graduate university courses linked to the Project Companies' business needs and internships within the Project Companies (and/or their Main Contractors and Main Subcontractors), whereas External training may include setting up or contributions to trade academies linked to the Project Companies' activities. With respect tp transfer of know-how, it is provided that Project Companies commit to a minimum training budget which they will use directly or through their Main Contractors and/or Main Subcontractors. The budget provided shall be a total of a minimum amount of seven (7) million US Dollars in agrregate to be divided as follow: - Two million (2,000,000) US Dollars per year during the first two (2) years of the Construction Phase, for a total of four million (4,000,000) US Dollars; - Three million (3,000,000) US Dollars for the third (3rd) year of the Construction Phase. The Convention also provides that should the Construction Phase extend beyond three (3) remaining years, Cam Iron shall commit to renew the training budget for an amount not less than two (2) million US Dollars per year calculated pro rata per month of extension.
Note on A18: Road Map of the Mbalam Mining Convention - Personnel Obligations: The Labor Committee shall be set up for Recruitment and Training and shall be established by the State and Cam Iron prior to the Construction Phase and for the Term of the Project.
Note on A21: Road Map of the Mbalam Mining Convention - Personnel Obligations: The Expansion Committee examines all proposals seeking access to the Mineral Terminal Facilities and the Railway Facilities and serve as a forum for discussing and coordinating expansion in general, being understood that Expansion refers tomeans any stage as from the Date of First Commercial Shipping to (a) the date that the maximum capacity of the Railway Facilities and the Mineral Terminal Facilities achieves or is demonstrated to achieve thirty five (35) million Tonne per annum or, (b) the fourth (4th) anniversary from the Date of First Commercial Shipping.
Note on A22: Road Map of the Mbalam Mining Convention - Personnel Obligations: The Joint Committee examines all matters put on its agenda with respect to the orientation, programming and control of the conduct of the Project Operations. (article 30.5.3)