## Conditions Precedent
Conditions Precedents to be satisfied | Required actions or operation | Date for compliance (time frame, deadline) | Party action accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance (State) | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Delivery of a commitment letter for the Debt required by the Project (article 4.1. (b)) | Negotiate and sign a commitment letter with the Lenders or the Lender if there only one. | August 29, 2013 | Cam Iron/Sundance |  |  | NA |  |  |  | Commitment Letter / Aknowledgment of receipt from the State of the notice of fulfillement of the Conditions Precedent | The State shall have no obligation to present the Enabling Law to the Parliament if this condition is not satisfied at the date for compliance
| Deliver the commitment letter to the State and, specifically, to the General Secretary of the Prime Minister, with a copy to the Ministry of Industry, Mines and Technological Development, to Patton Boggs and to the State Project Committee when the said Committee will be established | [9 empty] | The Convention may be terminated and any right arising from the Convention may be revoked
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Note on A4: Road Map of the Mbalam Mining Convention - Conditions Precedent : Conditions Precedent are the ones contained in article 4.1. of the Convention. The Parties’s rights and obligations under the Convention shall only become effective subject to the prior satisfaction of the said conditions. In other words consequence, the entry into force of the Convention is subject to the prior satisfaction of these conditions. We would like to draw your attention to the fact that pursuant to article 3.5 of the Convention, the following documents were suppose to be delivered at the Signature Date: - A letter agreement from Sundance to the State, which provides notably for a guaranty by Sundance of the obligations of Cam Iron under the Convention prior to the Date of the Entry into Force and an agreement to pay or cause to be paid to the State any breakup fee required to be paid in accordance with article 4.6 or the Bonus Payment payable pursuant to article 36.5; - The certificate of appropriate public officiels required under article 3.5 (b).
Note on D4: Road Map of the Mbalam Mining Convention - Conditions Precedent: Required actions or operations are the ones to be carried out in order to reach to the expected result, that is to say for the satisfaction of the condition precedent.
Note on F4: Road Map of the Mbalam Mining Convention - Conditions Precedent: Party means either the State or CamIron or any other Project Company (the Mine Project Company, the Railway Project Company or the Mineral Terminal Project Company), depending on the case.
Note on G4: Road Map of the Mbalam Mining Convention - Conditions Precedent: Road Map of the Mbalam Mining Convention - Conditions Precedent: This refers to the specific individual responsible for compliance within the “Party accountable for compliance”.
Note on I4: Road Map of the Mbalam Mining Convention - Conditions Precedent: This refers to the specific individual responsible for compliance within the “Party accountable for compliance”.
Note on M4: Road Map of the Mbalam Mining Convention - Conditions Precedent : The General Output includes a notification, in French and English with acknowledment of receipt when delivered in Cameroon, of any satisfaction of the Conditions Precedent as and when they occur (article 4.5. of the Convention). Such notifications shall be made to Mr NGO'O Cyrus cordinator of the Technical secretariat of the MINIMIDT in compliance with the provisions of aticle 63 of the Convention.
Note on A6: Road Map of the Mbalam Mining Convention - Conditions Precedent: The expression "commitment letter" is not defined by the Convention. In practice, commitment letter is known, in the finance sector, as a written promise delivered by a lender to make or insure a loan for a specific amount and on specified terms. The commitment letter contemplated in this Convention is relating to the Debt of the Project, which "means all indebtedness for borrowed money (including principal, interest, commissions and fees) to be paid or repaid by a Project Company under the Finances Documents relating to the amounts raised and used to fund (or refinance) the debt component of the Project costs (excluding the amounts borrowed to fund the Equity or interest accrued on said amount". The commitment letter is, thus, a letter to be signed by the Lenders in favour of Cam Iron, whereby such Lenders promise to grant to Sundance, Cam Iron or any Project Company a commercial credit, loan, bonds, financing or refinancing for the purpose of funding the Projet, it being specified that this commitment letter does concern loans or fund intended to finance equity in Cam Iron, Sundance or in any Project Company and interest accrued thereof.
Note on D6: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Convention does not specify the form and content of the commitment letter. Usually such letter contain: - a writtent undertaking by a Lender; - to provided a credit facility (which type or form is generally specified) to the borrower; - on mutually agreed upon terms, which serve as term sheet for negotiation of the credit agreement (Finance Agreement within the meaning of the Convention"). We understand, from the ASX Announcement and Media Release from Sundance Resources LTD, dated 11 January 2013, that Hanlong (Africa) Mining Investment Ltd ("Hanlong") had secured a financier commitment letter from China Everbright Bank Co. Ltd for US$438M, and that another Financier Commitment Letter for US$1.022 billion (announced on 22 October 2012) was already issued. The Convention does not expressly require for the commitment letter to be issued on behalf of Cam Iron. Therefore, in our view, since the above-mentioned commitmet letters are intended to fund the Project, they can validly be submitted to the State for the satisfaction of the Condition Precedent relating to the delivery of a commitment letter for the Debt required by the Project.
Note on F6: Road Map of the Mbalam Mining Convention - Conditions Precedent: We would like to draw your attention to the fact that if the financier commitment letter from China Everbright Bank Co. and for China Development Bank shall serve as commitment letter for the Debt of the Project, Hanlong shall be involved and: - Sundance will be accountable for collecting the commitment letters from Hanlong and to foward them to Cam Iron ; - Cam Iron will be responsible for the delivrance of the commitment letters to the State.
Note on D7: Road Map of the Mbalam Mining Convention - Conditions Precedent: In the absence of any particular specification in the Convention concerning the modalities for the deliverance of the commitment letter to the State, such delivrance shall be made in accordance with the general provisions of the Convention relating to communications and notices between the Parties.
Note on N7: Road Map of the Mbalam Mining Convention - Conditions Precedent (article 4. 3 (b) and (c): In the event that such Condition Precedent is not satisfied or waived on the compliance date, the Parties shall meet to decide within 90 days as from the date for compliance, either to waive in writing the non satisfied condition, or to postpone the date for compliance. Failure to reach an agreement with respect to the Conditions Precedent will lead to the cancellation of the Convention.
Note on D8: Road Map of the Mbalam Mining Convention - Conditions Precedent: Pursuant to article 4.5 (a) of the Convention, "each Party shall justify to the other Party any satisfaction of the Conditions Precedent as when they occur". According to article 64 of the Convention, the notification should be made by delivering to the State a notice wrtitten both in French and in English at the adressees provided in article 64 of the Convention: - The General Secratary Office of the Prime Minister; - The Ministry of Industry, Mines and Technological Development. Copy of all notifications to the State should be adressed to the State Project Committee. To recall, the State Project Committee is the committee that shall be established by the State in order to coordinate with Cam Iron and the Project Companies with respect to the performance of the State's responsabilities under the Project Agreements, as set forth in article 47 of the Mining Convention. The difficulty here concerning notifications to the State Project Committee of the satisfaction ot the Condition Precedent regarding the update of the Feasibilty Study is that the deadline provided for in the Convention for the establishment of this committee is after the Date of Entry into Force, that is well after the fulfillment of the condition. The Government is not required to set up the State Project Committee before the Date of Entry into Force. We recommend, however, to urge to Government for the establishment of this commitee as soon as possible given the major role it has to play in facilitating the Project. Please note also note that the firm Patton Boggs LLP (see it adress for notices in article 64 of the Convention) must receive a copy of all notices sent to the Government of Cameroon in connection with the Convention.
Note on D9: Road Map of the Mbalam Mining Convention - Conditions Precedent: Pursuant to article 4.5 (c) of the Convention, "each Party shall notify the other Party in writing of the occurrence of any event likely to prevent the Conditions Precedent from being satisfied before, or no later than, on the CP Long Stop Date, as soon as the Party becomes aware of the relevant event". According to article 64 of the Convention, the notification should be made by delivering to the State a notice wrtitten both in French and in English at the adressees provided in article 64 of the Convention: - The General Secratary Office of the Prime Minister; - The Ministry of Industry, Mines and Technological Development. Copy of all notifications to the State should be adressed to the State Project Committee. To recall, the State Project Committee is the committee that shall be established by the State in order to coordinate with Cam Iron and the Project Companies with respect to the performance of the State's responsabilities under the Project Agreements, as set forth in article 47 of the Mining Convention. The difficulty here concerning notifications to the State Project Committee of the satisfaction ot the Condition Precedent regarding the update of the Feasibilty Study is that the deadline provided for in the Convention for the establishment of this committee is after the Date of Entry into Force, that is well after the fulfillment of the condition. The Government is not required to set up the State Project Committee before the Date of Entry into Force. We recommend, however, to urge to Government for the establishment of this commitee as soon as possible given the major role it has to play in facilitating the Project. Please note also note that the firm Patton Boggs LLP (see it adress for notices in article 64 of the Convention) must receive a copy of all notices sent to the Government of Cameroon in connection with the Convention.