## Conditions Precedent
Conditions Precedents to be satisfied |  | Required actions or operation | Date for compliance (time frame, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance (State) | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance | Risk/sanction | Comments
[9 empty] | Cam Iron / Project Companies | State
Obtain of approval by the Parties on the form of all Annexes contemplated by the Convention (Article 4.1.c) |  | Ensure that all Annexes are finalized according to each Party's aim | May 29, 2014 | Cam Iron / State | General Manager/ Management / Legal |  |  | Pending | Copies of all annexes / Beneficiation Agreement |  | Signing by the Parties of all Annexes | Nullity of the Mining Convention / Automatic termination or revokation of any right arising from the Convention
Signing of all Annexes by the Parties
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Either consumate the transaction contemplated by the scheme of arrangement involving Sundance and Hanlong or complete a transaction with another entity (Article 4.1.d) |  | Negotiate with Hanglong Africa in order to terminate the transaction contemplated | May 29, 2014 | Sundance | Sundance CFO |  |  | Pending | Finance Documents of the Project |  | Find a financial Partner to the Project
In case this does not sucessful, negotiate with other entities capable of Financing the Project
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Deliver a signed copy of the Joint Liability Subscription Agreement (Article 4.1.f) |  | Preparing the Joint Liablity Subscription document | May 29, 2014 | Cam Iron | General Manager/ Management / Legal |  |  | Pending | Project Agreements |  | Signed copy of the Joint Liability Subscription Agreement
Have the documents signed by the Parties
Delivery of the signed copy of the Joint Liability Subscription Agreement to the State
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Ensure the passage of the Enabling Law and the issuance of the Promulgation Decree, including the publication of such Decree in the Official Gazette (Article 4.1.e) |  | Propose a draft Law to the State | May 29, 2014 | State of Cameroon / Under Cam Iron supervision | State of Cameroon / Under Cam Iron supervision |  | State of Cameroon / Under Cam Iron supervision | Pending | Fulfillement of the CP of 2013 (Feasibility Study and Commitment Letter) | Final Drafts of the Enabling Law and of the Promulgation Decree | Promulgation of the Enabling Law and its Decree in the Official Gazette
Ensures that the State enacts the Enabling Law with respect to the Mbalam Mining Convention along with the Promulgation Decree
Ensures that the States publishes the said Decree in the Official Gazette
Request from the State for the notification of the publication of the Enabling Law in the Official Gazette
Registration of the Mine Project Company, of the Railway Project Company (including the Railway Agreement) and of the Mineral Terminal Project Company and the conclusion and entry into force of their respective Share Transfer Agreements, Shareholder's Agreements, Accession Notices, and the Railway Agreement (Articles 4.1.g, h, i) |  | Take all steps as to the registration / incorporation of the Mine Project Company, the Railway Project Company and of the Mineral Terminal Project Company | May 29, 2014 | Cam Iron / State | Country Manager |  | State's representatives in Project Companies | Pending / Ongoing | Copies of the Share Transfer Agreements, Shareholders Agreements and Accession Notices/ Provisions of the Mbalam Convention on the shareholding of Project Companies |  | Registration of all companies related to the Project / Have their respectives Share Transfer Agreements, Shareholders Agreements and Accession Notices signed
Ensures that their respective Share Transfer Agreements, Shareholder's Agreements and Accession Notices are drafted, concluded and signed, and ensures their entry into force
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Obtain a certificate from the State certifying that all of State’s representations and warranties, as set forth in this Convention and the Project Agreements to which the State is a party shall be true and correct (Article 4.1.o) |  | Drafting and approval of the said Certificate by the State | May 29, 2014 | State of Cameroon |  |  | Document probably issued by the Finance Ministry but also approved by the Mines Ministry | Pending |  | Copy of the Mbalam Convention | Issuiance by the State of the Certificate on all warranties and representations to which the State is party
Execute the Technical Dispute Resolution Agreement (article 4.1.j) |  | Draft the Technical Dispute Resolution Agreement | May 29, 2014 | Cam Iron (Sundance) / State | Sundance Legal |  |  | Pending | Project Agreements / Specific Technical Dispute Agreements |  | Approval by the Parties of the Technical Dispute Resolution Agreement
Ensure the conclusion and signature of such Agreement
Ensure the respect of the terms and obligations contained in such Agreement
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Submit a certificate of validity of all representations and warrantees contained in the Convention and in the Project Agreements (Article 4.1.o) |  | Draft a certificate justifying the validity of all representations and warrantees contained in the Convention | May 29, 2014 | Cam Iron | Sundance Legal |  |  | Pending | Convention |  | Certificate of validity of all representations and warrantees contained in the Convention
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Receive approval by the State of any Finance Documents to which the State is a Party and the closing of the lending transactions contemplated by the Finance Documents (Article 4.1.l) |  | Identify all Finance Documents to which the State is a party | May 29, 2014 | Sundance / State | Sundance CFO/ Legal |  | Ministry of Finances | Pending | Finance Documents |  | Approval by the State of all Finance Documents and Closing of all lending transactions
Submit such documents to the State and have such documents approved and signed by the State
Identify and close all lending transactions contemplated by such Finance Documents after approval by the State of such Finance Documents
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notify to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Obtain the Mining Exploitation Permit (Article 4.1.m) |  | Obtain the Mining Permit as per the provisions of the 2001 Mining Code and the 2010 amending Law | May 29, 2014 | State under Cam Iron's supervision |  |  | State under Cam Iron supervision | Pending |  | Convention / Enabling Act / Official Gazette containing the Enabling Act | Obtaining of the Mining Exploitation Permit materialized by a Granting Decree published in the Official Gazette
Ensure that such obtaining is materialized by a publication in the Official Gazette of the Granting Decree
Delivery to the State by each Project Companies executing a Project Agreement or by any Subsidiary executing the Project a certificate of appropriate public official and a certificate delivered by an officer of the said Project Company or by the said subsidiary (Article 4.1.p). |  | Obtain a certificate of a public official as to the existence and good standing of the Project Company in its jurisdiction of organization | May 29, 2014 | Cam Iron/ Each Project Company | General Manager / Legal of Cam Iron and of each Project Company |  |  | Pending | Resolutions of the Board of Directors authorizing the execution of the Project Agreements of each Project Company / Any organizationnal document of each Project Company |  | Delivery to the State of a Certificate of Public Official and of a Certificate executed by each Project Company's officer
Draft a Certificate executed by a Project's Company officer
Send the Certificate executed by a Project Company's officer to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Delivery by the State to Each Project Company the incumbency and signatures of all states officers autorized to act with respect to Project Agreements (Article 4.1.q) |  | Received the Certificate from the State (Maybe from the Ministry of Mines and from the Ministry of Finances) | May 29, 2014 | State |  |  | State | Pending |  | Project Agreements | Obtaining a Certificate from the State
Issue to the State all required Bank Guaranties (Article 4.1.r) |  | Get in touch with relevant banking services in order to obtain the required Bank Guarantee | May 29, 2014 | Sundance | CFO |  |  | Pending |  | Finance Documents including lenders transactions | Submit all required Bank Guaranties to the State
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Execute the Railway Haulage Agreement by the Railway Project Company and the Mine Project Company (Article 4.1.s) |  | Draft the Railway Haulage Agreement | May 29, 2014 | Cam Iron /Railway Project Company | General Manager / Operations / Legal |  |  | Pending | Assessment and description of the tariffs to be charged by the Railway Project Company |  | Execution of the Railway Haulage Agreement
Ensure its execution by the Railway Project Company and the Mine Project Company
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Execute the Mineral Terminal Services Agreement by the Mineral Terminal Project Company and the Mine Project (Article 4.1.s) |  | Draft the Mineral Terminal Services Agreement | May 29, 2014 | Cam Iron / Mineral Terminal Project Company | General Manager / Operations / Legal |  |  | Pending | Assessment and description of the tariffs to be charged by the Mineral Terminal Project Company |  | Execution of the Mineral Terminal Services Agreement
Ensure its execution by the Mineral Terminal Project Company and the Mine Project
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Execute the Monitoring Agreement - Blending (Article 4.1.t) |  | Draft the Monitoring Agreement - Blending | May 29, 2014 | State / Mine Project Company and Cam Iron / the Republic of Congo / the Mineral Terminal Company | General Manager / Operations / Legal / Finance |  | MINIMIDT | Pending | All details of Blending Operations |  | Execution of the Monitoring Agreement - Blending
Ensure its execution
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Execute the Monitoring Agreement - Marketing (Article 4.1.u) |  | Draft the Monitoring Agreement - Marketing | May 29, 2014 | State / Mine Project Company and Cam Iron / the Marketing Company | General Manager / Operations / Legal / Finance |  | MINIMIDT | Pending | All details of Marketing Operations |  | Execution of the Monitoring Agreement - Marketing
Ensure its execution
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Execute the Monitoring Agreement - Treasury (Article 4.1.v) |  | Draft the Monitoring Agreement - Treasury | May 29, 2014 | State/ Mine Project Company/ Cam Iron / the Treasury Company | General Manager / Operations / Legal / Finance |  | MINIMIDT | Pending | All details of Treasury Operations |  | Execution of the Monitoring Agreement - Treasury
Ensure its execution
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Execute the Marketing Agreement, including the registration of the Marketing Company (Article 4.1.w) |  | Draft the Marketing Agreement | May 29, 2014 | Sundance | CFO and COO |  |  | Pending | All details of Marketing Operations and all Finance Documents |  | Execution of the Marketing Agreement / Registration of the Marketing Company
Ensure its execution
Ensure the registration of the Marketing Company
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Execute the Treasury Agreement, including the registration of the Treasury Company (Article 4.1.x) |  | Draft the Treasury Agreement | May 29, 2014 | Sundance | CFO |  |  | Pending | All details of Treasury Operations |  | Execution of the Treasury Agreement / Registration of the Treasury Company
Ensure its execution
Ensure the registration of the Treasury Company
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Ensure the binding and the effectiveness of the insurance policies required in accordance under the Finance Documents (Article 4.1.y) |  | Subscribe all insurance policies required under the Finance Documents | May 29, 2014 | Cam Iron | General Manager / Finance / Legal |  |  | Pending | All Finance Documents |  | Ensure the binding and effectiveness of insurance policies required under Finance Documents
Ensure their binding and effectiveness with respect to Operations carried out
Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention.
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
Ensure the execution by all Parties of each of the following (Article 4.1.z): |  | Notification of the satisfaction of this Condition Precedent should to be made to i) the General Secretary Office of the Prime Minister and to ii) the Ministry of Industry, Mines and Technological Development, with copy to i) The State Project Committee and to ii) Patton Boggs LLP in accordance with article 64 of the Convention. | May 29, 2014 | Cam Iron / Project Companies | General Manager / Operations / Legal / Finance |  |  | Pending |  |  | Ensure the execution of all such Agreements
Notification to the State, if applicable, any event, circumstance or consideration that prevents or may prevent the satisfaction of this Condition Precedent (delivrance of the commitment letter for the Debt required by the Project) before or at the latest on August 29, 2013
| Aerodrome Agreement | Draft and conclude the Aerodrome Agreement | [6 empty] | All details on the use of the Aerodrome
Ensure its execution
| Explosives Agreement | Draft and conclude the Explosive Agreement | [6 empty] | All details on the use and transport of Explosives
Ensure its execution
| Conservation Agreement | Draft and conclude the Conservation Agreement | [6 empty] | Details on the location of the Exploitation Area and on the Forest Management
Ensure its execution
| Road Agreement | Draft and conclude the Road Agreement | [6 empty] | Details of the Project Road Plan
Ensure its execution
| Blending Agreement | Draft and conclude the Blending Agreement | [6 empty] | All details of the Blending Operations
Ensure its execution
| Beneficiation Agreement | Draft and conclude the Beneficiation Agreement | [6 empty] | All Beneficiation Specifications
Ensure its execution
| Foreign Exchange Agreement | Draft the Foreign Exchange Agreement | [6 empty] | Financial provisions of the Convention and Tax and Customs Annex of the Convention
Ensure its execution
| Project Leases | Draft the Project Leases | [6 empty] | Draft leases contracts prepared either by Cam Iron and/or the Project Companies or by the Landlords
Ensure their execution
| Rehab Escrow Agreement | Draft and Conclude the Beneficiation Escrow Agreement and Rehab Escrow Agreement | [6 empty] | Details of the Rehabilitation Plan
Ensure their execution
Have a consensus with Government of Cameroon on pre-approved Qualified Contractors |  | Draft a list of all potentials Contractors | May 29, 2014 | Cam Iron / State | General Manager / Procurement |  | MINIMIDT | Pending | List of all Contractors which may be used for the Project |  | Issuance of a list of pre-approved Qualified Contractors
Submit the list to the Government of Cameroon in order to find a consensus
Note on A4: Road Map of the Mbalam Mining Convention - Conditions Precedent : Conditions Precedent are the ones contained in article 4.1. of the Convention. The Parties’s rights and obligations under the Convention shall only become effective subject to the prior satisfaction of the said conditions.
Note on F4: Road Map of the Mbalam Mining Convention - Conditions Precedent: Party means either the State or CamIron or any other Project Company (the Mine Project Company, the Railway Project Company or the Mineral Terminal Project Company), depending on the case.
Note on I4: Road Map of the Mbalam Mining Convention - Conditions Precedent: This refers to the specific individual responsible for compliance within the “Party accountable for compliance”.
Note on M4: Road Map of the Mbalam Mining Convention - Conditions Precedent : This includes any notification of compliance required by the mining convention (for example, article 4.5.a of the mining convention provides that “each Party shall justify and notify to the other Party any satisfaction of the Conditions Precedent as and when they occur”). Outputs also include any Finding of Compliance to be delivered by the State to any Project Company in accordance with the mining convention and with any applicable legislation/regulation.
Note on A6: Road Map of the Mbalam Mining Convention - Conditions Precedent : The Mining Convention contains 10 Annexes: - Annex I: Accession Notice - Annex II: BF Construction - Annex III: Tariff Framework - Annex IV: Collective Bargaining Agreement - Annex V: Tax Depreciation Schedule - Annex VI: Prohibited Imports - Annex VII: Fiscal & Customs Regime - Annex VIII: Mine Gate Value Determination; - Annex IX: Certain Shareholders Provisions - Annex X: Collective Bargaining Agreement
Note on N6: Road Map of the Mbalam Mining Convention - Conditions Precedent: In the event that such Condition Precedent is not satisfied or waived on the compliance date, the Parties shall meet to decide within 90 days as from the date for compliance, either to waive in writing the non satisfied condition, or to postpone the date for compliance. Failure to reach an agreement with respect to the Conditions Precedent will lead to the cancellation of the Convention.
Note on A10: Road Map of the Mbalam Mining Convention - Conditions Precedent: The expected financial transaction is to be carried out with Hanlong Group. However, if the arrangement is to be made with a party different from Hanlong capable of financing the Project, the third party must satisfy the State’s requirement that the third party has the independence and capacity to run the project. The said third party must also have a firm written commitment for the equity and debt necessary for the project
Note on A14: Road Map of the Mbalam Mining Convention - Conditions Precedent: It is a document in which Cam Iron expressly consents to be jointly and severally liable to the State for all the obligations undertaken by the Project Companies hereunder or under the various Project Agreements. Such document may include Articles 1200 et seq of the Cameroon Civil Code which inter alia will cause Cam Iron to either perform or pay for services due by Cam Iron or any Project Company. Cam Iron may be released from its responsibility in case all obligations undertaken under the Project Agreements are satisfied or where: - More than fifty percent (50%) of the voting equity interests in that Project Company are held by or have been transferred to the State or a Governmental Entity (whether together or by one of them); or - The State agrees in writing to release Cam Iron from that obligation on the basis of an alternate party acceptable to the State offering to be jointly and severally liable for the obligations of the Project Company and that party having financial standing which is no less than that of Cam Iron or, if less, otherwise acceptable to the State.
Note on A19: Road Map of the Mbalam Mining Convention - Conditions Precedent: However, the Government of Cameroon can only present the Enabling Law to parliament when the conditions precedent set-forth below are are satisfied within a six months period following the signing of the Mbalam Condition: - 4.1(a) (Delivery of an updated Feasibility Study including the Project Economic Model); - 4.1(b)(delivery of a commitment letter for the Debt required for the project);
Note on D23: Road Map of the Mbalam Mining Convention - Conditions Precedent: This mostly includes: - The legal incorporation (Registration at the Trade and Personal Property Credi Register); - The tax registration (Taxpayer's number obtaining); - The Social registration at the National Social Security Fund (NSIF).
Note on A27: Road Map of the Mbalam Mining Convention - Conditions Precedent: The representation and warranties arenot only limited to the Convention, but also include those set forth in the Project Agreements to whcih the State of Camreoon is a party
Note on A29: Road Map of the Mbalam Mining Convention - Conditions Precedent: Cam Iron and the Government of Cameroon have to adopt one or more separate agreements, which agreement(s) will constitute the Technical Dispute Resolution Agreement. In case such agreement is not met during the specified deadline, the Parties shall mutually agree in writing the waiver of any non-satisfied condition precedent or mutually agree to postpone the applicable 18 months period to any subsequent new date. If the Parties adopt a Technical Dispute Resolution Agreement, this Agreement shall supersede the provisions of Article 55.2 which provides for the conduct of Technical Disputes as per the Rules for Expertise of the International Chamber of Commerce
Note on A34: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Certificate shall be delivered by a Cam Iron's Officer. The Certificate shall certify that all of Cam Iron’s and the Project Company(ies) representations and warrantees set forth in the Mbalam Convention and the respective Project Agreements respectively are true and correct at the time of the Signature Date of the Mbalam Convention
Note on A42: Road Map of the Mbalam Mining Convention - Conditions Precedent: The delivery of the Exploitation Permit to Cam Iron shall be materialized by the notification, to Cam Iron, of the publication in the Official Gazette of the Granting Decree to the extent required by the Legislation.
Note on A44: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Certificate of appropriate public official shall be dated reasonably close to the date of execution of the Company's Project Agreement, and shall relate to the existence and good standing of such Project Company or Subsidiary in its jurisdiction of organization. The Certificate, duly executed and delivered by an officer of such Project Company or Subsidiary and dated as of the date of execution of the Company's Project Agreement shall include: - Resolutions of its board of directors then in full force and effect authorizing the execution, delivery and performance of the Company's Project Agreement and the transactions contemplated thereby; - The incumbency and signatures of those of such Project Company or any Subsidiary’s officers, authorized representatives, agents, managing members or general partners, as applicable, authorized to act with respect to each Project Agreement to be executed by such Project Company or Subsidiary and; - The full force and validity of each organizational document and copies thereof
Note on A48: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Certificate to be issued by the State shall present the incumbency and signatures of those State officials authorized to act with respect to each Project Agreement to be executed by such Project Company or Subsidiary.
Note on A50: Road Map of the Mbalam Mining Convention - Conditions Precedent: Bank Guarantee must be provided by an independent bank with Acceptable Bank rating whether or not located outside Cameroon.
Note on A61: Road Map of the Mbalam Mining Convention - Conditions Precedent The Monitoring Agreement - Blending is to be concluded between the Mine Project Company, Congo Iron, the Government of Cameroon and the Mineral Terminal Company.
Note on A65: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Monitoring Agreement - Marketing is to be concluded between the Mine Project Company, the Government of Cameroon and the Marketing Company.
Note on A69: Road Map of the Mbalam Mining Convention - Conditions Precedent: Agreement to be concluded between the Mine Project Company, the Government of Cameroon and the Treasury Company
Note on A73: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Marketing Agreement is to be concluded between the Mine Project Company and the Marketing Company.
Note on K73: Road Map of the Mbalam Mining Convention - Conditions Precedent:: Treasury Operations means: The commercial, logistical, technical and quality assurance operations for Marketing of the Sale Products; - Marketing of the Sale Products and; - Assumption of credit risk associated with the buyer of the Sale Products.
Note on A78: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Treasury Agreement is to be concluded between the Project Companies and the Treasury Company.
Note on K78: Road Map of the Mbalam Mining Convention - Conditions Precedent: Treasury Operations means the management of the sale proceeds received by the Mine Project Company on the Sale Products, carried out in accordance with the terms and conditions of the Convention and the Treasury Agreement.
Note on B89: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Aerodrome Agreement is to be completed by the Mine Project Company, Cam Iron and the Government of Cameroon.
Note on B91: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Explosive Agreement is to be completed by the Mine Project Company, Mineral Terminal Project Company, Railway Project Company and the Government of Cameroon
Note on B93: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Conservation Agreement is to be completed between Cam Iron and the Government of Cameroon and shall specify the scheme and operation mode of environmental compensation. The Government of Cameroon shall issue Cam Iron with the necessary authorizations for the above-mentioned conservation activity (ies) after the Signarture Date (Nov 29, 2012)
Note on B95: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Road Agreement, between Cam Iron and the Government of Cameroon, addresses the details of the Road Plan and other provisions regarding the Project Roads.
Note on B97: Road Map of the Mbalam Mining Convention - Conditions Precedent: The entry into agreement related to the blending of Mbalam Ore and iron ore from other territory covered by the Nabela Permit is to be concluded between the Mine Project Company, Congo Iron and the Mineral Terminal Project Company.
Note on B99: Road Map of the Mbalam Mining Convention - Conditions Precedent: The Beneficiation Agreement is to be entered between Cam iron and the Government of Cameroon wherein they consider alternatives and cooperate to identify and pursue a plan for building and operating the Beneficiation Facility and Beneficiation Power Station.
Note on B103: Road Map of the Mbalam Mining Convention - Conditions Precedent: Project Leases for the initial territory covered by the Exploitation Permit, Mineral Terminal Area and Railway Area.
Note on B105: Road Map of the Mbalam Mining Convention - Conditions Precedent: These Agreements are to be entered into between The Mine Project Company, Cam Iron and the Government of Cameroon. An escrow account has to be established wherein the Mine Project Company shall contribute 25% of the total funds required to finance the Beneficiation Facility.
Note on A107: Road Map of the Mbalam Mining Convention - Conditions Precedent: Cam Iron and the Government of Cameroon shall agree on the list of qualified contractors.