## Sheet1
CONSTRUCTION PHASE COMPLIANCES MONITORING TABLE
Monitoring Items/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Status | Individual/authority accountable for compliance | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Environmental and Security Issues | Issue and maintain a Bank Guarantee in the sum of US$20 million as the Mineral Terminal Guarantee (Article 29.2.1 (d) of the Mbalam Convention) | 10 business day from Project Commissioning | Mineral Terminal Project Company or Cam Iron on behalf of the latter |  |  | Not yet done | Designated representation of the Mineral Terminal Project Company or General Manager/CFO Cam Iron |  | Issuance and maintenance of the bank gurantee in the sum of twenty million USD until one year after the expiration of the concession to operate the Mineral Terminal Concession | To secure the obligations under the Environmental and Social Assessmnt and Management Plan and the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
| Undertaking to make financial contributions in the sum of US$ 20 million per year for five years to finance the South and East Regions Plan (Article 29.5.1 (d) of the Mbalam Convention) | 29/May/2013 | Cam Iron |  |  | Not yet done | General Manager/CFO Cam Iron |  | Payment of US$20 million per year for five years | To properly manage the social and environmental impact in resulting from the Project which is situtaed in the second largest ecological reserve in the world | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
| Approve waste management procedures and ensure compliance with the said procedures. These procedures are: | Prior to the commencement of work in the Project Area | Project Companies, Contractors and Sub-Contractors |  |  | Not yet done |  |  | Approval of waste management procedures and compliance with the said procedures | Protection of the Environment in compliance with the Legislation and standard set forth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Ensure that all waste is disposed in an environmental sensitive manner and as per the existing legislation;
- Take all reasonable steps to minimize the release of dangerous waste into the environment;
- Ensure that all contractor and sub-contractor waste are disposed daily at a location approved by the Project Company under existing legislation;
- Keep the Project Area clean and tidy;
Remove waste accumulated during the performance of work at most 21 days after the of the contract or termination of the Convention;
- Minimise the dust generated during works;
- Use only designated wash down areas for cleaning the machine;
- Ensure that personnel minimize lighting of fires or making tracts/roads that will disturb the ground surface and established flora and fauna;
- Maintain a register of all the chemicals fuels, oils and gases kept on the Project Area;
- Reporting of any incident in accordance with the Project reporting procedures;
Apply ‘Good International Industry Practice’ inclusive, but not limited to: the 2012 IFC Performance Standards on Environment and Social Sustainability, the IFC/World Bank Environmental Health and Safety Guidelines, Voluntary Principles on Security and Human Rights ILO Convention on Indigenous and Tribal People in Independent Countries, the UN Declaration on the Rights of Indigenous People International Commission on Mining and Metals and the World Commission on Dams (Article 29.4 (h)of the Mbalam Convention)
| Prepare, implement and comply with accident prevention schemes and emergency plans (Article 29.3 (a) (i) of the Mbalam Convention) | Prior to the commencement of work in the Project Area | Project Companies, Contractors and Sub-Contractors |  |  | Not yet done |  |  | Prepare, implment and comply with accident prevention schemes | Aim at preventing loss or threatened loss that posese risk to the Environment, personnel or the safety of persons and assets | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
| Conduct awareness campaigns on safety, health and diseases (Article 29.3 (a) of the Mbalam Convention | Prior to the commencement of work in the Project Area | Project Companies, Contractors and Sub-Contractors |  |  | Not yet done |  |  | Conduct and implement awareness campaigns on safety, health and disease | Aim at informing personnel | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
| Prepare, implement and comply with detailed procedures in order to guarantee optimum health and safety (Article 29.3 (a) (ii) of the Mbalam Convention) | Prior to the commencement of work in the Project Area | Project Companies, Contractors and Sub-Contractors |  |  | Not yet done |  |  | Prepare, implment and comply with procedures guaranteeing health and safety | Guarantee health and safety of personnel and Third Parties involved in the Project Operations or having a right to access the Project Facilities and or the Project Areas | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
| Undertaking to contribute the sum of US$ 700,000 per year to the sustainable development and community support fund (Article 29.5.(i) of the Mbalam Convention) | 29 May 2014 | Cam Iron and Project Companies |  |  | Not yet done |  |  | Undertaking (in our opinion in writing) to the Cameroon Government | to fund a sustainable development and community support fund | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
| Conclusion of a Conservation Convention | 29 May 2014 | Cam Iron and State of Cameroon |  |  | Not yet done |  |  | Submission to the State a plan for conservation and sustainable management of the forest Management Unit, payment of an annual fee of 2000 FCFA per hectare into a fund to fund conservation expenses | To detail the basis for the management and operation of activities of the Forest Management Unit which is contiguous to the Exploitation Area, to conserve the FMU as a biodiversity area, preservation of carbon credits related to FMU, establishment of an ecotourism area within the FMU and securing the FMU and dealing with trespasses | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
Note on A9: Enga Kameni: Construction phase means (i) with regard to the mining, railway and mineral terminal facilities is the period commecing on the Date of Entry into force until Project Commissioning subject, as the case may be, to the issuance of the Finding of Compliance and (ii) for any other Project Facilities, including the Beneficial Facility, the period during which the Project Company in charge of the Project Facility incurs expenses in connection with the acquisition, the development, and construction of such Project Facility until completion and commissioning of such other Project Facility after having been subject, as the case may be, to the issuance of the Finding of Compliance
Note on C13: Road Map of the Mbalam Mining Convention Project Commission means whichever date occurs last between the following three dates: - the date Mine Commissioning occurs; the date Railway Commissioning occurs or - the date Mineral terminal Commissioning occurs
Note on K13: Road Map of the Mbalam Mining Convention The aim is also to remedy damages caused to the environment, rehabilitation of the Project Area and the proper performance of environmental obligations
Note on B31: Enga Kameni: The Conservation Convention will deal with the management and operation of activities of the Forest Management Unit (FMU) and shall include provisions dealing with conservation of FMU as a biodiversity area and the preservation of all carbon credits associated with the FMU for the benefit of the Project Companies; the establishment of an ecotourism facility within the FMU and the protocols securing the FMU dealin with trespasses