## Lands Issues
CONSTRUCTION PHASE COMPLIANCES MONITORING TABLE
Monitoring Items/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Up to date status of compliance | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Land Issues | Occupation and use of private land | whenever the expropriation will be needed any Project Companies | Cam Iron or Others Project Compagnies |  | Whenever it is needed | State/ Cam Iron or all Others Comapnies requested the expropriation | Non specified | Non Specified | The State will be requested according to the procedure of expropriation under the Mining Code and this Agreement including Article 28 of the Mballam Convention
| Fees and indemnification | During the execution of the project | The Mining Project Compagnies | Cam Iron | To be accomplished whenever the expropriation will be needed | State and the Mine Compagnies | Non specified | Non Specified | The land concerned by the expropriation measure and by the indemnities paid to Third Parties (and the latter's identity) pursuant to the provisions respectively of Articles 28.1 and 28.2, shall be published in the Official Gazette, to the extent required by Legislation. | Non Specified | Non specified
| Covenants by the State on Conflicting Land Use | During the execution of the project | State and the and the projet compagnies |  | To be accomplished whenever the expropriation will be needed | State and the Mine Compagnies | Non specified |  | (a) Subject to the Legislation and the Reserved Rights, the State undertakes to: (i) ensure that its various ministries do not create or authorize material conflicting land use with respect to the land on which the Project Operations are being undertaken or conservation operations which are being undertaken by Cam Iron or a Project Company to offset the impact of Project Operations (including in accordance with the Conservation Convention); (ii) enforce any provisions of any concession, licence agreement, right or title that it has granted or entered into with a Third Party where the failure to do so is allowing that Third Party to cause or create a materially adverse land use with respect to the Project Operations; and (iii) not grant to a Third Party any rights to the land described in the Mineral Terminal Agreement as being set aside for expansion of the Mineral Terminal to achieve the Design Capacity nor will the State permit any ministry to utilise any of that land so set aside without having sought the confirmation from the Mineral Terminal Project Company that it no longer has any potential need for that land for the purpose of creating Expansion Capacity. To the extent possible, the Parties will consider including this land in the initial Project Lease for the Mineral Terminal Facility to avoid potential conflicts. Any violation of the foregoing by the State may be deemed a Compensation Event, subject to the definition set forth in Article 1 hereof, and, as such, may qualify for Convention Compensation pursuant to Article 39 hereof | Non Specified | Non specified | Any violation of the foregoing by the State may be deemed a Compensation Event, subject to the definition set forth in Article 1 hereof, and, as such, may qualify for Convention Compensation pursuant to Article 39 hereof.
| Emergency access to lands outside the Project Areas | Non spefcified | Cam Iron or Others Project Compagnies, contractor or subcontractor | Cam Iron | Whenever emergency is reported in the Project | Cam Iron and any applicable Project Company, Contractor or Subcontractor shall | Non specified | Non Specified |  | Non Specified | Non specified | Non specified
| Prohibition on the right to sublease, assign or pledge | During the execution of the project | The Project Companies | The Project Companies | during the execution of the project
Note on B11: Ernst & Young: Following the entry in force of the Mining Agreement, the State is required to grant lands to the Mine Project Company upon request by the latter. As per the Mining Code, the request is filed before the Minister in charge of Mines specifying the boundaries and the purpose of the request of an exclusive occupancy of the land. The Minister of Mines is required to forward the request to the Minister in charge of Lands requesting state approval and the expropriation of the lands needed for the Mbalam Ore. The Minister in charge of Lands shall approve such works by Ministerial Order. The said Ministerial Order shall designate the competent Senior Divisional Officer who shall have the relevant inquiry conducted by an affidavit and assessment committee. The committee shall be allowed six months from the time the matter was referred to them to produce the documents required to prepare the expropriation decree for the requested land. It is upon the issuance of the expropriation decree that the lands concerned shall be registered in the name of the State by the Minister in charge of lands who will equally issue an Order authorising the conclusion of the Project lease (long term lease) to be signed between the Mines Project Company and the Senior Divisional officer of the jurisdiction of the project
Note on J11: Ernst & Young: Following the entry in force of the Mining Agreement, the State is required to grant lands to the Mine Project Company upon request by the latter. As per the Mining Code, the request is filed before the Minister in charge of Mines specifying the boundaries and the purpose of the request of an exclusive occupancy of the land. The Minister of Mines is required to forward the request to the Minister in charge of Lands requesting state approval and the expropriation of the lands needed for the Mbalam Ore. The Minister in charge of Lands shall approve such works by Ministerial Order. The said Ministerial Order shall designate the competent Senior Divisional Officer who shall have the relevant inquiry conducted by an affidavit and assessment committee. The committee shall be allowed six months from the time the matter was referred to them to produce the documents required to prepare the expropriation decree for the requested land. It is upon the issuance of the expropriation decree that the lands concerned shall be registered in the name of the State by the Minister in charge of lands who will equally issue an Order authorising the conclusion of the Project lease (long term lease) to be signed between the Mines Project Company and the Senior Divisional officer of the jurisdiction of the project
Note on F12: Ernst & Young: The Mine Project Company shall fulfil its payment obligation within thirty (30) Days following receipt of said terms and conditions for payment, expressly provided that the rights to occupy and enjoy any land granted to the Mine Project Company is conditional upon the prior payment, by the Mine Project Company
Note on J12: Ernst & Young: This obligation is the responsibility of the State which provides: registration of the land concerned; signing expropriation orders on behalf of the State in accordance with the regulations in force.
Note on F13: Ernst & Young: The Project Companies shall give the State prompt notice of any event or circumstances known to them which has or could be reasonably be expected to result in conflicting land use or other violation of the State’s obligations of this Article 22.2 (whether material or not) so that the State may attempt to mitigate the impact, and the Project Companies shall cooperate with the State and use their reasonable efforts to mitigate any such impact.
Note on D14: Ernst & Young: According to article 22.4. In case of emergency, Cam Iron and any applicable Project Company, Contractor or Subcontractor shall, after having informed any competent authority thereof to the extent possible, take any reasonable step or measure in order to prevent any imminent hazard or emergency situation of which it will be advised in the areas immediately adjacent to the Project Areas.
Note on D15: Ernst & Young: According to article 22.5 The Project Companies will not have the right: (a) to sublease all or part of the Project Areas; (b) to assign all or part of their rights in the Project Areas; or (c) to mortgage, secure, pledge, assign by way of security, or grant any other security interest over all or part of any Project Area, except for the assignments or securities provided for under the Finance Documents,.