## Sheet1
CONSTRUCTION PHASE COMPLIANCES MONITORING TABLE
Monitoring Items/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Up to date status of compliance | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Mining Facilities | Project Lease Request | 12 July 2013 | CAM IRON SA |  | Not Specified | Minister in Charge of Mines | Not started |  | File stating the boundaries and the purpose of the land object of the request | Land Exproriation Decree Registration of of land in the name of the State Issue of Order authorising the conclusion of long term lease
| Grant of Exploitation Lease to the Mine Project Company | 12 July 2013 | The Republic of Cameroon\ |  |  | The President of the Republic The Minister in Charge of Mines | Not started
| Access and occupation of the Exploitation Area | N/A | The Mine Project Company |  |  | N/A | Not started |  | N/A | N/A | N/A | N/A
| Mine Project Company Environmental Bank Guarantee | Wiithin ten (10) Business Days as from the commencement of ground construction in the Construction Phase | The Mine Company or CAM IRON SA on behalf of the Mine Company |  |  | N/A | Not started |  | N/A
| Mine Commissioning | Six (6) years following the Date of Entry into Force or such later date as otherwise agreed. | CAM IRON SA The Mine Project Company |  |  | The State | Not started
Note on A13: Road Map of the Mbalam Mining Convention Mining Facilities with respect to the Construction Phase of the Project Comprises of all facilities constructed or operated within the Exploitation Area and which are used for the mining, crushing, screening and processing in view of producing the Mbalam Ore. The right to engage into such construction on the exploitation area is however subject to procurring the Project Lease which provides entitlement to the land necessary for the mining of the Mbalam Ore. It should be noted that unlike the case of construction of Other Facilities, where the Mine Project Company is required to file a request to the State identifying the Contractors or Subcontractors contemplated for the works, for the construction of the Mining Facilities, the Mine Project Company is not required to provide a request nor identify the Contractors and/or Subcontractors Upon obtaining the lease
Note on B13: Road Map of the Mbalam Mining Convention Following the entry in force of the Mining Agreement, the sate is required to grant lands to the Mine Project Company upon request by the latter. As per the Mining Code, the request is filed before the Minister in charge of Mines specifying the boundaries and the purpose of the request of an exclusive occupancy of the land. The Minister of Mines is required to forward the request tot he Minister in charge of Lands requesting state approval and the expropriation of the lands needed for the Mbalam Ore. The Minister in charge of Lands shall approve such works by Ministerial Order. The said Ministerial Order shall designate the competent Senior Divisional Officer who shall have the relevant inquiry conducted by a the affidavit and assessment committee. The committee shall be allowed six months from the time the matter was referred to them to produce the documents required to prepare the expropriation decree for the requested land. It is upon the issuance of the expropriation decree that the lands concerned shall be registered in the name of the State by the Minister in charge of lands who will equally issue an Order authorising the conclusion of the Project lease (long term lease) to be signed between the Mines Project Company and the Senior Divisional officer
Note on C13: Road Map of the Mbalam Mining Convention Article 8.1. (a) (ii)
Note on J13: Road Map of the Mbalam Mining Convention All expenses, compensations and generally all the expenditure resulting from the implementation of the measures to release the land and make it available for use shall be borne by the Mine Project Company
Note on B14: Road Map of the Mbalam Mining Convention Project lease is intended to secure the use and occupation of a portion of land within the exploitation area and also determine precisely the rights and obligations of project company
Note on B15: Elvis Ngwa Nde:
Note on B17: Road Map of the Mbalam Mining Convention Cam Iron undertakes and stands surety for the Mine Commissioning under the conditions of this Convention. Cam Iron, the Mine Project Company and the State undertake to comply with their respective obligations to cooperate to ensure Mine Commissioning