## Feuil1
Conditions Precedents to be satisfied | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge | Due date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Conduct the Beneficiation Operations and Produce the Beneficiated Ore | Conduct the Beneficiation Operations and Produce the Beneficiated Ore | During the Exploitation Phase (Stage 1) | Mine Project Company |  |  |  | Pending | Beneficiation Specifications / Beneficiation Agreement |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Establish or obtain a power supply which is of sufficient capacity as to support Beneficiation Operations | Establish or obtain a power supply which is of sufficient capacity as to support Beneficiation Operations | During Construction Phase | Mine Project Company |  |  |  | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Submit a pre-feasibility study on the Beneficiation Power Station | Submit a pre-feasibility study on the Beneficiation Power Station | Prior to the Date of First Commercial Shipping | Cam Iron / Mine Project Company /State |  |  | Independant Engineer selected by the State | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Take the following actions prior to the submission of the Feasibility Study relating to the design and construction of the Beneficiation Power Station: | Take the following actions prior to the submission of the Feasibility Study relating to the design and construction of the Beneficiation Power Station: | Period prior to the delivery to the State of the Beneficiation Power Station Feasibility Study | Mine Project Company |  |  |  | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Complete and provide to the State a Beneficiation Feasibility Study and a feasibility study relating to the design and construction of the Beneficiation Power Station | Complete and provide to the State a Beneficiation Feasibility Study and a feasibility study relating to the design and construction of the Beneficiation Power Station | 3 years from the date of First Commercial Shipping and on every second (2nd) anniversary thereafter until the ending point specified in the Beneficiation Agreement | Cam Iron / Mine Project Company /State |  |  | Independant Engineer selected by the State | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Fund the review of the Beneficiation Feasibility Study or updated pre-feasibility study or the review the draft Beneficiation Power Station Feasibility Study or pre-feasibility study to be made by the independant Engineer selected by the State | Fund the review of the Beneficiation Feasibility Study or updated pre-feasibility study or the review the draft Beneficiation Power Station Feasibility Study or pre-feasibility study to be made by the independant Engineer selected by the State |  | Mine Project Company |  |  |  | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Receive comments from the State on the Feasibility Study of the Beneficiation Power Station provided | Receive comments from the State on the Feasibility Study of the Beneficiation Power Station provided | Eighty (180) Days following the date on which the State receives the Beneficiation Feasibility Study | State |  |  |  | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Take into account the comments or objections provided by the State and achieve a consensual Beneficiation Feasibility Study | Take into account the comments or objections provided by the State and achieve a consensual Beneficiation Feasibility Study | (90) Days following the date on which the Mine Project Company receives comments from the State on the Beneficiation Feasibility Study | Mine Project Company |  |  |  | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Decision to construct or not the Beneficiation Power Station | Decision to construct or not the Beneficiation Power Station |  | Mine Project Company / State |  |  |  | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Enter with the State into the Beneficiation Agreement | Enter with the State into the Beneficiation Agreement |  | Mine Project Company |  |  |  | Pending |  |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Enter into a power purchase agreement on commercially reasonable and customary terms to purchase the power required by the Mine Project Company based on the Initial Beneficiation Production Capacity, the Interim Beneficiation Production Capacity or the Targeted Annual Production Capacity. | Enter into a power purchase agreement on commercially reasonable and customary terms to purchase the power required by the Mine Project Company based on the Initial Beneficiation Production Capacity, the Interim Beneficiation Production Capacity or the Targeted Annual Production Capacity. | During Construction Phase | Mine Project Company |  |  |  | Pending | Project Agreement |  | Conduct Beneficiation Operations and produce the Beneficiated Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Ensure that the Beneficiation Facility achieves at least the Initial Beneficiation Production Capacity or the Interim Beneficial Production Capacity in certain circumstances (article 10.13) | Ensure that the Beneficiation Facility achieves at least the Initial Beneficiation Production Capacity or the Interim Beneficial Production Capacity in certain circumstances (article 10.13) | During Construction Phase | Mine Project Company |  |  |  | Pending |  |  | Fulfill the Convention requirements on the Beneficiation Facility production | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Ensure that after ramp up,the Beneficiation Facility produces no less than the Minimum Annual Beneficiated Ore Production | Ensure that after ramp up,the Beneficiation Facility produces no less than the Minimum Annual Beneficiated Ore Production | From the date of BF Commissioning |  |  |  |  | Pending |  |  | Fulfill the Convention requirements on the Beneficiation Facility production | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Ensures that the production capacity of the Beneficiation Facility increases where the capacity to produce High Grade Ore from the Project reduces, in order to ensure the Beneficiation Facility, once built to a capacity of thirty-five (35) million Tonnes per annum and after ramp-up, produces Beneficiated Ore in an amount not less than the Targeted Annual Production Capacity. | Ensures that the production capacity of the Beneficiation Facility increases where the capacity to produce High Grade Ore from the Project reduces, in order to ensure the Beneficiation Facility, once built to a capacity of thirty-five (35) million Tonnes per annum and after ramp-up, produces Beneficiated Ore in an amount not less than the Targeted Annual Production Capacity. | During the Exploitation Phase (Stage 1) | Mine Project Company |  |  |  | Pending |  |  | Fulfill the Convention requirements on the Beneficiation Facility production | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Mine Project Company must carry out all Beneficiation Capacity Expansion Works necessary to maintain actual annual production capacity at a level equal to the Targeted Annual Production Capacity | Mine Project Company must carry out all Beneficiation Capacity Expansion Works necessary to maintain actual annual production capacity at a level equal to the Targeted Annual Production Capacity | Following BF Commissioning | Mine Project Company |  |  |  | Pending |  |  | Carry out the Expansion Works of the Beneficiation Facility | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Responsiblility for obtaining all Governmental Approvals necessary for Beneficiation Capacity Expansion Works (article 10.15) | Responsiblility for obtaining all Governmental Approvals necessary for Beneficiation Capacity Expansion Works (article 10.15) | Before Expansion Stage begins | Project Companies |  |  |  | Pending |  |  |  | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Sell at least fifteen percent (15%) in the aggregate of the total production of Beneficiated Ore to local processing facilities or steel mills (whether owned by the State or a Third Party located within the State) under financial terms and conditions that are consistent with international benchmark pricing and trading terms | Sell at least fifteen percent (15%) in the aggregate of the total production of Beneficiated Ore to local processing facilities or steel mills (whether owned by the State or a Third Party located within the State) under financial terms and conditions that are consistent with international benchmark pricing and trading terms | At any time during the Term of the Project | Mine Project Company |  |  |  | Pending |  |  | Respect the quotas of local transformation of Iron Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Ensure that at least fifteen percent (15%) of the Beneficiated Ore is processed by the Cameroonian company on reasonable terms and competitive prices | Ensure that at least fifteen percent (15%) of the Beneficiated Ore is processed by the Cameroonian company on reasonable terms and competitive prices | At any time during the Term of the Project | Mine Project Company |  |  |  | Pending | Beneficiation Agreement |  | Respect the quotas of local transformation of Iron Ore | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Note on A6: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : We specified that any Operations to be carried out by the Mine Project Company shall first be subject to their registration at the Cameroon Trande Register (article 6.4) and to the transfer by Cam Iron of the Mining Exploitation Permit and of the Exploitation Lease (article 8.1). The conduct of Beneficiation activities is subject to the grant of the Exploitation Permit to the Mine Project Company is subject to the production by the Mine Company of commercially exploitable Mbalam Ore, the production of beneficiated Ore being subject to the construction of the Beneficiation Facility.
Note on B6: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : We specified that any Operations to be carried out by the Mine Project Company shall first be subject to their registration at the Cameroon Trande Register (article 6.4) and to the transfer by Cam Iron of the Mining Exploitation Permit and of the Exploitation Lease (article 8.1). The conduct of Beneficiation activities is subject to the grant of the Exploitation Permit to the Mine Project Company is subject to the production by the Mine Company of commercially exploitable Mbalam Ore, the production of beneficiated Ore being subject to the construction of the Beneficiation Facility.
Note on A7: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : In order to provide the power sufficient for Beneficiation Operations the State may, within a period established in the Beneficiation Agreement, elect, in its discretion, to construct, own and operate, or procure the construction and operation of the Beneficiation Power Station. In the event the State does not elect to do so, the Mine Project Company shall designate one or more Third Parties approved by the State (such approval shall not be unreasonably withheld) to build, own and/or operate the Beneficiation Power Station. The provisions set forth herein regarding the obligations of the Mine Project Company in respect of causing the construction and operation of the Beneficiation Power Station shall be set forth in the Beneficiation Agreement and shall apply to the State in the event it elects to construct, own and operate, or procure the construction and operation of the Beneficiation Power Station.
Note on B7: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : In order to provide the power sufficient for Beneficiation Operations the State may, within a period established in the Beneficiation Agreement, elect, in its discretion, to construct, own and operate, or procure the construction and operation of the Beneficiation Power Station. In the event the State does not elect to do so, the Mine Project Company shall designate one or more Third Parties approved by the State (such approval shall not be unreasonably withheld) to build, own and/or operate the Beneficiation Power Station. The provisions set forth herein regarding the obligations of the Mine Project Company in respect of causing the construction and operation of the Beneficiation Power Station shall be set forth in the Beneficiation Agreement and shall apply to the State in the event it elects to construct, own and operate, or procure the construction and operation of the Beneficiation Power Station.
Note on C8: Road Map of the Mbalam Mining Convention - Exploitation phase - Beneficiation Operations Compliance: It being understood that this date refers to the date on which shall occur the first loading on a vessel of at least sixty thousands (60,000) Tonnes of Blended Ore (excluding shipping intended for one or more steel plants aiming at testing the iron ore), made effective by the issuance of the bill of loading relative to this first commercial shipping.
Note on A9: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : Actions to be taken consist of: - Conduct (or procure the conduct of) technical and economic studies relating to the building of or contracting a Third Party to build the Beneficiation Power Station or provide the required power on a regular basis and in accordance with any related provisions established in the Beneficiation Agreement; and - Inform the State of the findings of such studies; - Consult with the State in order to determine whether the State wishes to ensure that there is sufficient capacity within the Beneficiation Power Station to produce power in excess of the Mine Project Company’s requirements for the purposes of its Beneficiation Operations and, to the extent the State wishes there to be such additional capacity, it must provide such incentives or financial support to ensure the Mine Project Company does not incur a tariff for electricity which is greater than it would have, had the capacity of the Beneficiation Power Station been no more than was needed for the purposes of the Beneficiation Operations.
Note on B9: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : Actions to be taken consist of: - Conduct (or procure the conduct of) technical and economic studies relating to the building of or contracting a Third Party to build the Beneficiation Power Station or provide the required power on a regular basis and in accordance with any related provisions established in the Beneficiation Agreement; and - Inform the State of the findings of such studies; - Consult with the State in order to determine whether the State wishes to ensure that there is sufficient capacity within the Beneficiation Power Station to produce power in excess of the Mine Project Company’s requirements for the purposes of its Beneficiation Operations and, to the extent the State wishes there to be such additional capacity, it must provide such incentives or financial support to ensure the Mine Project Company does not incur a tariff for electricity which is greater than it would have, had the capacity of the Beneficiation Power Station been no more than was needed for the purposes of the Beneficiation Operations.
Note on A10: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance: The State shall have the right to use and share with Third Parties the Beneficiation Power Station Feasibility Study for the purpose of constructing the Beneficiation Power Station. The Project Companies shall keep the State informed of their timetable for preparing the Beneficiation Feasibility Study and Beneficiation Power Station Feasibility Study so that the State may arrange for the prompt review by its Independent Engineer.
Note on B10: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance: The State shall have the right to use and share with Third Parties the Beneficiation Power Station Feasibility Study for the purpose of constructing the Beneficiation Power Station. The Project Companies shall keep the State informed of their timetable for preparing the Beneficiation Feasibility Study and Beneficiation Power Station Feasibility Study so that the State may arrange for the prompt review by its Independent Engineer.
Note on D10: Ernst & Young:
Note on A11: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : In principle, the Independent Engineer shall be engaged by the State, at the sole expense of the State. However, the Mine Project Company shall set aside (for multiple studies if needed) five hundred thousand (500,000) US Dollars to fund such expense, from dividends due to the State. The Project Companies and their Subsidiaries shall and shall cause any person or entity preparing the Beneficiation Feasibility Study and Beneficiation Power Station Feasibility Study to cooperate with the Independent Engineer as it conducts its business and provide them with any materials they request.
Note on B11: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : In principle, the Independent Engineer shall be engaged by the State, at the sole expense of the State. However, the Mine Project Company shall set aside (for multiple studies if needed) five hundred thousand (500,000) US Dollars to fund such expense, from dividends due to the State. The Project Companies and their Subsidiaries shall and shall cause any person or entity preparing the Beneficiation Feasibility Study and Beneficiation Power Station Feasibility Study to cooperate with the Independent Engineer as it conducts its business and provide them with any materials they request.
Note on A13: Road Map of the Mbalam Mining Convention - Exploitation phase Beneficiation Operations compliance : If the Parties are unable to achieve a consensus on the Beneficiation Feasibility Study, then either Party may refer the disagreement to the Expert Procedure for resolution as a Technical Dispute or to the ordinary Dispute settlement procedure.
Note on B13: Road Map of the Mbalam Mining Convention - Exploitation phase Beneficiation Operations compliance : If the Parties are unable to achieve a consensus on the Beneficiation Feasibility Study, then either Party may refer the disagreement to the Expert Procedure for resolution as a Technical Dispute or to the ordinary Dispute settlement procedure.
Note on A14: Road Map of the Mbalam Mining Convention Exploitation Phase Beneficiations Operationc Compliance : Where a Beneficiation Feasibility Study demonstrates that the conditions in the BF Construction Conditions are not met, then the State cannot require the Mine Project Company to conduct the Beneficiation Operations. However, if the Mine Project Company is not obliged to conduct the Beneficiation Operations, then the Mine Project Company may nevertheless commit in writing to conduct the Beneficiation Operations, subject to the terms of the Project Agreements (a “Beneficiation Election”). If the State does not elect to build the Beneficiation Power Station, the Mine Project Company shall obtain or cause the Third Party designated to construct the Beneficiation Power Station to obtain whatever authorisations, approvals, consents and licences that are necessary for such Third Party to build and operate the Beneficiation Power Station.
Note on B14: Road Map of the Mbalam Mining Convention Exploitation Phase Beneficiations Operationc Compliance : Where a Beneficiation Feasibility Study demonstrates that the conditions in the BF Construction Conditions are not met, then the State cannot require the Mine Project Company to conduct the Beneficiation Operations. However, if the Mine Project Company is not obliged to conduct the Beneficiation Operations, then the Mine Project Company may nevertheless commit in writing to conduct the Beneficiation Operations, subject to the terms of the Project Agreements (a “Beneficiation Election”). If the State does not elect to build the Beneficiation Power Station, the Mine Project Company shall obtain or cause the Third Party designated to construct the Beneficiation Power Station to obtain whatever authorisations, approvals, consents and licences that are necessary for such Third Party to build and operate the Beneficiation Power Station.
Note on A15: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : The Beneficiation Agreement shall describe a process by which the Parties will consider different alternatives and cooperate to identify and pursue a plan for building and operating the Beneficiation Facility and Beneficiation Power Station. The Beneficiation Agreement will, in accordance with Article 10.3, address: (a) the procurement framework for the output of the Beneficiation Power Station and consider components of the tariff based on a reasonable return of and return on equity and other factors; and (b) the term of the concession which will be tied to the duration of the Exploitation Permit. The Beneficiation Agreement, on mutually agreeable terms, shall also provide the State with an option to build or cause to build the Beneficiation Power Station and to participate in the equity funding of the Beneficiation Power Station. Power sold to purchasers other than the Mine Project Company will not be included in the return to the equity holders of the owner and operator of the Beneficiation Power Station. The Beneficiation Agreement shall also address the details regarding the determination of whether the BF Construction Conditions have been met including specifying the formulae and methodology for calculating the Internal Rate of Return. The Parties acknowledge that in determining whether the BF Construction Conditions have been satisfied, the calculation of the Internal Rate of Return shall: - Be based on an assumption that the Beneficiation Facility has achieved the Targeted Annual Production Capacity for each year of Beneficiation Operations, notwithstanding the fact that the Beneficiation Facility may only be constructed to achieve the Initial Beneficiation Production Capacity or the Interim Beneficiation Production Capacity, or may otherwise achieve less that the Targeting Annual Production Capacity as a result of the flexibility being afforded to the Mine Project Company in achieving the Targeted Annual Production Capacity; and - Include the estimated investment and exploitation costs known as at the BF Construction Deadline (including reasonable contingency, escalation and inflation allowances and the estimated charge for power supply referred to in Article 10.5 and the forecast iron ore prices for the relevant iron ore products based on a mutually agreeable forecast such as the CRU forecast for relevant iron ore price for the years of the Beneficiation Operations, including the long term average where applicable, as of that date being such that they would enable the marketing of the Beneficiated Ore at an internationally competitive price. The Mine Project Company is to achieve an Internal Rate of Return for the Beneficiation Operations of not less than a rate equal to the Reference Rate plus five hundred (500) basis points.
Note on B15: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : The Beneficiation Agreement shall describe a process by which the Parties will consider different alternatives and cooperate to identify and pursue a plan for building and operating the Beneficiation Facility and Beneficiation Power Station. The Beneficiation Agreement will, in accordance with Article 10.3, address: (a) the procurement framework for the output of the Beneficiation Power Station and consider components of the tariff based on a reasonable return of and return on equity and other factors; and (b) the term of the concession which will be tied to the duration of the Exploitation Permit. The Beneficiation Agreement, on mutually agreeable terms, shall also provide the State with an option to build or cause to build the Beneficiation Power Station and to participate in the equity funding of the Beneficiation Power Station. Power sold to purchasers other than the Mine Project Company will not be included in the return to the equity holders of the owner and operator of the Beneficiation Power Station. The Beneficiation Agreement shall also address the details regarding the determination of whether the BF Construction Conditions have been met including specifying the formulae and methodology for calculating the Internal Rate of Return. The Parties acknowledge that in determining whether the BF Construction Conditions have been satisfied, the calculation of the Internal Rate of Return shall: - Be based on an assumption that the Beneficiation Facility has achieved the Targeted Annual Production Capacity for each year of Beneficiation Operations, notwithstanding the fact that the Beneficiation Facility may only be constructed to achieve the Initial Beneficiation Production Capacity or the Interim Beneficiation Production Capacity, or may otherwise achieve less that the Targeting Annual Production Capacity as a result of the flexibility being afforded to the Mine Project Company in achieving the Targeted Annual Production Capacity; and - Include the estimated investment and exploitation costs known as at the BF Construction Deadline (including reasonable contingency, escalation and inflation allowances and the estimated charge for power supply referred to in Article 10.5 and the forecast iron ore prices for the relevant iron ore products based on a mutually agreeable forecast such as the CRU forecast for relevant iron ore price for the years of the Beneficiation Operations, including the long term average where applicable, as of that date being such that they would enable the marketing of the Beneficiated Ore at an internationally competitive price. The Mine Project Company is to achieve an Internal Rate of Return for the Beneficiation Operations of not less than a rate equal to the Reference Rate plus five hundred (500) basis points.
Note on A17: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : It being understood that the Initial Beneficiation Production Capacity refers to a production capacity of no less than eleven (11) million Tonnes of Beneficiated Ore in any Calendar Year (or a pro rata portion of such tonnage based on the number of applicable Days in such Calendar Year) commencing on the date that is twelve (12) months following the BF Commissioning where the Beneficiation Facility is first built to that capacity, and that the Interim Beneficiation Production Capacity means a production capacity of no less than twenty two (22) million Tonnes of Beneficiated Ore in any Calendar Year (or a pro rata portion of such tonnage based on the number of applicable days in such Calendar Year) commencing on the date that is twelve (12) months following the BF Commissioning where the Beneficiation Facility is built to that capacity.
Note on B17: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : It being understood that the Initial Beneficiation Production Capacity refers to a production capacity of no less than eleven (11) million Tonnes of Beneficiated Ore in any Calendar Year (or a pro rata portion of such tonnage based on the number of applicable Days in such Calendar Year) commencing on the date that is twelve (12) months following the BF Commissioning where the Beneficiation Facility is first built to that capacity, and that the Interim Beneficiation Production Capacity means a production capacity of no less than twenty two (22) million Tonnes of Beneficiated Ore in any Calendar Year (or a pro rata portion of such tonnage based on the number of applicable days in such Calendar Year) commencing on the date that is twelve (12) months following the BF Commissioning where the Beneficiation Facility is built to that capacity.
Note on A18: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance: That is to say a minimum of eleven (11) million Tonnes of Beneficiated Ore from the Beneficiation Facility in any Calendar Year commencing in the date that is twelve (12) months following the Beneficiation Facility Commissionning.
Note on B18: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance: That is to say a minimum of eleven (11) million Tonnes of Beneficiated Ore from the Beneficiation Facility in any Calendar Year commencing in the date that is twelve (12) months following the Beneficiation Facility Commissionning.
Note on A19: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : It being understood that the Targeted Annual Production Capacity means, prior BF Commissioning, a target of thirty five (35) million Tonnes per annum of Mbalam Ore and Nabeba Ore and, after the establishment of the Beneficiation Facility, that facility achieving a production capacity of thirty -five (35) million Tonnes per annum of Mbalam Ore as provided for in this Convention.
Note on B19: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : It being understood that the Targeted Annual Production Capacity means, prior BF Commissioning, a target of thirty five (35) million Tonnes per annum of Mbalam Ore and Nabeba Ore and, after the establishment of the Beneficiation Facility, that facility achieving a production capacity of thirty -five (35) million Tonnes per annum of Mbalam Ore as provided for in this Convention.
Note on A20: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance Mine Project Company must undertake Beneficiation Capacity Expansion Works in order to maintain the Targeted Annual Production Capacity, the Mine Project Company must: - Notify the State of the proposed schedule for the commencement of construction and the completion of the relevant Beneficiation Capacity Expansion Works (the "Proposed Expansion Schedule") at least one hundred and eighty (180) Days prior to the commencement of such construction works; - Obtain the State’s approval, which will not be unreasonably withheld, for any changes to the Proposed Expansion Schedule; (iii) notify the State of the actual date of commencement of construction of the relevant Beneficiation Capacity Expansion Works within seven (7) Days of that date; and (iv) notify the State of the actual date of the completion of the Beneficiation Facility Commissioning of the relevant Beneficiation Capacity Expansion Works within seven (7) Days of that date.
Note on B20: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance Mine Project Company must undertake Beneficiation Capacity Expansion Works in order to maintain the Targeted Annual Production Capacity, the Mine Project Company must: - Notify the State of the proposed schedule for the commencement of construction and the completion of the relevant Beneficiation Capacity Expansion Works (the "Proposed Expansion Schedule") at least one hundred and eighty (180) Days prior to the commencement of such construction works; - Obtain the State’s approval, which will not be unreasonably withheld, for any changes to the Proposed Expansion Schedule; (iii) notify the State of the actual date of commencement of construction of the relevant Beneficiation Capacity Expansion Works within seven (7) Days of that date; and (iv) notify the State of the actual date of the completion of the Beneficiation Facility Commissioning of the relevant Beneficiation Capacity Expansion Works within seven (7) Days of that date.
Note on A22: Road Map of the Mbalam Mining Convention Exploitation Phase Beneficiation Operations Compliance : Such obligation is only relevant iin the event of there being a processing unit within the territory of the State capable of processing the Beneficiated Ore produced by the Mine Project Company.
Note on B22: Road Map of the Mbalam Mining Convention Exploitation Phase Beneficiation Operations Compliance : Such obligation is only relevant iin the event of there being a processing unit within the territory of the State capable of processing the Beneficiated Ore produced by the Mine Project Company.
Note on A23: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : Only if any Beneficiated Ore is processed into pellets by the Mine Project Company and there is a pelletisation facility that is a Cameroonian company that could process a portion of the Beneficiated Ore.
Note on B23: Road Map of the Mbalam Mining Convention - Exploitation Phase Beneficiation Operations Compliance : Only if any Beneficiated Ore is processed into pellets by the Mine Project Company and there is a pelletisation facility that is a Cameroonian company that could process a portion of the Beneficiated Ore.