## Feuil1
Conditions precedent to be satisfied | Required actions or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Status | Due Date for action | State authority accountable for compliance | Person in charge | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Prepare, implement and comply with accident prevention schemes and emergency plans (Article 29.3 (a) (i) of the Mbalam Convention) | Prepare, implement and comply with accident prevention schemes and emergency plans (Article 29.3 (a) (i) of the Mbalam Convention) | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Draft and execute an accident prevention schemes |  | Prevent loss or threatened loss that may be harmful to the Environment, personnel or the safety of persons and assets | The State of Cameroon will apply as penalty any amount provided for under applicable Legislation in the event of non-compliance
Conduct awareness campaigns on safety, health and diseases (Article 29.3 (a) of the Mbalam Convention | Conduct awareness campaigns on safety, health and diseases (Article 29.3 (a) of the Mbalam Convention | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Safety rules , rules on prevention on health and diseases |  | Inform personnel, Third Parties involved in the Project Operations or having access to the Project Facilities and members of the communities immediately neighbouring the Project Areas | The State of Cameroon will apply as penalty any amount provided for under applicable Legislation in the event of non-compliance
Prepare, implement and comply with detailed procedures in order to guarantee optimum health and safety (Article 29.3 (a) (ii) of the Mbalam Convention) | Prepare, implement and comply with detailed procedures in order to guarantee optimum health and safety (Article 29.3 (a) (ii) of the Mbalam Convention) | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Prepare, implement and comply with procedures guaranteeing health and safety |  | Guarantee health and safety of personnel and Third Parties involved in the Project Operations or having a right to access the Project Facilities and or the Project Areas | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
Approve waste management procedures and ensure compliance with the said procedures. These procedures are: | Approve waste management procedures and ensure compliance with the said procedures. These procedures are: | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Ensure that all waste is disposed in an environmental sensitive manner and as per the existing legislation; | - Ensure that all waste is disposed in an environmental sensitive manner and as per the existing legislation; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Take all reasonable steps to minimize the release of dangerous waste into the environment; | - Take all reasonable steps to minimize the release of dangerous waste into the environment; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Ensure that all contractor and sub-contractor waste are disposed daily at a location approved by the Project Company under existing legislation; | - Ensure that all contractor and sub-contractor waste are disposed daily at a location approved by the Project Company under existing legislation; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Keep the Project Area clean and tidy; | - Keep the Project Area clean and tidy; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Remove waste accumulated during the performance of work at most 21 days after the of the contract or termination of the Conevtnion; | - Remove waste accumulated during the performance of work at most 21 days after the of the contract or termination of the Conevtnion; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Minimise the dust generated during works; | - Minimise the dust generated during works; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Use only designated wash down areas for cleaning the machine; | - Use only designated wash down areas for cleaning the machine; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Ensure that personnel minimize lighting of fires or making tracts/roads that will disturb the ground surface and established flora and fauna; | - Ensure that personnel minimize lighting of fires or making tracts/roads that will disturb the ground surface and established flora and fauna; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Maintain a register of all the chemicals fuels, oils and gases kept on the Project Area; | - Maintain a register of all the chemicals fuels, oils and gases kept on the Project Area; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
- Reporting of any incident in accordance with the Project reporting procedures; | - Reporting of any incident in accordance with the Project reporting procedures; | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
Apply ‘Good International Industry Practice’ inclusive, but not limited to: the Equator Principle, the 2012 IFC Performance Standards on Environment and Social Sustainability, the IFC/World Bank Environmental Health and Safety Guidelines, Voluntary Principles on Security and Human Rights ILO Convention on Indigenous and Tribal People in Independent Countries, the UN Declaration on the Rights of Indigenous People International Commission on Mining and Metals and the World Commission on Dams (Article 29.4 (h)of the Mbalam Convention) | Apply ‘Good International Industry Practice’ inclusive, but not limited to: the Equator Principle, the 2012 IFC Performance Standards on Environment and Social Sustainability, the IFC/World Bank Environmental Health and Safety Guidelines, Voluntary Principles on Security and Human Rights ILO Convention on Indigenous and Tribal People in Independent Countries, the UN Declaration on the Rights of Indigenous People International Commission on Mining and Metals and the World Commission on Dams (Article 29.4 (h)of the Mbalam Convention) | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Approval of waste management procedures and compliace with the said procedure |  | Protection of the Environment in compliance with the Legislation and standards setforth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
Notify the Government of Cameroon of any accident that occurs or any hazard that is identified within the Project Area or its immediate surroundings (Article 29.3 (c) of the Mbalam Convention) | Notify the Government of Cameroon of any accident that occurs or any hazard that is identified within the Project Area or its immediate surroundings (Article 29.3 (c) of the Mbalam Convention) | During the Exploitation Phase | Project Companies, Contractors and Sub-Contractors | Pending |  |  |  | Occurrence of an accident or Hazard |  | Protection of the Environment in compliance with the Legislation and standards set forth in the Convention | The State of Cameroon will apply as penalty any amount provided for under applicable legislation in the event of non-compliance
Undertaking to contribute 0.75% of the gross sale price of the Mbalam Ore to the Special Development Fund (Article 29.5.(g)of the Mbalam Convention) | Undertaking to contribute 0.75% of the gross sale price of the Mbalam Ore to the Special Development Fund (Article 29.5.(g)of the Mbalam Convention) | During the Exploitation Phase | Project Companies and Marketing Company | Pending |  |  |  | Setting up of the Fund Committee |  | Contribute to the Development of Project Areas | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Contribution of 0.75% of net profits of the Project after tax to enable Cam Iron to carry out the environmental and community support programs (Article 29.5.(i) of the Mbalam Convention) | Contribution of 0.75% of net profits of the Project after tax to enable Cam Iron to carry out the environmental and community support programs (Article 29.5.(i) of the Mbalam Convention) | From and after the Date of First Commercial Shipment | Cam Iron or the Project Companies | Pending |  |  |  | Environmental and community support programs |  | Enabling the carrying out of environmental and community support programs within the framework of the sustainable development undertakings entered into under the Environmental and Social Assessment and Management Plan
Draft and execute of a Conservation Convention | Draft and execute of a Conservation Convention | During the Exploitation Phase | Cam Iron and the State of Cameroon | Pending |  | Ministry of Mines / Ministry of Forests / Minstry of Finance |  |  |  | Fund conservation expenses
Note on C23: Road Map of the Mbalam Mining Convention - Exploitation Phase Environmental and Security : Date of First Commercial Shipping means the date on which shall occur the first loading on a vessel of at least 60,000 tonnes of Blended Ore (excluding shipping intended for one or more steel plants aiming at testing the iron ore) made effective by the issuance of the bill of loading relative to this first commercial shipping
Note on A24: Road Map of the Mbalam Mining Convention - Exploitation Phase Environment and Security: The Conservation Convention will deal with the management and operation of activities of the Forest Management Unit (FMU) and shall include provisions dealing with conservation of FMU as a biodiversity area and the preservation of all carbon credits associated with the FMU for the benefit of the Project Companies; the establishment of an ecotourism facility within the FMU and the protocols securing the FMU dealin with trespasses. Under such Convention, Cam Iron shall submit to the State a plan for conservation and sustainable management of the forest Management Unit, payment of an annual fee of 3000 FCFA per hectare into a fund to fund conservation expenses.
Note on B24: Road Map of the Mbalam Mining Convention - Exploitation Phase Environment and Security: The Conservation Convention will deal with the management and operation of activities of the Forest Management Unit (FMU) and shall include provisions dealing with conservation of FMU as a biodiversity area and the preservation of all carbon credits associated with the FMU for the benefit of the Project Companies; the establishment of an ecotourism facility within the FMU and the protocols securing the FMU dealin with trespasses. Under such Convention, Cam Iron shall submit to the State a plan for conservation and sustainable management of the forest Management Unit, payment of an annual fee of 3000 FCFA per hectare into a fund to fund conservation expenses.