## Feuil1
Conditions Precedent to be satisfied | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party action accountable for compliance | Person in charge | Due date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Comply with the provisions Marketing Agreement and the Monitoring Agreement – Marketing (article 17.1) | Comply with the provisions Marketing Agreement and the Monitoring Agreement – Marketing (article 17.1) | During the Term of both Agreements | Cam Iron/ Project Companies/ State |  |  | Ministry of Finances / Ministry of Mines | Pending |  |  | Marketing Agreement / Monitoring Agreement - Marketing | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Comply with the provisions of the Offtake Agreements on Arm’s Length Terms (article 17.2) | Comply with the provisions of the Offtake Agreements on Arm’s Length Terms (article 17.2) | During the term of the Offtake Agreements | Cam Iron / Marketing Company |  |  |  | Pending | Convention |  | Offtake Agreement
Comply with the provisions of the Treasury Agreement and the Monitoring Agreement – Treasury (article 17.3) | Comply with the provisions of the Treasury Agreement and the Monitoring Agreement – Treasury (article 17.3) | During the Term of both Agreements | Cam Iron/ Project Companies/ State |  |  | Ministry of Finances / Ministry of Mines | Pending |  |  | Treasury Agreement / Monitoring Agreement -Treasury
Note on A6: Road Map of the Mbalam Mining Convention - Exploitation Phase Marketing & Treasury Operations : Such Agreements shall collectively govern the marketing of Mbalam Ore and Blended Ore by the Marketing Company and which shall include provisions providing that all transactions involving Mbalam Ore and Blended Ore will be on terms and conditions that transparently pass the price paid (less a logistic and financing fee of two and a half per cent (2.5%) and an administrative fee of two and half per cent (2.5%)) for the Mbalam Ore, or the portion of Blended Ore that consists of Mbalam Ore, back to the Mine Project Company in accordance with the provisions of the Marketing Agreement and subject to the Monitoring Agreement- Marketing.
Note on B6: Road Map of the Mbalam Mining Convention - Exploitation Phase Marketing & Treasury Operations : Such Agreements shall collectively govern the marketing of Mbalam Ore and Blended Ore by the Marketing Company and which shall include provisions providing that all transactions involving Mbalam Ore and Blended Ore will be on terms and conditions that transparently pass the price paid (less a logistic and financing fee of two and a half per cent (2.5%) and an administrative fee of two and half per cent (2.5%)) for the Mbalam Ore, or the portion of Blended Ore that consists of Mbalam Ore, back to the Mine Project Company in accordance with the provisions of the Marketing Agreement and subject to the Monitoring Agreement- Marketing.
Note on A8: Road Map of the Mbalam Mining Convention - Exploitation Phase Marketing & Treasury Operations : Such Agreements shall collectively govern the Treasury Operations by the Treasury Company.
Note on B8: Road Map of the Mbalam Mining Convention - Exploitation Phase Marketing & Treasury Operations : Such Agreements shall collectively govern the Treasury Operations by the Treasury Company.