## Feuil1
Conditions precedents to be satisfied | Required actions or operations | Date for compliance (timeframe, deadline) | Party action accountable for compliance | Person in charge | Due date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Start the Mineral Terminal Operations after obtaining of the Mineral Terminal Concession and after Mineral Terminal Commissionning had bet met by the issuance of Finding of Compliance (article 13.1.j) | Start the Mineral Terminal Operations after obtaining of the Mineral Terminal Concession and after Mineral Terminal Commissionning had bet met by the issuance of Finding of Compliance (article 13.1.j) | During Exploitation Phase (Stage 1) | Mineral Terminal Project Company |  |  |  | Pending | Mineral Terminal Concession |  | Execution of the Mineral Terminal Operations in compliance with the provisions of the Convention | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Ensure that the Mineral Terminal Agreement is drafted and executed (article 13.1) | Ensure that the Mineral Terminal Agreement is drafted and executed (article 13.1) | During Construction Phase | Mineral Terminal Project Company |  |  |  | Pending |  |  | Executed Mineral Terminal Agreement | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Ensure that the Mineral Terminal initially handles the thirty five million (35,000,000) Tonnes of Ore in a Calendar Year and also handles the Design Capacity as specified in the Mineral Terminal Agreement | Ensure that the Mineral Terminal initially handles the thirty five million (35,000,000) Tonnes of Ore in a Calendar Year and also handles the Design Capacity as specified in the Mineral Terminal Agreement | During Construction Phase | Mineral Terminal Project Company |  |  |  | Pending | Mineral Terminal Agreement |  | Meet the capacity expectations of the Mineral Terminal | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Ensure that the tariffs payable with respect to the Mineral Terminal are calculated substantially in accordance with the draft Tariff Frameworks for the Railway and Mineral Terminal which are attached to this Convention as Annex III | Ensure that the tariffs payable with respect to the Mineral Terminal are calculated substantially in accordance with the draft Tariff Frameworks for the Railway and Mineral Terminal which are attached to this Convention as Annex III | During Exploitation Phase (Stage 1) | Mineral Terminal Project Company |  |  |  | Pending | Annex III of the Convention |  | Respect of the method of calculation of Tariff payable with respct to the Mineral Terminal | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Operate the Mineral Terminal in a manner that allows the Mineral Terminal to: (i) handle Initial Capacity and Expansion Capacity up to the Design Capacity); and (ii) incorporate technical aspects of the Mineral Terminal services being provided to any party up to the Design Capacity | Operate the Mineral Terminal in a manner that allows the Mineral Terminal to: (i) handle Initial Capacity and Expansion Capacity up to the Design Capacity); and (ii) incorporate technical aspects of the Mineral Terminal services being provided to any party up to the Design Capacity | During Exploitation Phase (Stage 1) | Mineral Terminal Project Company |  |  |  | Pending |  |  | Operate the Mineral Terminal in compliance with Operating Standards | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Maintain and keep the Mineral Terminal Facilities in sound working order and in accordance with this Convention and the Operating Standards (article 13.1.g) | Maintain and keep the Mineral Terminal Facilities in sound working order and in accordance with this Convention and the Operating Standards (article 13.1.g) | During Exploitation Phase (Stage 1) | Mineral Terminal Project Company |  |  |  | Pending | Operating Standards/ Convention |  |  | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Conduct all the works necessary and all the repairs of any damages that could occur in compliance with the provisions of the Mineral Terminal Agreement | Conduct all the works necessary and all the repairs of any damages that could occur in compliance with the provisions of the Mineral Terminal Agreement | During Exploitation Phase (Stage 1) | Mineral Terminal Project Company |  |  |  | Pending |  |  |  | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Provide to the State an independent report prepared by an independent expert approved by the State (article 13.1.h) | Provide to the State an independent report prepared by an independent expert approved by the State (article 13.1.h) | Within three (3) months of the end of every two (2) years commencing upon Project Commissioning | Mineral Terminal Project Company |  |  |  | Pending |  |  | Independant Expert Report | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Carry out the Mineral Terminal Operations within the surface, subsurface and waterside areas contemplated by the Mineral Terminal Agreement, the site plan of which will be attached to the Mineral Terminal Agreement (article 13.2.a) | Carry out the Mineral Terminal Operations within the surface, subsurface and waterside areas contemplated by the Mineral Terminal Agreement, the site plan of which will be attached to the Mineral Terminal Agreement (article 13.2.a) | During Exploitation Phase (Stage 1) | Mineral Terminal Project Company |  |  |  | Pending | Mineral Terminal Agreement |  | Operate the Mineral Terminal in compliance with Operating Standards | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Benefit of the grant to the Mineral Terminal Project Company of the right for a period of ten (10) years after the expiry of the Mineral Terminal Agreement to operate and maintain the Mineral Terminal (article 13.5) | Benefit of the grant to the Mineral Terminal Project Company of the right for a period of ten (10) years after the expiry of the Mineral Terminal Agreement to operate and maintain the Mineral Terminal (article 13.5) | Upon the expiration of the initial twenty-five (25) year term of the Mineral Terminal Company’s right to operate the Mineral Terminal | State |  |  | Ministry of Mines | Pending | Mineral Terminal Agreement |  | Renew the Mineral Terminal Agreement | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Possibility for The Mineral Terminal Project Company and the State to enter into the Mineral Terminal Operations Agreement (article 13.5.b) | Possibility for The Mineral Terminal Project Company and the State to enter into the Mineral Terminal Operations Agreement (article 13.5.b) | Upon the expiration of the initial twenty-five (25) year term of the Mineral Terminal Company’s right to operate the Mineral Terminal | Mineral Terminal Project Company / State |  |  | Ministry of Mines | Pending |  |  | Terminate the Mineral Terminal Agreement | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Possibility for the State to grant a Third Party the right to operate the Mineral Terminal Facilities (article 13.5.c) | Possibility for the State to grant a Third Party the right to operate the Mineral Terminal Facilities (article 13.5.c) | At the end of the initial twenty-five (25) year term of the right of the Mineral Terminal Project Company to operate the Mineral Terminal | State |  |  | Ministry of Mines | Pending |  |  |  | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Note on C6: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: Stage 1 of the Exploitation Phase means the period from the Date of First Commercial Shipping and ending on the earlier of (a) the date that the maximum capacity of the Railway Facilities and the Mineral Terminal Facilities achieves or is demonstrated to achieve thirty five (35) million Tonne per annum or, (b) the fourth (4th) anniversary from the Date of First Commercial Shipping.
Note on A7: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: The Mineral Terminal Agreement is to be drawn up as a BOOT model and shall, along with the Mineral Terminal Project Company Shareholders’ Agreement, provide and set the framework of the conditions for the funding and conduct, by the Mineral Terminal Project Company, of the Mineral Terminal Operations within the Mineral Terminal Area
Note on B7: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: The Mineral Terminal Agreement is to be drawn up as a BOOT model and shall, along with the Mineral Terminal Project Company Shareholders’ Agreement, provide and set the framework of the conditions for the funding and conduct, by the Mineral Terminal Project Company, of the Mineral Terminal Operations within the Mineral Terminal Area
Note on A8: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance : The Design Capacity means the one hundred million (100,000,000) tonnes of iron ore in a Calendar Year (consisting of thirty-five million (35,000,000) Tonnes plus sixty-five million (65,000,000) wet tonnes) based on the assumptions to be detailed in the Railway Agreement and Mineral Terminal Agreement.
Note on B8: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance : The Design Capacity means the one hundred million (100,000,000) tonnes of iron ore in a Calendar Year (consisting of thirty-five million (35,000,000) Tonnes plus sixty-five million (65,000,000) wet tonnes) based on the assumptions to be detailed in the Railway Agreement and Mineral Terminal Agreement.
Note on A10: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: It being understood that: The Initial Capacity means in million Tonnes per annum, the maximum number of Tonnes of iron ore that can be hauled using the Railway Facilities and handled and loaded onto vessels using the Mineral Terminal Facilities including any capacity created by operational efficiencies, de-bottlenecking and other minor capital works excluding any Expansion Capacity, based on the construction of such Railway Facilities and Mineral Terminal Facilities in accordance with the initial design specifications to achieve the Targeted Annual Production Capacity; The Expansion Capacity means the capacity of ore that can be hauled using the Railway Facilities and handled and loaded onto vessels using the Mineral Terminal Facilities based on construction of new facilities and assets that are beyond the scope of the design for the Initial Capacity; The Design Capacity means one hundred million (100,000,000) tonnes of iron ore in a Calendar Year (consisting of thirty-five million (35,000,000) Tonnes plus sixty-five million (65,000,000) wet tonnes) based on the assumptions to be detailed in the Railway Agreement and Mineral Terminal Agreement
Note on B10: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: It being understood that: The Initial Capacity means in million Tonnes per annum, the maximum number of Tonnes of iron ore that can be hauled using the Railway Facilities and handled and loaded onto vessels using the Mineral Terminal Facilities including any capacity created by operational efficiencies, de-bottlenecking and other minor capital works excluding any Expansion Capacity, based on the construction of such Railway Facilities and Mineral Terminal Facilities in accordance with the initial design specifications to achieve the Targeted Annual Production Capacity; The Expansion Capacity means the capacity of ore that can be hauled using the Railway Facilities and handled and loaded onto vessels using the Mineral Terminal Facilities based on construction of new facilities and assets that are beyond the scope of the design for the Initial Capacity; The Design Capacity means one hundred million (100,000,000) tonnes of iron ore in a Calendar Year (consisting of thirty-five million (35,000,000) Tonnes plus sixty-five million (65,000,000) wet tonnes) based on the assumptions to be detailed in the Railway Agreement and Mineral Terminal Agreement
Note on A13: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: The independant report shall be based on the maintenance carried out during the past two (2) years and the maintenance required during the succeeding two (2) year period in order to ensure that the applicable Mineral Terminal Project Company’s obligations are met. The Mineral Terminal Agreement will contain the form of instructions to be provided to the independent expert in connection with its audit.
Note on B13: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: The independant report shall be based on the maintenance carried out during the past two (2) years and the maintenance required during the succeeding two (2) year period in order to ensure that the applicable Mineral Terminal Project Company’s obligations are met. The Mineral Terminal Agreement will contain the form of instructions to be provided to the independent expert in connection with its audit.
Note on A15: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: However, that the State shall not be required to negotiate any such new agreement with the Mineral Terminal Project Company if a material default has occurred or is persisting within twenty four (24) months of the end of the term of the Mineral Terminal Agreement (the 25 years period).
Note on B15: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: However, that the State shall not be required to negotiate any such new agreement with the Mineral Terminal Project Company if a material default has occurred or is persisting within twenty four (24) months of the end of the term of the Mineral Terminal Agreement (the 25 years period).
Note on A16: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: Each of the State and the Mineral Terminal Project Company shall commence negotiating the terms of the Mineral Terminal Operations Agreement at least one (1) year prior to the expiry of the Mineral Terminal Agreement. For the term of the Mineral Terminal Operations Agreement, the Mineral Terminal Project Company shall have exclusive possession (but not title) of all Assets of the Mineral Terminal Project Company that transferred to the State following expiration of the Mineral Terminal Agreement, except as may be requested by the State in the exercise of its Reserved Rights. Under the Mineral Terminal Operations Agreement, the Mineral Terminal Project Company shall: - Be obliged to maintain and keep the Mineral Terminal in sound order and conduct all necessary works and repair any damage that occurs from use of the Mineral Terminal; - Be obliged to include in the tariff to be charged to a user other than with respect to the tariff being charged to the Mine Project Company and Congo Iron for the Initial Capacity and the Reserve Expansion Capacity, if being utilized, a capital component prescribed by the State, which amount shall be solely for the benefit of the State; and for the avoidance of doubt, the tariff will substantially reflect the tariff referred to in Article 4 of the Tariff Framework Agreement, excluding the State charge component referred to in Article 4.6 of the Tariff Framework but the State charge will be imposed on any usage above the Initial Capacity and Reserve Expansion Capacity; and - Be entitled to include in the tariff to be charged to a user, the fixed and variable operating costs associated with the Mineral Terminal Project Company providing a haulage service to the user, including the costs referred to in Article 13.5(b)(ii)(A) an equitable portion of any Sustaining Capital incurred by the Mineral Terminal Project Company together with a Fixed Profit Margin on each of the fixed and variable costs and on the Sustaining Capital. The Mineral Terminal Project Company shall provide to the State within three (3) months of the end of every two (2) year period from the effective date of the Mineral Terminal Operations Agreement, an independent report by an independent expert approved by the State on the maintenance carried out during the past two (2) year period and the maintenance required during the succeeding two (2) year period in order to ensure the Mineral Terminal Project Company’s obligations are being met.
Note on B16: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: Each of the State and the Mineral Terminal Project Company shall commence negotiating the terms of the Mineral Terminal Operations Agreement at least one (1) year prior to the expiry of the Mineral Terminal Agreement. For the term of the Mineral Terminal Operations Agreement, the Mineral Terminal Project Company shall have exclusive possession (but not title) of all Assets of the Mineral Terminal Project Company that transferred to the State following expiration of the Mineral Terminal Agreement, except as may be requested by the State in the exercise of its Reserved Rights. Under the Mineral Terminal Operations Agreement, the Mineral Terminal Project Company shall: - Be obliged to maintain and keep the Mineral Terminal in sound order and conduct all necessary works and repair any damage that occurs from use of the Mineral Terminal; - Be obliged to include in the tariff to be charged to a user other than with respect to the tariff being charged to the Mine Project Company and Congo Iron for the Initial Capacity and the Reserve Expansion Capacity, if being utilized, a capital component prescribed by the State, which amount shall be solely for the benefit of the State; and for the avoidance of doubt, the tariff will substantially reflect the tariff referred to in Article 4 of the Tariff Framework Agreement, excluding the State charge component referred to in Article 4.6 of the Tariff Framework but the State charge will be imposed on any usage above the Initial Capacity and Reserve Expansion Capacity; and - Be entitled to include in the tariff to be charged to a user, the fixed and variable operating costs associated with the Mineral Terminal Project Company providing a haulage service to the user, including the costs referred to in Article 13.5(b)(ii)(A) an equitable portion of any Sustaining Capital incurred by the Mineral Terminal Project Company together with a Fixed Profit Margin on each of the fixed and variable costs and on the Sustaining Capital. The Mineral Terminal Project Company shall provide to the State within three (3) months of the end of every two (2) year period from the effective date of the Mineral Terminal Operations Agreement, an independent report by an independent expert approved by the State on the maintenance carried out during the past two (2) year period and the maintenance required during the succeeding two (2) year period in order to ensure the Mineral Terminal Project Company’s obligations are being met.
Note on A17: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: In that case, the State must offer to the Mineral Terminal Project Company the right to match the offer from that Third Party and the State shall give the Mineral Terminal Project Company material terms of any such offer and the Mineral Terminal Project Company shall have thirty (30) Days from its receipt of those details in which to advise the State of its position on the matter; provided, however, that the State shall not be required to award such new agreement or extension to the Project Company if a material default has occurred or is persisting within twenty-four (24) months of the end of the term of the Mineral Terminal Operations Agreement or if the Beneficiation Operations have not commenced. The Mineral Terminal Project Company shall then, to the extent legally permissible, transfer, assign or grant a perpetual license (for no additional charge) to use the knowhow and business systems for running the Mineral Terminal to the State or whoever is to run the Mineral Terminal and the Mineral Terminal Project Company and Cam Iron shall cooperate and take all reasonably requested actions to facilitate the transfer of the right to operate the Mineral Terminal to a Third Party.
Note on B17: Road Map of the Mbalam Mining Convention - Exploitation Phase Mineral Terminal Operations Compliance: In that case, the State must offer to the Mineral Terminal Project Company the right to match the offer from that Third Party and the State shall give the Mineral Terminal Project Company material terms of any such offer and the Mineral Terminal Project Company shall have thirty (30) Days from its receipt of those details in which to advise the State of its position on the matter; provided, however, that the State shall not be required to award such new agreement or extension to the Project Company if a material default has occurred or is persisting within twenty-four (24) months of the end of the term of the Mineral Terminal Operations Agreement or if the Beneficiation Operations have not commenced. The Mineral Terminal Project Company shall then, to the extent legally permissible, transfer, assign or grant a perpetual license (for no additional charge) to use the knowhow and business systems for running the Mineral Terminal to the State or whoever is to run the Mineral Terminal and the Mineral Terminal Project Company and Cam Iron shall cooperate and take all reasonably requested actions to facilitate the transfer of the right to operate the Mineral Terminal to a Third Party.