## Feuil1
Conditions precedent to be satisfied | Required Actions or operation | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Provisoin of Independent Expert Report (Art. 12.1.1 (h)) | Provisoin of Independent Expert Report (Art. 12.1.1 (h)) | Within the 4th quarter of every two (2) year period commencing upon Project Commissionin | Railway Project Company |  |  | Not specified | Pending | Independent Report |  | Approved Maintainance Reports | Not specified
Approval of Independent Expert Report (Art. 12.1.1 (h)) | Approval of Independent Expert Report (Art. 12.1.1 (h)) | Within the 4th quarter of every two (2) year period commencing upon Project Commissionin | State | N/A | N/A | Not specified | Pending |  |  | Approved Maintainance Reports | Not specified
Review of terms of Railway Concession (Art. 12.1.1 (l)) | Review of terms of Railway Concession (Art. 12.1.1 (l)) | Every 5 years during the term of the Railway Agreement | Railway Project Company / State | TBD | TBD | Not specified | Pending | List of expectations that are not being met (if any) Take account of anticipated operating conditons | List of expectations that are not being met (if any) Take account of anticipated operating conditons | Reviewed terms of the Railway Concession | Not specified
Request for an autorisation to use Railway facilities for transport of the Sale Products, the Goods and the Nabeda Goods (Article 12.2.4) | Request for an autorisation to use Railway facilities for transport of the Sale Products, the Goods and the Nabeda Goods (Article 12.2.4) | On the Date of Entry into Force | Railway Project Company | TBD | TBD | Not specified | Pending | Autorisation to transport Sale Products, the Goods and the Nabeda Goods |  | Approval / Denial of autorisation
Railway Operatorship Transfer (Art. 12.2.2) | Railway Operatorship Transfer (Art. 12.2.2) | Prior to expiry of Railway Agreement | Railway Project Company / State | TBD | TBD | Not specified | Pending | Execise of Operation pre-emption right (Art. 12.2.2 (c)) |  | 10 Year extention of Railway operation rights / or transfer to a Third Party | Risk of transfer to a third party if pre-emption is not exercised
Note on G6: Elvis Ngwa Nde: Presumably MINIMIDT
Note on K6: Elvis Ngwa Nde: Approved maintenance carried out during 2 last years and maintenance required during 2 following years
Note on A8: Elvis Ngwa Nde: This is the opportunity to discuss in good faith opportunities to expand the Railway to provide services for additional mines or commodity producers, the goal of which is increasing revenue for the Parties, however, such review is not to result in any adverse change to either: (i) the operating conditions for the Railway Facilities; or (ii) the basis on which the tariff is being charged for the Initial Capacity.
Note on B8: Elvis Ngwa Nde: This is the opportunity to discuss in good faith opportunities to expand the Railway to provide services for additional mines or commodity producers, the goal of which is increasing revenue for the Parties, however, such review is not to result in any adverse change to either: (i) the operating conditions for the Railway Facilities; or (ii) the basis on which the tariff is being charged for the Initial Capacity.
Note on A9: Elvis Ngwa Nde: To the extent that such autorisation exists under the Legislation
Note on B9: Elvis Ngwa Nde: To the extent that such autorisation exists under the Legislation
Note on A10: Elvis Ngwa Nde: Operatorship upon expiration of 25 Years term of Railway Agreement The Railway Agreement that has the terms and conditions for the operation of the Railway Operations is entered into for a term of 25 years from the Date of Entry into Force. Upon the expiration of this term, the State and the Railway Project Company, to the extent they have reached agreement shall enter into a Railway Operations Agreement to extend the right of operation of the Railway to an additional 10 Years. (12.2.2 (a)). In this event, there shall be an automatic transfer of Assets of the Railway Project Company to the State and the Project Company shall only have possession rights over the assets. Otherwise, the State shall grant the operatorship of the Railway Facilities to a Third Party and in this case, there is an automatic transfer of the assets together with possession.
Note on B10: Elvis Ngwa Nde: Operatorship upon expiration of 25 Years term of Railway Agreement The Railway Agreement that has the terms and conditions for the operation of the Railway Operations is entered into for a term of 25 years from the Date of Entry into Force. Upon the expiration of this term, the State and the Railway Project Company, to the extent they have reached agreement shall enter into a Railway Operations Agreement to extend the right of operation of the Railway to an additional 10 Years. (12.2.2 (a)). In this event, there shall be an automatic transfer of Assets of the Railway Project Company to the State and the Project Company shall only have possession rights over the assets. Otherwise, the State shall grant the operatorship of the Railway Facilities to a Third Party and in this case, there is an automatic transfer of the assets together with possession.