## Feuil1
Conditions Precedent | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Up to date status of compliance | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Issue and maintain a Bank Guarantee in the sum of US$20 million known as the Mineral Terminal Project Company Guarantee (Article 29.2.1 (d)) | Issue and maintain a Bank Guarantee in the sum of US$20 million known as the Mineral Terminal Project Company Guarantee (Article 29.2.1 (d)) | 10 business day from Project Commissioning | Mine Project Company | TBD | TBD |  | Not yet started | Certificate issued by the bank which has issued the Bank Guarantee |  | Discharge of Cam Iron or the Project Company | Not yet started | State shall fully enforce all remedies available under applicable laws and regulatoins
Establishment of Rehab Escrow Account & Rehab Escrow Agreement(Article 29.2.1 (i)) | Establishment of Rehab Escrow Account & Rehab Escrow Agreement(Article 29.2.1 (i)) | Earlier on or otherwise Upon Project commissoining | Mine Project Company / Cam Iron | TBD | TBD |  | Not yet started | Certificate issued by bank where the account has been opened Draft Escro Account Agreement |  | Rehab Escro Account Rehab Escro AccountAgreement | Not yet started | State shall fully enforce all remedies available under applicable laws and regulatoins
USD 5.8 Millioin Monthly Contributions to Rehab Escrow Account as Rehabilitation Cost for Exploitation Area (Article 29.2.1 (i)) | USD 5.8 Millioin Monthly Contributions to Rehab Escrow Account as Rehabilitation Cost for Exploitation Area (Article 29.2.1 (i)) | At the end of the 10th month that follows the 31 of December of the year when the Project commissioning occurs | Mine Project Company / Cam Iron | TBD | TBD |  | Not yet started | Payment of USD 5.8 Millioin Monthly contribution |  | Bank deposit slip | Not yet started | State shall fully enforce all remedies available under applicable laws and regulatoins
Rehabilitation works in the event of renunciation of the Exploitation permit (Art 53.2.(a)) | Rehabilitation works in the event of renunciation of the Exploitation permit (Art 53.2.(a)) | As from the approval of the renunciation by the State | Mine Project Company | TBD | TBD |  | Not yet started | Renunciation works plan |  | Rehabilitated mining site | Not yet started | The renounced permit will only vest in the state upon completion of all the rehabilitation works thus state will fully enforce remedies under applicable law to ensure compliance
End of project / withdrawal or renounciation rehabilitation works (Art 54.2.8) | End of project / withdrawal or renounciation rehabilitation works (Art 54.2.8) | Upon expiry of Mining title / upon notification of renunciation or withdrawal | Project Companies | TBD | TBD |  | Not yet started | End of project / renunciation notice |  | Rehabilitated mining site | Not yet started | All property on mining site shall become State property
Note on A6: Road Map of the Mbalam Mining Convention : This Bank Guarantee is aimed at securing the obligations the Mineral Terminal Project Company under the Environmental and Social Assessment and Management Plan and the Mbalam Convention including inter alia, the rehabilitation of the Project Area occupied and generally, proper performance of its environmental obligations. This Bank Guarantee shall be maintained in place untill one year after the expiration of the Mining Permit.
Note on B6: Road Map of the Mbalam Mining Convention : This Bank Guarantee is aimed at securing the obligations the Mineral Terminal Project Company under the Environmental and Social Assessment and Management Plan and the Mbalam Convention including inter alia, the rehabilitation of the Project Area occupied and generally, proper performance of its environmental obligations. This Bank Guarantee shall be maintained in place untill one year after the expiration of the Mining Permit.
Note on C6: Road Map of the Mbalam Mining Convention Project Commission means whichever date occurs last between the following three dates: - the date Mine Commissioning occurs; - the date Railway Commissioning occurs or - the date Mineral terminal Commissioning occurs
Note on K6: Road Map of the Mbalam Mining Convention The aim is also to remedy damages caused to the environment, rehabilitation of the Project Area and the proper performance of environmental obligations
Note on C7: Road Map of the Mbalam Mining Convention : Due to the fact that contributions to the Rehad Escrow Account should must begin at the latest on December 31 of the year in which Project Commissioning occurs
Note on I7: Road Map of the Mbalam Mining Convention : This must be a bank with a physical presence in Cameroon that is under the supervision and regulation of the State’s national monetary authority (COBAC).
Note on A8: Road Map of the Mbalam Mining Convention : Contributions are required to be made in 10 Equal instalments of USD 5 800 000 and should total USD 58 Million
Note on B8: Road Map of the Mbalam Mining Convention : Contributions are required to be made in 10 Equal instalments of USD 5 800 000 and should total USD 58 Million
Note on A9: Road Map of the Mbalam Mining Convention : As from approval of the application for renunciation, the Mine Project Company shall cease the mining works and, unless the State requires otherwise, shall undertake rehabilitation works of the mining site concerned by the renunciation in accordance with the requirements of the Environmental and Social Assessment and Management Plan.
Note on B9: Road Map of the Mbalam Mining Convention : As from approval of the application for renunciation, the Mine Project Company shall cease the mining works and, unless the State requires otherwise, shall undertake rehabilitation works of the mining site concerned by the renunciation in accordance with the requirements of the Environmental and Social Assessment and Management Plan.
Note on A10: Road Map of the Mbalam Mining Convention : Under Article 88 of the Mining Code, where a mining permit , is abandoned, withdrawen or renounced, the holder shall remove any mining plant found on the land covered by the permit. Under the Mbalam convention however, the state can dispense the relevant project company of this obligation. In this case the State shall provide a written notice. All rehabilitation and remediation required by the applicable environmental Legislation and the Environmental and Social Assessment and Management Plan shall be performed regardless of whether the State elects to receive assets of the Project Companies pursuant to its rights under Articles 9.4, 10.15, 12.2.1 and 13.4 unless the State gives written notice to the respective Project Company that the Project Company is excused from such rehabilitation and remediation and rehabilitation and remediation in other areas will only be performed if expressly required by another Project Agreement.
Note on B10: Road Map of the Mbalam Mining Convention : Under Article 88 of the Mining Code, where a mining permit , is abandoned, withdrawen or renounced, the holder shall remove any mining plant found on the land covered by the permit. Under the Mbalam convention however, the state can dispense the relevant project company of this obligation. In this case the State shall provide a written notice. All rehabilitation and remediation required by the applicable environmental Legislation and the Environmental and Social Assessment and Management Plan shall be performed regardless of whether the State elects to receive assets of the Project Companies pursuant to its rights under Articles 9.4, 10.15, 12.2.1 and 13.4 unless the State gives written notice to the respective Project Company that the Project Company is excused from such rehabilitation and remediation and rehabilitation and remediation in other areas will only be performed if expressly required by another Project Agreement.