## Feuil1
Monitoring Items/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | CamIron | State
| Draft an action plan on the construction of the new facility |  | Cam Iron / Project Companies / Third Party |  |  |  |  | New buliding consstruction specifications |  | Building the new Project Facility | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Draft an environmental and social assessment and management plan specific to the requested facility and to the site plan |  |  |  |  | Ministry of Environment |  | Environmental Charter and relevant texts |  |  | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Prepare a Project Lease Request | [9 empty] | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Sent the Request for construction of a new facility to the State along with the action plan, the environmental and social assessment and management plan, and with the Project Lease request | Immediately gy the time all documents are ready |  |  |  | Ministry of Mines |  |  |  |  | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Obtain a response of the State after the transmission of the request for the construction of a new facility | 180 Days after the request submission | State |  |  | Ministry of Mines |  |  |  |  | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Take the following actions after reception of the State comments: | 180 Days after reception of the State comments | Cam Iron / Project Companies / Third Party | [7 empty] | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| In case there is no dismissal of the request, the State shall: |  | State |  |  | Ministry of Mines |  |  |  |  | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Obtain the Additional Facility Autorisation from the State or any necessary document from the State notably the Project Lease and the soecific Project Agreement | 180 Days following the date of receipt by the State of the revised and finalized file containing the Additional Facility Request | Cam Iron / Project Companies / Third Party |  |  | Ministry of Mines |  | Additionnal Facility Authorization for the contruction of the new building |  |  | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Start the construction of the said new Project Facility |  | Cam Iron / Project Companies / Third Party | [7 empty] | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
| Specific provisions for the Beneficiation Power Station | [9 empty] | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Existing Facilities | Instead of constructing additional facilities, the Parties may agree on the use of all existing facilities |  | State / relevant Project Companies / relevant Third Parties | [6 empty] | Use of the existing facilities for Project needs | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Existing Facilities | Establishment of a hydrocarbon facility at the Mineral Terminal, |  | State / Project Companies (mainly the Mineral Terminal Project Company) | [6 empty] | Establishment of a hydrocarbon facility at the Mineral Terminal | Payment of Penalties for Delay Breach of Events provided in article 50.3 and depending on the nature of the Delay Breach
Note on E4: Road Map of the Mbalam Mining Convention This refers to the specific individual responsible for compliance within the “Party accountable for compliance”.
Note on B6: Road Map of the Mbalam Mining Convention - Other Project Facilities compliance : The action to be drafted shall present: - The extent to which the building of the new facility satisfies a need of the Project that cannot be met by existing Project Facilities; - The practical arrangement with respect to the base area, layout, design materials and time table for commencement, development, construction, layout and completion of said new facility, determined on the basis of studies conducted by a Subsidiary, Contractor or Subcontractor; as well as the impact on the Project in terms of deadlines, costs and profits; - The site plan of the requested facility and in particular whether it can be connected to the Exploitation Area, the Railway Area or the Mineral Terminal Area and be the subject of an amendment to the relevant Specific Agreement; or, on the contrary, whether it requires the delivery of a Project Lease or the conclusion of an Additional Specific Agreement; - The identity of the Project Company in charge of building the requested facility and of the Contractor(s) and Subcontractor(s) contemplated by the tender or pre-qualified as the case may be for the design, construction, operation and maintenance of the requested facility; - The information as to whether the operation of the requested facility (being a facility that does not form part of any Expansion Capacity) it allows for the generation of additional income.
Note on B10: Road Map of the Mbalam Mining Convention - Other Project Facilities : After reception of the request notice, the State shall either provide its comments and recommendations to the Project Company that made the Additional Facility Request or dismiss the Additional Facility Request, subject to such dismissal being justified by one or more of the following reasons: - The needs justifying the building of the requested additional facility can be met by an existing Project Facility or another pre-existing facility; - Failure to comply with the Legislation (with respect to the provisions contained in the action plan); - Material violation of any Project Agreements by a Project Company, Contractor or Subcontractor over the trailing twenty-four (24) month period, or the occurrence of five (5) or more breaches over the same such period which, in the aggregate, have a Material Adverse Effect; - If the said request does not materially comply with the practices generally accepted for high-scale international iron ore exploitation projects; or - The request does not comply with the State’s material interests and standards with respect to environmental or social policies or other reasonable considerations.
Note on B11: Road Map of the Mbalam Mining Convention - Other Project Facilities : - Supplement the Additional Facility Request to take into account the State's comments and recommendations provided that they are justified from a technical and/or economical standpoint under the Legislation; - Prepare a draft Project Lease, a draft Additional Specific Agreement or a draft amendment to the applicable Specific Agreement; - Provide all such documentation to the State, together with any other information as may be reasonably required by the State.
Note on B12: Road Map of the Mbalam Mining Convention - Other Project Facilities : The State shall the authorise the building of the requested additional facility by : - Entering, with the Project Company that made the Additional Facility Request, into a Project Lease or an Additional Specific Agreement, or, as the case may be, an amendment to the applicable Specific Agreement; - Considering in good faith and not unreasonably withholding its consent to any applications in compliance with the Legislation for any Project Company of any other necessary permit, authorisation or administrative document, according to the Legislation, to validly authorise the Project Company that made the Additional Facility Request to build the requested Additional Facility.
Note on B13: Road Map of the Mbalam Mining Convention : Where the building of any additional facility has been the subject of a Project Lease, an Additional Specific Agreement or an amendment to the applicable Specific Agreement shall be drafted, this additional facility shall become a Project Facility and the legal regime applicable to the Assets comprising said additional facility, the maintenance and repair obligations and, as the case may be, Third Party access, shall be treated in accordance with the provisions of this Convention applicable to the Project Facilities, as supplemented, as the case may be, in the Project Lease, the Additional Specific Agreement or in the amendment to the existing Specific Agreement
Note on B15: Road Map of the Mbalam Mining Convention - Other Project Facilities : If the Additional Facility Authorisation could not be delivered for the Beneficiation Power Station due to a refusal of the State and the State considers, at its sole discretion, that the building of the said facility is of particular significance for the needs of the local or national economy, the State may: - Freely organise a public offering, in compliance with the World Bank standards, for the financing, construction, maintenance and operation of the Beneficiation Power Station on the basis of all the rights equivalent to those covered by an Additional Facility Authorisation with a view to building said facility and, provided that the service offering issued for the building of said facility generally is substantially similar in substance to the service offering that would have been issued for the facility initially requested by a Project Company; - Subject to the successful bidder agreeing to supply the said services by the BF Construction Deadline (or such earlier date as mutually agreed by the State and Cam Iron) and paying damages commensurate with estimated losses to the Mine Project Company if it fails to provide the timely supply of the power, compel the Mine Project Company requiring the power for the purposes of the Beneficiation Facility to enter into any agreement with the successful bidder in the context of the aforementioned public offering, under conditions better than (when accessed by the Mine Project Company) or identical to those set forth in the Additional Facility Request.
Note on B16: Road Map of the Mbalam Mining Convention : Where such infrastructure is operated by a public entity (or a semi-public entity Controlled by a Governmental Entity), the State undertakes to reasonably facilitate the conclusion of the necessary agreements between the operator and the relevant Project Company. In case the Parties reach to an agreement with respect to the use of an existing facility, the relevant Project Company may, if it considers it appropriate, upgrade and maintain and repair any of the existing facilities which it uses and for these purposes. The relevant Project Companies may become the exclusive manager or operator under conditions mutually agreed between the Parties.
Note on B17: Road Map of the Mbalam Mining Convention - Other Project Facilities : Such hydrocarbon facility will be suitable for the import, storage and distribution of hydrocarbon products. The Mineral Terminal Project Company will develop or engage a Contractor to develop a hydrocarbon facility to meet the requirements of the Project Operations and as part of its commitment to the State, the Project Companies agree to work with the State to see how the hydrocarbon facility and the Mineral Terminal can be designed and developed to provide a capacity beyond the needs of the Project so as to support the hydrocarbon demand of the region around the Mineral Terminal Facility and without limitation the Mineral Terminal Project Company will: - Assist in the assessment of the regional demand for hydrocarbon products; - Control and Ensure the design a hydrocarbon facility which is sufficient to meet the requirements of both the Project and more broadly, the region; - Work with the State to determine how best to integrate the requirements of the Project with the forecast requirements of the region so as to use the Project’s hydrocarbon demand as the catalyst for the development of a hydrocarbon facility which can support the requirements of the region; - Work with the State to develop a funding plan for the proposed hydrocarbon facility; - Use its proposed hydrocarbon product buying power to support or attract the involvement of a fuel supply and distributor to assist in the development of the hydrocarbon facility. However, the development and operation of such a hydrocarbon facility is not intended to adversely impact on the: - Economics of the Project and in particular the tax and excise concessions on hydrocarbon products; - Occupation health and safety of the Mineral Terminal Project Company’s operations; and - Operating philosophy of the Mineral Terminal Project Company.