## Feuil1
Monitoring Items/ Category (1) | Required action or operation or process (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Implimentation of Fund Committee | Implimentation of Fund Committee | There is no date for the setting-up of the Committee. However, the first composition shall be agreed to by the Parties prior to the Date of Entry into Force, notably before May 2014 | Project Companies | Cam Iron | Not specified | Cam Iron and State | To be done | See the Table relating to Commitee | See the Table relating to Committee | Not Speficfied3 | Not Speficfied1 | Not Speficfied
Creation of Joint committee | Creation of Joint committee | Thirty (30) Days following the Date of Entry into Force, the committee described in this Article 30.5 | State, Cam Iron | Cam Iron |  |  | To be done | At least forty-five (45) Days prior to the beginning of each Calendar Year, Cam Iron shall, in consultation with the State, send to the State a proposal for funding the Joint Committee for the following Calendar Year, on the basis of the estimated operational costs, including the daily compensation of the State Representatives | The State, within forty-five (45) Days following receipt of the aforementioned proposal, shall: accept this proposal; or provide its comments and recommendations to Cam Iron. In case of the State’s failure to respond within the aforementioned period, the State shall be deemed to have accepted the proposal | Not Speficfied6 | Not Speficfied5 | Not Speficfied7