## Feuil1
Monitoring Issue/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance (State) | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | CamIron/Sundance/Project Companies | State
Beneficiation Facilities | Guarantee and surety for the construction of the Beneficiation Facility | 120 months following the Date of the First Commercial Shipping | Cam Iron |  |  |  | Not yet done | Guarantee and surety for the construction of the Beneficiation Facility |  | The construction of the Beneficiation Facility will enable Beneficiation of the Low Grade Ore in order to produce Beneficiated Ore
Beneficiation Facilities | Notification of the State of the actual date of commencement of construction of the Beneficiation Facility within seven days | 7 days from the date of construction | Mine Project Company |  |  |  | Not yet done | Notice to the State |  | Construction of the Beneficiation Facility
Beneficiation Facilities | Non-termination and non-suspension of the construction of the Beneficiation Facility for a period of sixty days or more
Beneficiation Facilities | Prompt notification to the State of Force Majeure, Legitimate Cause or Economic Hardship and exercise of all reasonable efforts to overcome the event. Immediate notification once the event is overcome | Immediately the event occurs | Mine Project Company |  |  |  | Not yet done | Prompt notification once Force Majeure occurs |  | Overcoming the event
Beneficiation Facilities | Issuance of a Finding of Compliance at the normal or early expiration of the BF Construction Deadline | At the normal or expiration of the BF Construction Deadline | Mine Project Company should request issuance of the Finding of Compliance |  |  | State of Cameroon | Not yet done | Request for the Finding of Compliance |  | Recognition by the State that the Beneficiation Facility meets the Specifications and applicable Legislation relating to it.
Beneficiation Facilities | Using reasonable endeavours to facilitate the conclusion of the financing of the Beneficiation Facility | Prior to the construction of the Beneficiation Facility | Project Companies |  |  |  | Not yet done | Carryout financing by using project financing and minimising equity financing | Not withhold consent in case undistributed profits are contemplated being used for the financing | Facilitiating the financing of the Beneficiation facility by minimising the use of equity financing
Beneficiation Facilities | Undertaking to carry out the commissioning of the Beneficiation Facility on the basis of at least the Initial Beneficiation Production | At most 365 days after the BF Commissioning Deadline | Mine Project Comapny |  |  |  | Not yet done | Undertaking to carry out the commissioning of the Beneficiation Facility within 365 Days after the Beneficiation Facility Commissioning Deadline |  | Ensure that the Beneficiation Facility is built within a given time frame.
Beneficiation Facilities | Entry into a Beneficiation Escrow Agreement |  | Mine Project Company, Cam Iron and the State |  |  |  | Not yet done | Concluding a Beneficiation Escrow Agreement and making contributions into the Beneficiation Escrow Account |  | Creation of a Beneficiation Escrow Account with an independent escrow agent in a neutral country wherein the Mine Project Company shall contribute 25% of total funds required to finance the Beneficiation Facility
Beneficiation Facilities | Undertaking to ensure that the Beneficiation Facility shall be initially constructed and commissioned to achieve at least the Initial Beneficiation Production Capacity |  | Cam Iron |  |  |  | Not yet done | Undertaking that the Beneficiation Facility is constructed and commissioned |  | To achieve at least Initial Beneficiation Production Capacity or the Interim Beneficiation Production Capacity
Note on E4: Elvis Ngwa Nde: Road Map of the Mbalam Mining Convention - Conditions Precedent: This refers to the specific individual responsible for compliance within the “Party accountable for compliance”.
Note on C6: Road Map of the Mbalam Mining Convention Date of the First Commercial Shipping means the date on which shall occur the first lodaing on a vessel of at least 60,000 tonnes of Blended Ore (excluding shipping intended for one or more steel plants aiming at testing the iron ore), made effecive by the issuance of the bill of loading relative to this first commercial shipping).
Note on B9: Enga Kameni: Force Majeure can be: (i) Ordinary Force Majeure (which is any circumstance external for the affected Party, indepndent of its will reasonable unforseeable that prevents the party invoking it from performing its statutory or regulatory obligations or (ii) Political Force Majeure which can be an act of war, act of rebellion or any closing by the State of a border terminal through which iron ore is transported into the territory of the State.
Note on B10: Enga Kameni: Finding of Compliance means finding of compliance by the State of any Project Facility according to the Specifications and applicable Legislation relating thereto and the delivery by the State to the relevant Project Company of t hat finding of compliance It should be pointed out that if the State makes any observations, the Mine Project Company will have a period of 180days to complete works aim at addressing the observation of the State
Note on B13: Enga Kameni: If the Mine project Company does not comply with its obligations regarding the construction and commissioning of the Beneficiation Facility, the funds in the escrow account will be made available to the Mine Project Company for purpose to finance the Beneficiation Facility pursuant to any structure chosen by the State. Such fund will remain in escrow for 10 years from the date it is determined that the Mine project Company will not comply with its obligations to construct the Beneficiation Facility to be available to the State for deployment for the purpose of financing the Beneficiation Facility. Any excess left will be distibuted to the shareholders of the Mine Project company. If the State through the Mine Project Company has not arranged for the utilisation of such funds for the construction of the Beneficiation Facility by the 1O anniversary, then such funds shall be distributed to the Shareholders of the Mine Project Company.
Note on K14: Enga Kameni: Interim Beneficiation Production Capacity means a production capacity of no less than 22 million tonnes of Beneficiated Ore in a Calender Year commencing on the date that is 12 months following the BF Commissioning where the Beneficiation Facility is built to that capacity