## Feuil1
Monitoring Items/ Category (1) | Required action or operation or process (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Design Capacity of the Mineral Terminal (article 11.1.) | Prepare a draft of the Mineral Terminal Concession to be granted to the Mineral Terminal Project Company in accordance with article 13.1(c) of the Convention. | Not specified | State, Cam Iron and Contractors and subcontractor | Cam Iron | Not specified | To be done | All the Parties |  | The State hereby agrees to hereinafter organize the Special Development Fund. With respect to the long term funding of the development of the area impacted by the Project, the State intends to allocate thirty percent (30%) of its portion of the base charge tariff paid by Expansion Capacity users and 30% of the lease payments it receives in connection with the Mineral Terminal Site and Railway Site to fund the Special Development Fund | Not Speficfied | Not speciefied | Not specified
Construction of the Dual Track Design (article 11.3.) Election by the State in its sole discretion and by the Date of Entry into Force, of the funding of the costs required to build out the foundation for a dual track design. | Grant of the Mineral Terminal Concession to the Mineral Terminal Project Company (article 13.1(c). | Date of Entry into Force - May 2014 | Cam Iron, Contractors and subcontractor | Cam Iron the Project Company | Not specified | To be done | All the Parties |  |  | Not Speficfied | Not speciefied | Not specified
Mineral Terminal Operations (article 13.1.c) | Start of the Mineral Terminal Operations | By the date of granting of the Mineral Terminal Concession / Date when the Mineral Terminal Company becomes Party to the Convention (at the time of the incorporation at the Trade Register - article 6.4.) | Project Companies | Cam Iron | Not specified | To be done | Cam Iron and State | See the Table relating to Commitee | See the Table relating to Committee | Not Speficfied | Not speciefied | Not specified
Mineral Terminal Agreement (article 13.1.d) | Review of the terms of the Mineral Terminal Concession by the State and the Mineral Terminal Project Company (article 13.1(l) of the Convention | Every five (5) years, during the term of the Mineral Terminal Agreement | State, Cam Iron | Cam Iron |  | To be done |  |  |  | Not Speficfied | Not speciefied | Not specified
Complete the Mineral Terminal Project Commissioning (articles 13.1(i) and (j)) |  |  | Cam Iron, and the Project Companies | Cam Iron and the Project Compagnies | See the date fo compliance | To be done | Cam Iron and the Project companies |  |  | Not Speficfied |  | it's important to clarify who will finance the special development fund created by Cam Iron
Note on B6: Ernst & Young: Mineral Terminal Concession is defined under article 1 of the Convention as "a concession granted by the appropriate authority and the terms of which are set out in the Mineral Terminal Agreement". The right for the Mineral Terminal Project Company to undertake Mineral Terminal Operations including the design, construction, operation and maintenance of the Mineral Terminal Facilities, is subject to the grant to the Mineral Terminal Project Company of the Mineral Terminal Concession. In fact, article 13.1(c) states that the Mineral Terminal Project Company shall have the right to carrry out the Mineral Terminal Operations as of the later of the date when: - the Mineral Terminal Project Company becomes Party to the Convention by delivering to the State the Accession Notice in accordance with article 6.4 of the Convention. The deliverance of such executed Accession Notice is a Condition Precedent to the entry into force of the Convention and should therefore occur before the Date of Entry into Force (that is to say during the pre-contractual phase as defined in this Roadmap); - the Mineral Terminal Concession is granted to the Mineral Terminal Project Company.
Note on C8: Ernst & Young: The Mineral Terminal Operations can start as from this date but this is not a deadline or time-limit to start the said operations but merely the date when the Mineral Terminal Project Company shall have the right to start Mineral Terminal Operations.
Note on A9: Road Map of the Mbalam Mining Convention - Construction Phase:: The Mineral Terminal Agreement is to be drawn up as a BOOT model and shall, along with the Mineral Terminal Project Company Shareholders’ Agreement, provide and set the framework of the conditions for the funding and conduct, by the Mineral Terminal Project Company, of the Mineral Terminal Operations within the Mineral Terminal Area. The Mineral Terminal Agreement will contain the form of instructions to be provided to the independent expert in connection with its audit of the Mineral Terminal Project Company's obligations. The term of the Mineral Terminal Agreement shall be for twenty five (25) years from the Date of Entry into Force. (article 13.1.k)
Note on B9: Road Map of the Mbalam Mining Convention - Construction Phase: This is to ensure the expectations of both Parties are being met and to otherwise take account of anticipated operating conditions for the next succeeding five (5) year period and to discuss, in good faith, opportunities to expand the Mineral Terminal to provide services for additional mines, the goal of which is increasing revenue for the Parties.
Note on C9: Ernst & Young: This means that the first review may occur before the Mineral Terminal Commissioning which may occur 6 years from the Date of Entry into Force.