## Feuil1
Monitoring Items / Categories | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party action accountable for compliance | Person in charge | Due date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Construction and Operation of the Expansion Capacity | Cooperate and agree on a plan for the construction of the Expansion Capacity | By the time an Applicant is selected by the State under Feasibility Expert proposal |  | Selected Applicant / Expansion Project Companies | [5 empty] | Plan for the construction of the Expansion Capacity | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Construction and Operation of the Expansion Capacity | Start the effective construction of the Expansion Capacity | By the time an Applicant is selected by the State under Feasibility Expert proposal |  | Selected Applicant / Expansion Project Companies (in case they have negotiated) | [5 empty] | Expansion Capacity | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Construction and Operation of the Expansion Capacity | Solve all disputes arising between the Expansion Project Companies and applicant pursuant to the procedures set forth in the Technical Dispute Resolution Agreement | Throughout the Expansion Stage | Expansion Project Companies / Selected Applicant | Selected Applicant / Expansion Project Companies |  |  |  | Technical Dispute Agreement |  |  | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Construction and Operation of the Expansion Capacity | Enter into an agreement agreeing to be bound by the procedures set forth in the Technical Dispute Resolution Agreement | Selected Applicant |  | Selected Applicant / Expansion Project Companies |  |  |  | Technical Dispute Agreement |  | Issuance of an Expansion Directive | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Note on B6: Road Map of the Mbalam Mining Convention - Expansion Stage Construction and Operation of the Expansion Capacity : The plan shall relate to the design, construction and commissioning (consistent with the Services Application and Services Feasibility Study) that minimizes, to the extent reasonably possible, the disruption the construction causes to the existing users and addresses any detailed specifications for construction and commissioning not specified in the Services Application and Services Feasibility Study that are necessary to integrate the Expansion Project and existing assets.