## Feuil1
Monitoring Items/ Category (1) | Required action or operation or process (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Design Capacity of the Mineral Terminal (article 11.1.) | Prepare a draft of the Mineral Terminal Concession to be granted to the Mineral Terminal Project Company in accordance with article 13.1(c) of the Convention. | Not specified | The State | General Manager / Operations / Legal |  | The Port Authority if the Mineral Terminal Area is located within a perimter regulated by the Port Authority | TBD | Mineral Terminal Agreement (article 1 relating to the defintion of Mineral Terminal Concession) | Mineral Terminal Agreement (article 1 relating to the defintion of Mineral Terminal Concession) | Draft the Mineral Terminal Concession
Construction of the Dual Track Design (article 11.3.) Election by the State in its sole discretion and by the Date of Entry into Force, of the funding of the costs required to build out the foundation for a dual track design. | Grant of the Mineral Terminal Concession to the Mineral Terminal Project Company (article 13.1(c). | Date of Entry into Force - May 2014 | State / but also Cam Iron (Sundance) | Sundance CFO and COO |  | Ministry of Transports | TBD |  | Reception by the State of the updated Feasibility Study / Specifications of the Dual Track Design | Ensure that criteria for Dual Track Design construction are met and meet the conditions of funding such construction
Mineral Terminal Operations (article 13.1.c) | Start of the Mineral Terminal Operations | By the date of granting of the Mineral Terminal Concession / Date when the Mineral Terminal Company becomes Party to the Convention (at the time of the incorporation at the Trade Register - article 6.4.) | Cam Iron / Project Companies | General Manager / Operations |  |  | TBD | Mineral Terminal Specifications provided by the State |  | Start the Mineral Terminal Operations
Mineral Terminal Agreement (article 13.1.d) | Review of the terms of the Mineral Terminal Concession by the State and the Mineral Terminal Project Company (article 13.1(l) of the Convention | Every five (5) years, during the term of the Mineral Terminal Agreement | State / Mineral Terminal Project Company | General Manager / Legal / Finance / Operations |  | Ministry of Mines | TBD |  |  | Ensure that all obligations of the Parties deriving from the Mineral Terminal Agreement were met.
Complete the Mineral Terminal Project Commissioning (articles 13.1(i) and (j)) | Complete the Mineral Terminal Project Commissioning (articles 13.1(i) and (j)) | Within 6 years following the Date of Entry into Force, which shall occur at the latest 18 months of the Signature Date (article 3.6 (a)) of the Convention) | Mineral Terminal Project Company/State |  |  | Port Authority | TDB | Mineral Terminal Specifications | Mineral Terminal Specifications | Finding of Compliance | A penalty for Delay Breacn Event of 70 000$ US per day of the delay if the delay Railway Commissioning result in a delay in the Project Commissioning Article 50.3 (a)(i) of the Convention
Note on A6: Road Map of the Mbalam Mining Convention - Construction Phase: The Mineral Terminal shall be designed in a manner based on the assumptions and principles set forth in the Railway Agreement and Mineral Terminal Agreement respectively suited to eventually handle the Design Capacity. Such Design Capacity shall be done without materially adversely impacting: - The Initial Capacity and Expansion Capacity for a total capacity equal to the Design Capacity; or - The technical aspects of the Railway haulage services and Mineral Terminal services being provided to any party up to the Design Capacity.
Note on B6: Ernst & Young: Mineral Terminal Concession is defined under article 1 of the Convention as "a concession granted by the appropriate authority and the terms of which are set out in the Mineral Terminal Agreement". The right for the Mineral Terminal Project Company to undertake Mineral Terminal Operations including the design, construction, operation and maintenance of the Mineral Terminal Facilities, is subject to the grant to the Mineral Terminal Project Company of the Mineral Terminal Concession. In fact, article 13.1(c) states that the Mineral Terminal Project Company shall have the right to carrry out the Mineral Terminal Operations as of the later of the date when: - the Mineral Terminal Project Company becomes Party to the Convention by delivering to the State the Accession Notice in accordance with article 6.4 of the Convention. The deliverance of such executed Accession Notice is a Condition Precedent to the entry into force of the Convention and should therefore occur before the Date of Entry into Force (that is to say during the pre-contractual phase as defined in this Roadmap); - the Mineral Terminal Concession is granted to the Mineral Terminal Project Company.
Note on G6: Ernst & Young: In principle, such concessions are granted by ports authorities specially when the terminal to be constructed and operated is within a port. For example, the Kribi Port Authority is in charge of granting concession for industrial activities within the Port of Kribi, including mineral activities undertaken therein, in accordance with decree n°99/132 of 15 June 1999 relating to the organization and operation of the Port of Kribi
Note on C8: Ernst & Young: The Mineral Terminal Operations can start as from this date but this is not a deadline or time-limit to start the said operations but merely the date when the Mineral Terminal Project Company shall have the right to start Mineral Terminal Operations.
Note on A9: Road Map of the Mbalam Mining Convention - Construction Phase:: The Mineral Terminal Agreement is to be drawn up as a BOOT model and shall, along with the Mineral Terminal Project Company Shareholders’ Agreement, provide and set the framework of the conditions for the funding and conduct, by the Mineral Terminal Project Company, of the Mineral Terminal Operations within the Mineral Terminal Area. The Mineral Terminal Agreement will contain the form of instructions to be provided to the independent expert in connection with its audit of the Mineral Terminal Project Company's obligations. The term of the Mineral Terminal Agreement shall be for twenty five (25) years from the Date of Entry into Force. (article 13.1.k)
Note on B9: Road Map of the Mbalam Mining Convention - Construction Phase: This is to ensure the expectations of both Parties are being met and to otherwise take account of anticipated operating conditions for the next succeeding five (5) year period and to discuss, in good faith, opportunities to expand the Mineral Terminal to provide services for additional mines, the goal of which is increasing revenue for the Parties.
Note on C9: Ernst & Young: This means that the first review may occur before the Mineral Terminal Commissioning which may occur 6 years from the Date of Entry into Force.
Note on C10: Ernst & Young: The deadline for the Mineral Terminal Commissioning is not provided by the Convention but stipulates that the Project Commissioning shall within 6 years following the Date of Entry into Force or such later date as otherwise agreed. Which means that Mineral Terminal Comissioning shall occur before or on the date of the Project Commissioning. Please note that as per article 13.1.(j) of the Convention, the issuance by the State to the Mineral Terminal Project Company of a Finding of Compliance will constitute the Mineral Terminal Commissioning. In this respect the afore-mentioned article provides that the State may raise reservations that the Mineral Terminal has not been constructed in accordance with the Mineral Terminal Specifications. In that case, such reservations must be resolve prior to the Mineral Terminal Commissioning. The Mineral Terminal Project Company will have a period of 180 days to do the works such as to allow the removal of such reservation. An additional delay of 90 days can be added to the 180 days to the extent that the Mineral Terminal Project Company is diligently working to remove such reservations and can demontrates in good faith that the reservations cannot be resolved within the 180 day.