## Feuil1
Monitoring Items/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Mining Facilities | Transfer of the Exploitation Permit from Cam Iron to the Mine Project Company (Art 8.1 (a) (i) and 9.1 (a)) for the Mine Project Company to be entitled to undertake the construction of the Mining Facilities), and application for the approval of the transfer. | The Date of Entry Into Force (see our comment for legal basis) | CAM IRON SA |  |  |  | TBD | The Exploitation Permit The draft assignment contract The draft request for the approval of the assignment |  | The assignment contract The application for the approval of the assignment | Impossibility to Conduct Mining Operations
| Submission of an application for the approval of the transfer to the Ministry in charrge of Mining (article 20 of the Mining Code) | The Date of Entry Into Force (see our comment for legal basis) | CAM IRON SA |  |  |  | TBD | The transfer contract |  | Application the approval of the transfer | Impossibility to Conduct Mining Operations
| Approval of the assignment by the Ministry in charge of mining and publication of the relevant arrété (Art 8.1(a)(i) of the Convention and section 20 of the Mining Code) | 45 days of the Date of Entry into Force | The State |  |  | The Minister in charge of mining | TBD |  | The request for the approval of the assignment | Arrété approving the assignment The publication of the arrêté to the Official Gazette | The Exploitation Permit will not be transferred to the Mine Project Company and the Mine Project Company will not be entitled to undertake Mining Operations
| "Grant" of Exploitation Lease to the Mine Project Company | 45 days of the Date of Entry into Force | The State/The Mine Project Company |  |  | The Minister in Charge of Mines with respect to the issuance of the order authorizing the execution of the Exploitation Lease The senior divisional officer of the division where the land is situated, for the execution of the Exploitation Lease with the General Manager of the Mine Project Company | TBD | The Project Lease Request The request for the registration of the Exploitation Lease to the land register |  | The arrêté authorizing the execution of the Exploitation Lease The Exploitation Lease The certificate of registration of the lease to the land register | The Mine Project Company will not have the right to access and occupy the land located within the Exploitation Area
| Prepare or approve the waste management procedure referred to in article 29.4 (a) of the Convention | Prior to
| Start the construction of the Mining Facilities | at the latest to 2 years of the date of issuance of the Exploitation Permit | The Mine Project Company/The State | The COO |  | N/A | TBD | The development and exploitation plan of the deposit | N/A | Finding of Compliance | Per diem delay penalty amounting to 5000 US$ (adjusted by the Inflation Adjustment) per Day (article 50.3ii)
| Report on details of development works | At the latest on the 90th day after the conclusion of each Calender Year after the Date of Entry into Force has occured | The Mine Project Company |  |  | N/A | TBD | Details of development work | N/A | Development work report | Per diem delay penalty amounting to 5000 US$ (adjusted by the Inflation Adjustment) per Day (article 50.3ii)
| Report on any information requirement specifically for mining companies listed on the Austrialian Securities Exchange | At the latest on the 90th day after the conclusion of each Calender Year after the Date of Entry into Force has occured |  |  |  | N/A | TBD | Any on any information specifically required by Austrialian Securities Exchange | N/A | Report on information required by Austrialian Securities Exchange | Per diem delay penalty amounting to 5000 US$ (adjusted by the Inflation Adjustment) per Day (article 50.3ii)
| Administrative and technical supervision, tax, customs and other audits (article 30.2 of the Convention) | The frequency of the audits contemplated under article 30.2 of the Convention shall be detailed by a mutually agreeable manual describing the procedure applicable to all Project Areas, which frequency shall not exceed: i) 1 time per Calendar Year for tax audits; ii) 2 times per Calendar Year for customs audits iii) 1 time per quater Year for any other audit | The State |  |  | Auditors (mining officials, authorized and qualified representative of the tax administration, customs agents appointed for that purpose, other representatives of the State and consultants authorized by the State |  | Manual describing the procedure applicable to all Project Areas, the Convention, the Legislation, Operating Standards, Good International Industry Practice | Manual describing the procedure applicable to all Project Areas, the Convention, the Legislation, Operating Standards, Good International Industry Practice | Audit report
| Mine Commissioning | Six (6) years following the Date of Entry into Force or such later date as otherwise agreed. | CAM IRON SA The Mine Project Company | The COO |  | The State | Not started | Provision of the Mining Convention Provision of the Mine Project Agreement |  |  | Per diem delay penalty amounting to 7000 US$ (adjusted by the Inflation Adjustment) per Day (article 50.3ii)
Note on A6: Road Map of the Mbalam Mining Convention Under the Construction Phase, Mining Facilities of the Project Comprises of all facilities constructed or operated within the Exploitation Area and which are used for mining, crushing, screening and processing in view of producing the Mbalam Ore. The responsibility to carry out the construction lies with the Mines Project Company which refers to the Project Company that should be established by Cam Iron to accede to the Exploitation Permit and shall be in charge of Mining Operations. On this grounds, priority for compliance will consist in ensuring the transfer of the Exploitation Permit to the Mines Project company given that it is the holding of the Exploitation Permit that entitles the Mines Project Company to engage in Mining Operations (the design, construction, operation and maintenance of the Mining Facilities, including dismantling and rehabilitation of the said Mining Facilities) The right to engage into such construction on the exploitation area is however subject to procurring the Exploitation Lease. This is the Project Lease which provides entitlement to the land necessary for the mining of the Mbalam Ore. It should be noted that unlike the case of construction of Other Facilities, where the Mine Project Company is required to file a request to the State identifying the Contractors or Subcontractors contemplated for the works, for the construction of the Mining Facilities, the Mine Project Company is not required to provide a request nor identify the Contractors and/or Subcontractors Upon obtaining the lease
Note on B6: Road Map of the Mbalam Mining Convention To recall, Mining Facilities shall be constructed by the Mine Project Company, which is the company established by Cam Iron in charge of Mining Operations, it being specified that Mining Operations include the design and the construction of Mining Facilities as well as the operation and maintenance thereof. Pursuant to article 9.1 (a) of the Convention, the Mine Project Company shall have the right to carry out Mining Operations, thus to start the construction of the Mining Facilities as of the later of the date when: - the Mine Project Company become a Party to the Convention by delivering to the Sate the Accession Notice contemplated under article 6.4 of the Convention; this event is stipulated as a Condition Precedent to the entry into force of the Convention and is deemed to have already occrured once we get into the Construction Phase; - the Exploitation Permit is transferred from Cam Iron to the Mine Project Company. The transfer of the Exploitation Permit to the Mine Project Company is therefore necessary for it to be granted the rights to undertake the design and construction of the Mining Facilities
Note on C6: Road Map of the Mbalam Mining Convention We remind that the Date of the Entry into Force is the date on which all the Conditions Precedent shall be satisfied or waived. This day shall occur no later than 18 months after the Signature Date, that is at the latest on 29 May 2014. Which means that assignment of the Exploitation Permit should occur at the latest on 29 May 2014. In this respect, we would like to draw your attention to the fact that pursuant to section 20 of the Mining Code, the Minister in charge of mining shall have a period 45 days to approve the assignment of any mining title. This means that the application for the approval of the assignment should be submitted to the Minister at least 45 days before the deadline (if any) that is imparted by Convention to the Minister for the approval of the said assignment. Pursuant to article 8.1 (a) (i) of the Convention, the State should "publish in the Official Gazette a decree of the appropriate authority, upon proposition of the Minister, an arrêté of the Minister authorizing and acknowledging the transfer of the Exploitation Permit from Cam Iron to the Mine Project...", within 45 days of the Date of Entry into Force or such longer period as may be reasonably required by the State. The Convention provides therefore for the approval and the publication of the assignment within 45 days from the Date of Entry into Force. It would therefore be advisable for the transfer and assignment of the Exploitation Permit to the Mine Project Company to occur at the latest on the Date of Entry into Force, in order to comply with the provisions of section 20 of the Mining Code.
Note on L6: Ernst & Young: According to article 9.1(a) of the Convention, the Mine Project Company would have the right to carry out Mining Operations, including the design and construction of the Mining Facilities.
Note on B8: Road Map of the Mbalam Mining Convention Article 8.1(a)(i) of the Convention requires for the approval by "a decree of the appropriate authority" or the Minister "to the extent required under the Legislation…". In fact, under section 20 of the Mining Code as in force at the Signature Date, the assignment is approved by the Minister.
Note on L8: Ernst & Young: The endorsement is deemed granted in the event the Minister does not respond within 45 days (as per Art 9.3 of the Mining Code implementation decree)
Note on B9: Road Map of the Mbalam Mining Convention The Exploitation Lease is the Project Lease granted over the Exploitation Area in accordance with the Convention. Pursuant to article 4.1(z)(ix) of the Convention, the Exploitation Lease should be executed by the Parties (that is the State and the Mine Project Company) as a Condition Precedent to the Entry into Force of the Convention. We specify that pursuant to section 68(2) of the Mining Code, the execution of the Exploitation Lease must be authorized by an order (arrêté) of the Minister in charge of mining. In other words, the authorization to sign the Exploitation Lease must be obtained before the execution thereof. According to article 68 of the Mining Code, the execution of the Exploitation Lease (by the Senior Divisional Officer and the General Manager of the Project Company) authorize the use of the land by the Mine Project Company. It results from the above that, in fact, the grant of the Exploitation Lease shall occur before the Date of the Entry into Force of the Convention, by the issuance of the arrêté of the Minister in charge of Mines authorising the signing of the Exploitation Lease and the execution thereof. However, some compliance still has to be performed even after the execution (granting) of the Exploitation Lease. The Exploitation Lease shall be registered with the tax administration (the registration does not give raise to the payment of registration duties, of which the Mine Project Company is exempted in accordance with Annex VII, article 1(c) of the Convention). Moreover, the Mine Project Company request for the registration of the lease in the land registry of the division where the land is situated. A certificate of registration of the lease shall be issued to the Mine Project Company. These are, in our view, the actions that should be performed to materialise the grant of the Exploitation Lease.
Note on D9: Road Map of the Mbalam Mining Convention The State shall: - Issue the arrêté authorizing the signing of the Exploitation Lease; - sign the Exploitation Lease with the Mine Project Company. In fact this is done during the pre-contractual phase, as per article 4(z)(ix) of the Convention. The shall also register the Exploitation Lease both with the Tax Administration and the land register. The Mine Project Company shall request for the registration the Exploitation Lease with the tax administration and the land register (article 68 of the Mining Code).
Note on B10: Road Map of the Mbalam Mining Convention Pursuant to article 29.4(a) of the Convention, prior to commencing work on the Project Area, The Mine Project Company or its Contractor or Subcontractor where the work is to be carried by any such Contractor or Subcontractor, prepare a waste management procedures and comply with such procedures while undertaking the work. When the waste management procedure is prepared by a Contractor or Subcontractor, it shall be submitted to the Mine Project Company for approval.
Note on C11: Road Map of the Mbalam Mining Convention Pursuant to section 49 of the Mining Code, the Mine Project Company must start the development works (including construction works) within not more than 2 years of the grantig of the permit
Note on K11: Ernst & Young: The Convention does not required for the delivrance by the State to Cam Iron of a Finding of Compliance for the commencement of the construction works. However, in our view, it would be advisable to request for such delivrance in order to avoid any dispute on the compliance with the provisions of section 49 of the Mining Code by the Mine Project Company
Note on B12: Road Map of the Mbalam Mining Convention In relation to Administrative and Technical Supervision and Financial Audit, the Mine Project Company is required to provide update reports relating to the Mining Operations. Under the Construction Phase, this report consist in providing to the Minister in charge of mining the activity report relating to the development works. (Art. 30.3. (a) (ii)
Note on B14: Road Map of the Mbalam Mining Convention Article 30.2 of the Convention grants to the State the right to audit and inspect for all Project Operations, including operations relating to the construction of the Mining Facilities. The purpose of the administrative supervision is to control the technical regularity of the conduct of the Project Operations, notably compliance by any Project Company (thus by the Mine Project Company with respect to the construction of Mining Facilities) with its obligations under the Environmental and Social Assessment and Management Plan, the preservation of public safety, safety and health of the personnel and compliance with the relevant Project Agreement (the Convention as far as Mining Facilities are concerned) and the Legislation. In addition to the administrative supervision, the State has the right to cause the records and books of account relating to the Project Operations to be examined by the Auditors, in accordance with the acounting procedure to be agree by the Parties prior to the Date of Entry into Force.
Note on C14: Road Map of the Mbalam Mining Convention Pursuant to article 30.2(i) of the Convention, a mutually agreed manual of procedures applicable shall be drafted under the oversee of the relevant State ministry(ies) (Ministry of finances, Ministry in charge of environment, Labour Ministry, Ministry of mines specifically). This manual will describe the procedures applicable to all Project Areas, which will reiterate the provisions of article 30 of the Convention and detail the frequency at which the Auditor can undertake the operations describe in Article 30.2 (a) to (h).
Note on B15: Road Map of the Mbalam Mining Convention Cam Iron undertakes and stands surety for the Mine Commissioning under the conditions of this Convention. Cam Iron, the Mine Project Company and the State undertake to comply with their respective obligations to cooperate to ensure Mine Commissioning
Note on C15: Road Map of the Mbalam Mining Convention The deadline for the Mine Commissioning is not provided by the Convention but stipulates that the Project Commissioning shall within 6 years following the Date of Entry into Force or such later date as otherwise agreed. Which means that Mine Comissioning shall occur before or on the date of the Project Commissioning.