## Feuil1
Monitoring Items / Categories | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party action accountable for compliance | Person in charge | Due date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Services Application | Submit a Services Application for the Reserve Expansion Capacity without prior State approval (article 18.6) | During the Expansion Stage | Mine Project Company / Cam Iron |  |  |  |  | Convention |  | Expand the Resrve Capacity | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Services Application | Right to submit a Service Application with prior State approval and Mine Project Company and Cam Iron | At any stage following the end of Stage 1 | Third Party |  |  |  |  | Convention
Services Application | Offer the ability to Expansion Capacity under restrictions contained in the Finance Documents (article 18.7) |  | Expansion Project Companies |  |  |  |  | Finance Documents
Services Application | Invite (by notice published in the national newspaper in the territory of the State) the submission of Services Applications, and all Services Applications howsoever received shall be considered within two (2) months of the closing date of that invitation. (article 18.7) | At least one (1) occasion in each two (2) year period, the first such period is to commence within the two (2) year period following the expiration of Stage 1 | Expansion Project Companies
Services Application | Submit all applications to the Feasibility Expert for a determination as to whether such Services Application is complete and sufficient to proceed with a Services Feasibility Study. |  | Applicants
Services Application | Review of all applications and decision as to whether an application may be accepted or rejected (article 18.12.1) |  | Expansion Committee |  |  |  |  | Applications made
Note on A6: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Services Application mean the application for Mineral Terminal Services or Railway Haulage services sent by Mine Project Company, Congo Iron or any Third Party to an Expansion Project Company and the State. Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Pursuant to the provisions of article 18.8 of the Convention, a Services Application must: - Be submitted in writing to the relevant Expansion Project Company(ies); and - Contain the following information: - The full name and registration details of the applicant; - The ownership structure of the applicant and the applicant’s project; - A general description of the applicant’s project; - The status of the applicant’s project feasibility study; - The status of all statutory and regulatory approvals required to be obtained in respect of the applicant’s project; - The type of iron ore product to be produced by the applicant; - The applicant’s current resource and reserve definition; - The applicant’s planned production profile (being estimated tonnage of product produced per annum, including ramp-up, and the duration of the proposed use of Railway haulage or Mineral Terminal services being applied for); - The applicant’s infrastructure requirements, including requirements for: - The Mineral Terminal Project Company to provide Mineral Terminal services; and - The Railway Project Company to provide Railway haulage services, to the applicant; - A timetable for the construction, commissioning and operation of the applicant’s project; - Details of the applicant’s proposed project financing; - Reasonably requested financial information; - An overview of any negative impact on environmental, geological and societal conditions and mitigation measures; - Such other information as the Expansion Committee, Expansion Project Companies or the State may reasonably request; and - Details of any assistance which the State has indicated it will be providing to the applicant.
Note on B6: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : However, in the event an applicant only requires either the Mineral Terminal services or the Railway haulage services, then its Services Application should make this clear.
Note on A7: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Services Application mean the application for Mineral Terminal Services or Railway Haulage services sent by Mine Project Company, Congo Iron or any Third Party to an Expansion Project Company and the State. Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Pursuant to the provisions of article 18.8 of the Convention, a Services Application must: - Be submitted in writing to the relevant Expansion Project Company(ies); and - Contain the following information: - The full name and registration details of the applicant; - The ownership structure of the applicant and the applicant’s project; - A general description of the applicant’s project; - The status of the applicant’s project feasibility study; - The status of all statutory and regulatory approvals required to be obtained in respect of the applicant’s project; - The type of iron ore product to be produced by the applicant; - The applicant’s current resource and reserve definition; - The applicant’s planned production profile (being estimated tonnage of product produced per annum, including ramp-up, and the duration of the proposed use of Railway haulage or Mineral Terminal services being applied for); - The applicant’s infrastructure requirements, including requirements for: - The Mineral Terminal Project Company to provide Mineral Terminal services; and - The Railway Project Company to provide Railway haulage services, to the applicant; - A timetable for the construction, commissioning and operation of the applicant’s project; - Details of the applicant’s proposed project financing; - Reasonably requested financial information; - An overview of any negative impact on environmental, geological and societal conditions and mitigation measures; - Such other information as the Expansion Committee, Expansion Project Companies or the State may reasonably request; and - Details of any assistance which the State has indicated it will be providing to the applicant.
Note on B7: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : The Services Application shall be delivered to the State, the Expansion Committee and the Expansion Project Companies. Any original, amended, or cancelled Services Application received by any one of the Expansion Project Companies must be forwarded to the State "as is." The Expansion Project Companies shall provide any potential applicant with the information necessary to submit a Services Application and assist applicants in preparing a Services Application.
Note on A8: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Services Application mean the application for Mineral Terminal Services or Railway Haulage services sent by Mine Project Company, Congo Iron or any Third Party to an Expansion Project Company and the State. Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Pursuant to the provisions of article 18.8 of the Convention, a Services Application must: - Be submitted in writing to the relevant Expansion Project Company(ies); and - Contain the following information: - The full name and registration details of the applicant; - The ownership structure of the applicant and the applicant’s project; - A general description of the applicant’s project; - The status of the applicant’s project feasibility study; - The status of all statutory and regulatory approvals required to be obtained in respect of the applicant’s project; - The type of iron ore product to be produced by the applicant; - The applicant’s current resource and reserve definition; - The applicant’s planned production profile (being estimated tonnage of product produced per annum, including ramp-up, and the duration of the proposed use of Railway haulage or Mineral Terminal services being applied for); - The applicant’s infrastructure requirements, including requirements for: - The Mineral Terminal Project Company to provide Mineral Terminal services; and - The Railway Project Company to provide Railway haulage services, to the applicant; - A timetable for the construction, commissioning and operation of the applicant’s project; - Details of the applicant’s proposed project financing; - Reasonably requested financial information; - An overview of any negative impact on environmental, geological and societal conditions and mitigation measures; - Such other information as the Expansion Committee, Expansion Project Companies or the State may reasonably request; and - Details of any assistance which the State has indicated it will be providing to the applicant.
Note on A9: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Services Application mean the application for Mineral Terminal Services or Railway Haulage services sent by Mine Project Company, Congo Iron or any Third Party to an Expansion Project Company and the State. Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Pursuant to the provisions of article 18.8 of the Convention, a Services Application must: - Be submitted in writing to the relevant Expansion Project Company(ies); and - Contain the following information: - The full name and registration details of the applicant; - The ownership structure of the applicant and the applicant’s project; - A general description of the applicant’s project; - The status of the applicant’s project feasibility study; - The status of all statutory and regulatory approvals required to be obtained in respect of the applicant’s project; - The type of iron ore product to be produced by the applicant; - The applicant’s current resource and reserve definition; - The applicant’s planned production profile (being estimated tonnage of product produced per annum, including ramp-up, and the duration of the proposed use of Railway haulage or Mineral Terminal services being applied for); - The applicant’s infrastructure requirements, including requirements for: - The Mineral Terminal Project Company to provide Mineral Terminal services; and - The Railway Project Company to provide Railway haulage services, to the applicant; - A timetable for the construction, commissioning and operation of the applicant’s project; - Details of the applicant’s proposed project financing; - Reasonably requested financial information; - An overview of any negative impact on environmental, geological and societal conditions and mitigation measures; - Such other information as the Expansion Committee, Expansion Project Companies or the State may reasonably request; and - Details of any assistance which the State has indicated it will be providing to the applicant.
Note on A10: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Services Application mean the application for Mineral Terminal Services or Railway Haulage services sent by Mine Project Company, Congo Iron or any Third Party to an Expansion Project Company and the State. Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Pursuant to the provisions of article 18.8 of the Convention, a Services Application must: - Be submitted in writing to the relevant Expansion Project Company(ies); and - Contain the following information: - The full name and registration details of the applicant; - The ownership structure of the applicant and the applicant’s project; - A general description of the applicant’s project; - The status of the applicant’s project feasibility study; - The status of all statutory and regulatory approvals required to be obtained in respect of the applicant’s project; - The type of iron ore product to be produced by the applicant; - The applicant’s current resource and reserve definition; - The applicant’s planned production profile (being estimated tonnage of product produced per annum, including ramp-up, and the duration of the proposed use of Railway haulage or Mineral Terminal services being applied for); - The applicant’s infrastructure requirements, including requirements for: - The Mineral Terminal Project Company to provide Mineral Terminal services; and - The Railway Project Company to provide Railway haulage services, to the applicant; - A timetable for the construction, commissioning and operation of the applicant’s project; - Details of the applicant’s proposed project financing; - Reasonably requested financial information; - An overview of any negative impact on environmental, geological and societal conditions and mitigation measures; - Such other information as the Expansion Committee, Expansion Project Companies or the State may reasonably request; and - Details of any assistance which the State has indicated it will be providing to the applicant.
Note on B10: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : If the Feasibility Expert determines that a Services Application is incomplete, it shall advise the Expansion Committee of such deficiencies and the Expansion Committee shall notify the applicant and identify to the applicant the deficiencies in the Services Application. If an applicant receives a notice of the type referred to in Article 18.10(b), then it must amend the Services Application within thirty (30) Days of its original submission otherwise it will be deemed that the applicant wishes to cancel its Services Application. On receipt of the amended Services Application the provisions of Article 18.10(a) will apply.
Note on A11: Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Services Application mean the application for Mineral Terminal Services or Railway Haulage services sent by Mine Project Company, Congo Iron or any Third Party to an Expansion Project Company and the State. Road Map of the Mbalam Mining Convention - Expansion Stage Services Application : Pursuant to the provisions of article 18.8 of the Convention, a Services Application must: - Be submitted in writing to the relevant Expansion Project Company(ies); and - Contain the following information: - The full name and registration details of the applicant; - The ownership structure of the applicant and the applicant’s project; - A general description of the applicant’s project; - The status of the applicant’s project feasibility study; - The status of all statutory and regulatory approvals required to be obtained in respect of the applicant’s project; - The type of iron ore product to be produced by the applicant; - The applicant’s current resource and reserve definition; - The applicant’s planned production profile (being estimated tonnage of product produced per annum, including ramp-up, and the duration of the proposed use of Railway haulage or Mineral Terminal services being applied for); - The applicant’s infrastructure requirements, including requirements for: - The Mineral Terminal Project Company to provide Mineral Terminal services; and - The Railway Project Company to provide Railway haulage services, to the applicant; - A timetable for the construction, commissioning and operation of the applicant’s project; - Details of the applicant’s proposed project financing; - Reasonably requested financial information; - An overview of any negative impact on environmental, geological and societal conditions and mitigation measures; - Such other information as the Expansion Committee, Expansion Project Companies or the State may reasonably request; and - Details of any assistance which the State has indicated it will be providing to the applicant.