## Feuil1
Monitoring Items/ Category (1) | Required action or operation or process (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Services Feasibility Study | Agree on a mutually acceptable independent expert - Feasibility Expert (article 18.13) | Prior to the end of Stage 1 | The State / Cam Iron |  |  |  |  | Convention |  | Receive a notice (an “Expansion Directive”) to the Project Companies instructing them to proceed with the acceptance and implementation of a request for Expansion Capacity | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Services Feasibility Study | Complete and send a copy of the Services Feasibility Study to one or more of the Expansion Committee, the Expansion Project Companies, the State and the applicant for Expansion Capacity | Upon instruction of the State | Feasibility Expert |  |  |  |  | Applicant's file request |  | Receive a notice (an “Expansion Directive”) to the Project Companies instructing them to proceed with the acceptance and implementation of a request for Expansion Capacity | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Services Feasibility Study | Approval or rejection of the applicant' request based on the results of the Feasibility Expert |  | State / Feasibility Expert |  |  |  |  | Applicant's file request |  | Receive a notice (an “Expansion Directive”) to the Project Companies instructing them to proceed with the acceptance and implementation of a request for Expansion Capacity | The State may terminate all or any part of the Project Agreements and revoke all permits, authorisations and approvals of Cam Iron and the Project Companies, and shall draw upon any Bank Guarantee, surety or other security provided under any Project Agreement, or otherwise collect compensation from Cam Iron or the applicable Project Company to indemnify it for any actual or reasonably expected Losses resulting from such Permit Withdrawal Breach / Terminate the Exploitation Permit (article 50.5.a)
Note on A6: Road Map of the Mbalam Mining Convention - Expansion Stage Services Feasibility Study : Services Feasibility study means a technical, commercial and economic feasibility study of the provision of Mineral Terminal Services, and the provision of Railway haulage services, as applied for under a Services Application. Services Feasibility Study must in particular: - Require an in-depth review of the information provided by the applicant in its Services Application; - Retermine the impact, including any anticipated delays and disruptions, of the provision of Mineral Terminal services and Railway haulage services to the applicant on: (A)the Mineral Terminal Operations, including with respect to the Environment, efficiency, reliability and safety; (B) the Mineral Terminal capital and operating costs payable by the applicant, existing users of the Mineral Terminal and the Mineral Terminal Project Company; (C) the Railway Operations, including with respect to the Environment, efficiency, reliability and safety; (D) the Railway capital and operating costs payable by the applicant, existing users of the Railway and the Railway Project Company; (E) the obligations of the Mineral Terminal Project Company to existing users of the Mineral Terminal; (F) the obligations of the Railway Project Company to existing users of the Railway; (G) the legitimate business and commercial interests of the Expansion Project Companies; (H) whether the requested Expansion Capacity will result in an increase to the aggregate tariffs paid by an existing user of the Railway and Mineral Terminal (if there is no such increase then such determination shall be referred to as a “Positive Economic Feasibility Determination”); and (I) whether the requested Expansion Capacity will result in any adverse impact (other than nominal impacts) on the Environment, efficiency, reliability and safety of the Railway Operations and Mineral Terminal Operations (which shall include whether any proposed physical collateral of rolling stock or other movable assets operated by the Expansion Project Companies for the benefit of all users and securing the financing for such requested Expansion Capacity could, upon default thereunder, reasonably be expected to result in a material adverse impact on the overall Railway and Mineral Terminal system) or the loss of capacity for existing users (if there is no such adverse impact or loss of capacity then such determination shall be referred to as a “Positive Technical Feasibility Determination”); - Identify any additional land over which an Expansion Project Company may need to obtain a Project Lease in order to ensure that company has security of title to the surface area of the land on which the Railway Facility or the Mineral Terminal Facility may need to be expanded onto in order to allow for the construction and operation of the Expansion Capacity; - Identify the statutory and regulatory approvals required to be obtained by the applicant and: - The Mineral Terminal Project Company for the provision of Mineral Terminal services; and the Railway Project Company for the provision of Railway haulage services; - Review the applicant’s financial capacity to fund the construction of any additional Railway Facility or Mineral Terminal Facility infrastructure and meet its obligations under the anticipated service agreement with respect to provision of each of: - The Mineral Terminal services; and - The Railway haulage services, to the applicant; - Review the financial capacity of the Mineral Terminal Project Company to finance the supply of Mineral Terminal services to the applicant; - Review the financial capacity of the Railway Project Company to finance the supply of Railway haulage services to the applicant; - Review current environmental, geological and social conditions and analyse the expected impact on the same of the proposed services including with respect to noise pollution, water use and availability, endangered species, archaeological remains, nuisance and job creation; - Identify the applicant’s lenders' requirements in the context of the supply of: (A) the Mineral Terminal services; and (B) the Railway haulage services, to the applicant; - Make recommendations on each of the elements described above in Article 18.13.2(d)(i) in order to contribute to the acceptance of the Service Application.; and - Include a reasonable timetable and deadlines for completing the works required to create the Expansion Capacity.
Note on B6: Road Map of the Mbalam Mining Convention - Expansion Stage Services Feasibility Study : The Feasibility Expert shall conduct completeness reviews of Services Applications pursuant to Article 18.10 and feasibility studies regarding requests for Expansion Capacity. If the State and Cam Iron have not agreed on a Feasibility Expert prior to the time the first Services Application is submitted, the State and Cam Iron shall each identify an independent expert within sixty (60) Days of submission of the Services Application, and the two independent experts will choose a third independent expert who shall be the Feasibility Expert. If a Party fails to identify an independent expert, the expert appointed by the other Party shall select the Feasibility Expert. Each of the State and Cam Iron may from time to time demand the removal of the Feasibility Expert, provided that the Feasibility Expert shall complete any Services Feasibility Studies then in progress. Upon a demand for removal of the Feasibility Expert, the State and Cam Iron shall attempt to identify a mutually acceptable replacement Feasibility Expert, but if they are unable to do so within one hundred and twenty (120) Days of the demand for removal, then the other Party shall identify a new Feasibility Expert. If directed by the Expansion Committee, the Feasibility Expert shall promptly commence the Services Feasibility Study, and shall complete and send the Services Feasibility Study to the State within a reasonable time frame from the date of receipt of such direction, having regard to the scope of work to be undertaken to produce the Services Feasibility Study.
Note on A7: Road Map of the Mbalam Mining Convention - Expansion Stage Services Feasibility Study : Services Feasibility study means a technical, commercial and economic feasibility study of the provision of Mineral Terminal Services, and the provision of Railway haulage services, as applied for under a Services Application. Services Feasibility Study must in particular: - Require an in-depth review of the information provided by the applicant in its Services Application; - Retermine the impact, including any anticipated delays and disruptions, of the provision of Mineral Terminal services and Railway haulage services to the applicant on: (A)the Mineral Terminal Operations, including with respect to the Environment, efficiency, reliability and safety; (B) the Mineral Terminal capital and operating costs payable by the applicant, existing users of the Mineral Terminal and the Mineral Terminal Project Company; (C) the Railway Operations, including with respect to the Environment, efficiency, reliability and safety; (D) the Railway capital and operating costs payable by the applicant, existing users of the Railway and the Railway Project Company; (E) the obligations of the Mineral Terminal Project Company to existing users of the Mineral Terminal; (F) the obligations of the Railway Project Company to existing users of the Railway; (G) the legitimate business and commercial interests of the Expansion Project Companies; (H) whether the requested Expansion Capacity will result in an increase to the aggregate tariffs paid by an existing user of the Railway and Mineral Terminal (if there is no such increase then such determination shall be referred to as a “Positive Economic Feasibility Determination”); and (I) whether the requested Expansion Capacity will result in any adverse impact (other than nominal impacts) on the Environment, efficiency, reliability and safety of the Railway Operations and Mineral Terminal Operations (which shall include whether any proposed physical collateral of rolling stock or other movable assets operated by the Expansion Project Companies for the benefit of all users and securing the financing for such requested Expansion Capacity could, upon default thereunder, reasonably be expected to result in a material adverse impact on the overall Railway and Mineral Terminal system) or the loss of capacity for existing users (if there is no such adverse impact or loss of capacity then such determination shall be referred to as a “Positive Technical Feasibility Determination”); - Identify any additional land over which an Expansion Project Company may need to obtain a Project Lease in order to ensure that company has security of title to the surface area of the land on which the Railway Facility or the Mineral Terminal Facility may need to be expanded onto in order to allow for the construction and operation of the Expansion Capacity; - Identify the statutory and regulatory approvals required to be obtained by the applicant and: - The Mineral Terminal Project Company for the provision of Mineral Terminal services; and the Railway Project Company for the provision of Railway haulage services; - Review the applicant’s financial capacity to fund the construction of any additional Railway Facility or Mineral Terminal Facility infrastructure and meet its obligations under the anticipated service agreement with respect to provision of each of: - The Mineral Terminal services; and - The Railway haulage services, to the applicant; - Review the financial capacity of the Mineral Terminal Project Company to finance the supply of Mineral Terminal services to the applicant; - Review the financial capacity of the Railway Project Company to finance the supply of Railway haulage services to the applicant; - Review current environmental, geological and social conditions and analyse the expected impact on the same of the proposed services including with respect to noise pollution, water use and availability, endangered species, archaeological remains, nuisance and job creation; - Identify the applicant’s lenders' requirements in the context of the supply of: (A) the Mineral Terminal services; and (B) the Railway haulage services, to the applicant; - Make recommendations on each of the elements described above in Article 18.13.2(d)(i) in order to contribute to the acceptance of the Service Application.; and - Include a reasonable timetable and deadlines for completing the works required to create the Expansion Capacity.
Note on D7: Road Map of the Mbalam Mining Convention - Expansion Stage Services Feasibility Study : The Feasibility Expert shall establish a process acceptable to the Expansion Committee, the Expansion Project Companies and the State in their reasonable discretion for the Project Companies, the applicant for Expansion Capacity and the State to provide input and comments on the Services Feasibility Study which the Feasibility Expert may consider but is not required to accept.
Note on A8: Road Map of the Mbalam Mining Convention - Expansion Stage Services Feasibility Study : Services Feasibility study means a technical, commercial and economic feasibility study of the provision of Mineral Terminal Services, and the provision of Railway haulage services, as applied for under a Services Application. Services Feasibility Study must in particular: - Require an in-depth review of the information provided by the applicant in its Services Application; - Retermine the impact, including any anticipated delays and disruptions, of the provision of Mineral Terminal services and Railway haulage services to the applicant on: (A)the Mineral Terminal Operations, including with respect to the Environment, efficiency, reliability and safety; (B) the Mineral Terminal capital and operating costs payable by the applicant, existing users of the Mineral Terminal and the Mineral Terminal Project Company; (C) the Railway Operations, including with respect to the Environment, efficiency, reliability and safety; (D) the Railway capital and operating costs payable by the applicant, existing users of the Railway and the Railway Project Company; (E) the obligations of the Mineral Terminal Project Company to existing users of the Mineral Terminal; (F) the obligations of the Railway Project Company to existing users of the Railway; (G) the legitimate business and commercial interests of the Expansion Project Companies; (H) whether the requested Expansion Capacity will result in an increase to the aggregate tariffs paid by an existing user of the Railway and Mineral Terminal (if there is no such increase then such determination shall be referred to as a “Positive Economic Feasibility Determination”); and (I) whether the requested Expansion Capacity will result in any adverse impact (other than nominal impacts) on the Environment, efficiency, reliability and safety of the Railway Operations and Mineral Terminal Operations (which shall include whether any proposed physical collateral of rolling stock or other movable assets operated by the Expansion Project Companies for the benefit of all users and securing the financing for such requested Expansion Capacity could, upon default thereunder, reasonably be expected to result in a material adverse impact on the overall Railway and Mineral Terminal system) or the loss of capacity for existing users (if there is no such adverse impact or loss of capacity then such determination shall be referred to as a “Positive Technical Feasibility Determination”); - Identify any additional land over which an Expansion Project Company may need to obtain a Project Lease in order to ensure that company has security of title to the surface area of the land on which the Railway Facility or the Mineral Terminal Facility may need to be expanded onto in order to allow for the construction and operation of the Expansion Capacity; - Identify the statutory and regulatory approvals required to be obtained by the applicant and: - The Mineral Terminal Project Company for the provision of Mineral Terminal services; and the Railway Project Company for the provision of Railway haulage services; - Review the applicant’s financial capacity to fund the construction of any additional Railway Facility or Mineral Terminal Facility infrastructure and meet its obligations under the anticipated service agreement with respect to provision of each of: - The Mineral Terminal services; and - The Railway haulage services, to the applicant; - Review the financial capacity of the Mineral Terminal Project Company to finance the supply of Mineral Terminal services to the applicant; - Review the financial capacity of the Railway Project Company to finance the supply of Railway haulage services to the applicant; - Review current environmental, geological and social conditions and analyse the expected impact on the same of the proposed services including with respect to noise pollution, water use and availability, endangered species, archaeological remains, nuisance and job creation; - Identify the applicant’s lenders' requirements in the context of the supply of: (A) the Mineral Terminal services; and (B) the Railway haulage services, to the applicant; - Make recommendations on each of the elements described above in Article 18.13.2(d)(i) in order to contribute to the acceptance of the Service Application.; and - Include a reasonable timetable and deadlines for completing the works required to create the Expansion Capacity.