## Feuil1
Monitoring Items/ Category (1) | Required action or operation or process (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Implimentation of Fund Committee | Implimentation of Fund Committee |  | Project Companies | Cam Iron | Not specified | Cam Iron and State | To be done | See the Table relating to Commitee | See the Table relating to Committee | Not Speficfied | Not Speficfied | Not Speficfied
Creation of Joint committee | Creation of Joint committee |  | State, Cam Iron | Cam Iron |  |  | To be done | (a) At least forty-five (45) Days prior to the beginning of each Calendar Year, Cam Iron shall, in consultation with the State, send to the State a proposal for funding the Joint Committee for the following Calendar Year, on the basis of the estimated operational costs, including the daily compensation of the State Representatives | The State, within forty-five (45) Days following receipt of the aforementioned proposal, shall: (i) accept this proposal; or (ii) provide its comments and recommendations to Cam Iron. (c) In case of the State’s failure to respond within the aforementioned period, the State shall be deemed to have accepted the proposal | Not Speficfied | Not Speficfied | Not Speficfied
Note on A6: Ernst & Young: See the Table relating to composition and mission of Fund Committee
Note on B6: Ernst & Young: See the Table relating to composition and mission of Fund Committee
Note on C6: Ersnt&Young: There is no date for the setting-up of the Committee. However, the first composition shall be agreed to by the Parties prior to the Date of Entry into Force, notably before May 2014
Note on A7: Ernst & Young: Please refer to article 30 and seq of The Convention and the table relating to Commity Convention.
Note on B7: Ernst & Young: Please refer to article 30 and seq of The Convention and the table relating to Commity Convention.
Note on C7: Ernst&Young: Thirty (30) Days following the Date of Entry into Force, the committee described in this Article 30.5