## Feuil1
Monitoring Items / Categories | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party action accountable for compliance | Person in charge | Due date for action | State authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comments
[8 empty] | Cam Iron | State
Blending Operations Compliance | Comply with the provisions of the Mineral Terminal Services Agreement (article 16.1(b) and (c) of the Convention) | During the term of the Mineral Terminal Services Agreement | Mine Project Company/Mineral Terminal Project Company |  |  |  | Pending | The Mineral Terminal Services Agreement |  | The requirements of the Mineral Terminal Services Agreement duly satisfied | To be provided each by the Mineral Terminal Services Agreement, the Blending Agreement and the Monitoring Agreement-Blending
| Comply with the provisions of the Blending Agreement 16.1(b) and (c) of the Convention) | During the term of the Blending Agreement | Mine Project Company/Mineral Terminal Project Company/congo Iron |  |  |  | Pending | The Blending Agreement |  | The requirements of the Blending Agreement duly satisfied
| Comply with the provisions of the Monitoring Agreement - Blending 30.6(a)(i) | During the term of the Monitoring Agreement-Blending | Cam Iron/Congo Iron/the State/the Mineral Terminal Project Company |  |  |  | Pending | The Monitoring Agreement - Blending |  | The requirements of the Monitoring Agreement-Blending duly satisfied
Note on A6: Ernst & Young: Pursuant to article 1 of the Convention, Blending Operations means the operations relating to the industrial process whereby Nabeba Ore (iron ore produced from the area covered by the Nabeba Permit in the Republic of Congo), an Other Ores (other than Nabeba Ore) (with the consent of the State) are blended with Mbalam Ore, which operations are carried out in accordance with the terms and conditions of the Convention, the Blending Agreement, and the Monitoring Agreement - Blending or such similar agreements. To recall, Blending Operations shall be carried out by the Mineral Terminal Project Company (see the definition of the Mineral Terminal Project Company according to which the Mineral Terminal Project is in charge both of the Mineral Terminal Operations and the Blending Operations). However, we would like to draw your attention to the fact that article 16.1(c) of the Convention seems to indicate that the Mine Project Company can also conduct Blending Operations within the Mineral Terminal Area under the Conditions set forth in the Mineral Terminal Services Agreement. It results from the definition of Blending Operations that such operations shall be carried out in accordance with the provisions of: - the Convention; - the Blending Agreement to be concluded between the Mine Project Company, Congo Iron and the Mineral Terminal Project Company; - the Mineral Terminal Agreement (see the definition if this agreement) - the Monitoring Agreement - Blending - the Mineral Terminal Services Agreement.
Note on B6: Road Map of the Mbalam Mining Convention - Exploitation Phase Blending Operations : The Mineral Terminal Services Agreement is the services agreement concluded between the Mineral Terminal Project Company and either the Mine Project Company or a Third Party contracting to utilise the services of the Mineral Terminal Project Company which may include a description of the tariff to be charged by the Mineral Terminal Project Company (article 1 of the Convention). Pursuant to article 16.1(c) of the Convention, the Mineral Terminal Service Agreement provide and set the framework of the conditions for the conduct by the Mine Project Company of the Blending Operations within the Mineral Terminal Area. Reference is therefore made to this agreement with respect to the requirements and compliances to be satified within the course of Blending Operations. This convention must be concluded prior to and as a Condition Precedent to the entry into force of the Convention.
Note on B7: Road Map of the Mbalam Mining Convention - Exploitation Phase Blending Operations : The Blending Agreement means the agreement relating to the Blending of Mbalam Ore from the territory covered by the Nabeba Permit to be concluded between the Mine Project Company, Congo Iron and the Mineral Terminal Project Company which will establish the provisions regarding the blending of Mbalam Ore and Nabeba Ore. As per article 16.1 (c) of the Convention, the Blending Agreement provides for, with the Mineral Terminal Services Agreement, the framework of the Conditions of conduct by the Mine Project Company of Blending Operations within the Mineral Terminal Area. This convention must be concluded prior to and as a Condition Precedent of the entry into force of the Convention.
Note on B8: Road Map of the Mbalam Mining Convention - Exploitation Phase Blending Operations : As per article 1 of the Convention, Monitoriing Agreement -Blending means the agreement relating to the rights of the State to review the Blending Operations and the right for the Mine Project Company and Congo Iron to be protected from discriminatory or disproportionate treatment with regard to Blending Operations. This Contract shall therefore be concluded between the State, Cam Iron, Congo Iron and the Mineral Terminal Project Company prior to and as a Condition Precedent of the entry into force of the Convention.