## Feuil1
Monitoring Items/ Category (1) | Required action or operation (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
| Contribuate in the Management and funding of the direct environmental and social impact by tthe creation creation of Fund Commitee |  | State, Cam Iron and Contractors and subcontractor | Cam Iron | Not specified | All the Parties | To be done | Cam Iron undertakes to make a cash contribution of twenty million (20,000,000) US Dollars per year for five (5) years commencing on the Date of Entry into Force to finance the South and East Regions Plan | The State hereby agrees to hereinafter organize the Special Development Fund. With respect to the long term funding of the development of the area impacted by the Project, the State intends to allocate thirty percent (30%) of its portion of the base charge tariff paid by Expansion Capacity users and 30% of the lease payments it receives in connection with the Mineral Terminal Site and Railway Site to fund the Special Development Fund | Not Speficfied | Not speciefied | Not specified
| The Project Companies shall also contribute or shall cause Marketing Company to contribute to the Special Development Fund (which in addition to other uses may be used for university and technical educational purposes) an amount equal to 0.75% of the gross sales price of Mbalam Ore sold (whether it is sold as part of Blended Ore or otherwise). | All the duration the project | Cam Iron, Contractors and subcontractor | Cam Iron the Project Company | Not specified | All the Parties | To be done |  |  | Not Speficfied | Not speciefied | Not specified
| Implimentation of Fund Committee | There is no date for the setting-up of the Committee. However, the first composition shall be agreed to by the Parties prior to the Date of Entry into Force, notably before May 2014 | Project Companies | Cam Iron | Not specified | Cam Iron and State | To be done | See the Table relating to Commitee | See the Table relating to Committee | Not Speficfied | Not speciefied | Not specified
| Creation of Joint committee | Thirty (30) Days following the Date of Entry into Force, the committee described in this Article 30.5 | State, Cam Iron | Cam Iron |  |  | To be done | (a) At least forty-five (45) Days prior to the beginning of each Calendar Year, Cam Iron shall, in consultation with the State, send to the State a proposal for funding the Joint Committee for the following Calendar Year, on the basis of the estimated operational costs, including the daily compensation of the State Representatives | The State, within forty-five (45) Days following receipt of the aforementioned proposal, shall: (i) accept this proposal; or (ii) provide its comments and recommendations to Cam Iron. (c) In case of the State’s failure to respond within the aforementioned period, the State shall be deemed to have accepted the proposal | Not Speficfied | Not speciefied | Not specified
| Fund the Special Development Fund | Not Specified | Cam Iron, and the Project Companies | Cam Iron and the Project Compagnies | See the date fo compliance | Cam Iron and the Project companies | To be done | Cam Iron undertakes to make a cash contribution of twenty million (20,000,000) US Dollars per year for five (5) years commencing on the Date of Entry into Force to finance the South and East Regions Plan |  | Not Speficfied |  | it's important to clarify who will finance the special development fund created by Cam Iron
Note on B6: Road Map of the Mbalam Mining Convention Please refer to Article 29.5 of the Convention
Note on J6: Road Map of the Mbalam Mining Convention According to article 29.5.1 (f),(g)(h)(i) of the Convention
Note on B8: Ernst & Young: See the Table relating to composition and mission of Fund Committee
Note on B9: Ernst & Young: Please refer to article 30 and seq of The Convention and the table relating to Commity Convention.