## Feuil1
Monitoring Items/ Category (1) | Required action or operation or process (what need to be done) | Date for compliance (timeframe, deadline) | Party accountable for compliance | Person in charge of action (CamIron/Sundance) | Due date for action | Authority accountable for compliance | Status | Input (information and documents required for compliance) |  | Output (deliverable resulting from compliance) | Risk/sanction | Comment
[8 empty] | Cam Iron | State
Mineral Terminal Facilities | Prepare a draft of the Mineral Terminal Concession to be granted to the Mineral Terminal Project Company in accordance with article 13.1(c) of the Convention. | Not specified | The State | General Manager / Operations / Legal |  | The Port Authority if the Mineral Terminal Area is located within a perimter regulated by the Port Authority | TBD | Mineral Terminal Agreement (article 1 relating to the defintion of Mineral Terminal Concession) | Mineral Terminal Agreement (article 1 relating to the defintion of Mineral Terminal Concession) | Draft the Mineral Terminal Concession
| Grant of the Mineral Terminal Concession to the Mineral Terminal Project Company (article 13.1(c). | Date of Entry into Force - May 2014 | State / but also Cam Iron (Sundance) | Sundance CFO and COO |  | Ministry of Transports | TBD |  | Reception by the State of the updated Feasibility Study / Specifications of the Dual Track Design | Ensure that criteria for Dual Track Design construction are met and meet the conditions of funding such construction
| Start of the Mineral Terminal Operations | By the date of granting of the Mineral Terminal Concession / Date when the Mineral Terminal Company becomes Party to the Convention (at the time of the incorporation at the Trade Register - article 6.4.) | Cam Iron / Project Companies
| Review of the terms of the Mineral Terminal Concession by the State and the Mineral Terminal Project Company (article 13.1(l) of the Convention | Every five (5) years, during the term of the Mineral Terminal Agreement | State / Mineral Terminal Project Company
| Complete the Mineral Terminal Project Commissioning (articles 13.1(i) and (j)) | Within 6 years following the Date of Entry into Force, which shall occur at the latest 18 months of the Signature Date (article 3.6 (a)) of the Convention) | Mineral Terminal Project Company/State
Note on A6: Road Map of the Mbalam Mining Convention - Construction Phase: Mineral Terminal means the mineral terminal dedicated to the Project, which consists of the Mineral Terminal Facilities, located in the Mineral Terminal Area, the building and operation of which is entrusted to the Mineral Terminal Project Company, under the responsibility of Cam Iron, in accordance with the provisions of this Convention and the Mineral Terminal Agreement.
Note on B6: Ernst & Young: Mineral Terminal Concession is defined under article 1 of the Convention as "a concession granted by the appropriate authority and the terms of which are set out in the Mineral Terminal Agreement". The right for the Mineral Terminal Project Company to undertake Mineral Terminal Operations including the design, construction, operation and maintenance of the Mineral Terminal Facilities, is subject to the grant to the Mineral Terminal Project Company of the Mineral Terminal Concession. In fact, article 13.1(c) states that the Mineral Terminal Project Company shall have the right to carrry out the Mineral Terminal Operations as of the later of the date when: - the Mineral Terminal Project Company becomes Party to the Convention by delivering to the State the Accession Notice in accordance with article 6.4 of the Convention. The deliverance of such executed Accession Notice is a Condition Precedent to the entry into force of the Convention and should therefore occur before the Date of Entry into Force (that is to say during the pre-contractual phase as defined in this Roadmap); - the Mineral Terminal Concession is granted to the Mineral Terminal Project Company.
Note on G6: Ernst & Young: In principle, such concessions are granted by ports authorities specially when the terminal to be constructed and operated is within a port. For example, the Kribi Port Authority is in charge of granting concession for industrial activities within the Port of Kribi, including mineral activities undertaken therein, in accordance with decree n°99/132 of 15 June 1999 relating to the organization and operation of the Port of Kribi
Note on C8: Ernst & Young: The Mineral Terminal Operations can start as from this date but this is not a deadline or time-limit to start the said operations but merely the date when the Mineral Terminal Project Company shall have the right to start Mineral Terminal Operations.
Note on B9: Road Map of the Mbalam Mining Convention - Construction Phase: This is to ensure the expectations of both Parties are being met and to otherwise take account of anticipated operating conditions for the next succeeding five (5) year period and to discuss, in good faith, opportunities to expand the Mineral Terminal to provide services for additional mines, the goal of which is increasing revenue for the Parties.
Note on C9: Ernst & Young: This means that the first review may occur before the Mineral Terminal Commissioning which may occur 6 years from the Date of Entry into Force.
Note on C10: Ernst & Young: The deadline for the Mineral Terminal Commissioning is not provided by the Convention but stipulates that the Project Commissioning shall within 6 years following the Date of Entry into Force or such later date as otherwise agreed. Which means that Mineral Terminal Comissioning shall occur before or on the date of the Project Commissioning. Please note that as per article 13.1.(j) of the Convention, the issuance by the State to the Mineral Terminal Project Company of a Finding of Compliance will constitute the Mineral Terminal Commissioning. In this respect the afore-mentioned article provides that the State may raise reservations that the Mineral Terminal has not been constructed in accordance with the Mineral Terminal Specifications. In that case, such reservations must be resolve prior to the Mineral Terminal Commissioning. The Mineral Terminal Project Company will have a period of 180 days to do the works such as to allow the removal of such reservation. An additional delay of 90 days can be added to the 180 days to the extent that the Mineral Terminal Project Company is diligently working to remove such reservations and can demontrates in good faith that the reservations cannot be resolved within the 180 day.